## Lookups
Scenario | Status | Phase | Decision Status | Risk Rating | Currency
Solo / AI-Assisted | Not Started | MVP-P0 | CONFIRMED | Critical | EGP
Lean Team | In Progress | MVP-P1 | PROPOSED | High | USD
Recommended Team | Blocked |  | TBD | Medium | AED
| Ready for QA |  | REQUIRED | Low
Done
Deferred

## Assumptions
Estimation & Delivery Assumptions
Yellow cells editable. Decision Align v1.1: Firebase-first; Daily is P0. Project start date / rates / calendar remain TBD.
Input | Value | Unit | Decision State | Scenario | FTE | Nominal h/week | Productive Factor | Effective h/week | Status
Hours per Story Point | 6 | hours/SP | PROPOSED | Solo / AI-Assisted | 1 | 40 | 0.75 | 30 | PROPOSED
Contingency | 0.15 | % | PROPOSED | Lean Team | 3 | 40 | 0.75 | 90 | PROPOSED
Working Hours / Day | 8 | hours | PROPOSED | Recommended Team | 5 | 40 | 0.75 | 150 | PROPOSED
Working Days / Week | 5 | days | PROPOSED
Productive Capacity / FTE | 0.75 | % of nominal | PROPOSED
Project Start Date |  | date | TBD
Blended Hourly Rate | 0 | selected currency/hour | TBD
Currency | EGP |  | TBD
P0 Scope | MVP-P0 (includes Daily) |  | CONFIRMED baseline
P1 Scope | Post-launch Events / remaining P1 |  | CONFIRMED Events post-launch
Decision Align v1.1 note | Always-on Azure/ASP.NET/PG infra removed from MVP estimates via E12 retarget to Firebase serverless (reallocation). No invented calendar dates. |  | CONFIRMED guidance

## Task Estimates
Task-Level Estimation Base
Derived from MVP Product Backlog / WBS after Decision Align v1.1 Firebase-first rebase. Planned Hours = Base Hours × (1+contingency). Dates/staffing TBD.
WBS | Epic ID | Epic | Item ID | Task | Phase | Decision State | Primary Role | Workstream | Story Points | Base Hours | Contingency Hours | Planned Hours | Status
002 | E01 | Product & UX Foundation | F01.1.T1 | Analysis & Design | MVP-P0 | PROPOSED | Product Owner | Product/UX | 2 | 12 | 1.8 | 13.8 | Not Started
003 | E01 | Product & UX Foundation | F01.1.T2 | Implementation | MVP-P0 | PROPOSED | Product Owner | Product/UX | 3 | 18 | 2.7 | 20.7 | Not Started
004 | E01 | Product & UX Foundation | F01.1.T3 | Validation & QA | MVP-P0 | PROPOSED | QA Engineer | Product/UX | 2 | 12 | 1.8 | 13.8 | Not Started
006 | E01 | Product & UX Foundation | F01.2.T1 | Analysis & Design | MVP-P0 | PROPOSED | UX/Game Designer | Product/UX | 3 | 18 | 2.7 | 20.7 | Not Started
007 | E01 | Product & UX Foundation | F01.2.T2 | Implementation | MVP-P0 | PROPOSED | UX/Game Designer | Product/UX | 4 | 24 | 3.6 | 27.6 | Not Started
008 | E01 | Product & UX Foundation | F01.2.T3 | Validation & QA | MVP-P0 | PROPOSED | QA Engineer | Product/UX | 3 | 18 | 2.7 | 20.7 | Not Started
010 | E01 | Product & UX Foundation | F01.3.T1 | Analysis & Design | MVP-P0 | PROPOSED | UX Designer | Product/UX | 3 | 18 | 2.7 | 20.7 | Not Started
011 | E01 | Product & UX Foundation | F01.3.T2 | Implementation | MVP-P0 | PROPOSED | UX Designer | Product/UX | 4 | 24 | 3.6 | 27.6 | Not Started
012 | E01 | Product & UX Foundation | F01.3.T3 | Validation & QA | MVP-P0 | PROPOSED | QA Engineer | Product/UX | 3 | 18 | 2.7 | 20.7 | Not Started
014 | E01 | Product & UX Foundation | F01.4.T1 | Analysis & Design | MVP-P0 | PROPOSED | UI Designer | Product/UX | 3 | 18 | 2.7 | 20.7 | Not Started
015 | E01 | Product & UX Foundation | F01.4.T2 | Implementation | MVP-P0 | PROPOSED | UI Designer | Product/UX | 4 | 24 | 3.6 | 27.6 | Not Started
016 | E01 | Product & UX Foundation | F01.4.T3 | Validation & QA | MVP-P0 | PROPOSED | QA Engineer | Product/UX | 3 | 18 | 2.7 | 20.7 | Not Started
018 | E01 | Product & UX Foundation | F01.5.T1 | Analysis & Design | MVP-P0 | PROPOSED | UX Designer | Product/UX | 2 | 12 | 1.8 | 13.8 | Not Started
019 | E01 | Product & UX Foundation | F01.5.T2 | Implementation | MVP-P0 | PROPOSED | UX Designer | Product/UX | 3 | 18 | 2.7 | 20.7 | Not Started
020 | E01 | Product & UX Foundation | F01.5.T3 | Validation & QA | MVP-P0 | PROPOSED | QA Engineer | Product/UX | 2 | 12 | 1.8 | 13.8 | Not Started
022 | E02 | Arabic Content System | F02.1.T1 | Analysis & Design | MVP-P0 | CONFIRMED/PROPOSED | Content Architect | Content | 3 | 18 | 2.7 | 20.7 | Not Started
023 | E02 | Arabic Content System | F02.1.T2 | Implementation | MVP-P0 | CONFIRMED/PROPOSED | Content Architect | Content | 4 | 24 | 3.6 | 27.6 | Not Started
024 | E02 | Arabic Content System | F02.1.T3 | Validation & QA | MVP-P0 | CONFIRMED/PROPOSED | QA Engineer | Content | 3 | 18 | 2.7 | 20.7 | Not Started
026 | E02 | Arabic Content System | F02.2.T1 | Analysis & Design | MVP-P0 | PROPOSED | Content Lead | Content | 2 | 12 | 1.8 | 13.8 | Not Started
027 | E02 | Arabic Content System | F02.2.T2 | Implementation | MVP-P0 | PROPOSED | Content Lead | Content | 3 | 18 | 2.7 | 20.7 | Not Started
028 | E02 | Arabic Content System | F02.2.T3 | Validation & QA | MVP-P0 | PROPOSED | QA Engineer | Content | 2 | 12 | 1.8 | 13.8 | Not Started
030 | E02 | Arabic Content System | F02.3.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Content Designer | Content | 3 | 18 | 2.7 | 20.7 | Not Started
031 | E02 | Arabic Content System | F02.3.T2 | Implementation | MVP-P0 | CONFIRMED | Content Designer | Content | 4 | 24 | 3.6 | 27.6 | Not Started
032 | E02 | Arabic Content System | F02.3.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Content | 3 | 18 | 2.7 | 20.7 | Not Started
034 | E02 | Arabic Content System | F02.4.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Content Designer | Content | 3 | 18 | 2.7 | 20.7 | Not Started
035 | E02 | Arabic Content System | F02.4.T2 | Implementation | MVP-P0 | CONFIRMED | Content Designer | Content | 4 | 24 | 3.6 | 27.6 | Not Started
036 | E02 | Arabic Content System | F02.4.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Content | 3 | 18 | 2.7 | 20.7 | Not Started
038 | E02 | Arabic Content System | F02.5.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Content Designer | Content | 3 | 18 | 2.7 | 20.7 | Not Started
039 | E02 | Arabic Content System | F02.5.T2 | Implementation | MVP-P0 | CONFIRMED | Content Designer | Content | 4 | 24 | 3.6 | 27.6 | Not Started
040 | E02 | Arabic Content System | F02.5.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Content | 3 | 18 | 2.7 | 20.7 | Not Started
042 | E02 | Arabic Content System | F02.6.T1 | Analysis & Design | MVP-P0 | PROPOSED | Arabic Reviewer | Content | 2 | 12 | 1.8 | 13.8 | Not Started
043 | E02 | Arabic Content System | F02.6.T2 | Implementation | MVP-P0 | PROPOSED | Arabic Reviewer | Content | 3 | 18 | 2.7 | 20.7 | Not Started
044 | E02 | Arabic Content System | F02.6.T3 | Validation & QA | MVP-P0 | PROPOSED | QA Engineer | Content | 2 | 12 | 1.8 | 13.8 | Not Started
046 | E02 | Arabic Content System | F02.7.T1 | Analysis & Design | MVP-P0 | PROPOSED | Content Engineer | Content | 3 | 18 | 2.7 | 20.7 | Not Started
047 | E02 | Arabic Content System | F02.7.T2 | Implementation | MVP-P0 | PROPOSED | Content Engineer | Content | 4 | 24 | 3.6 | 27.6 | Not Started
048 | E02 | Arabic Content System | F02.7.T3 | Validation & QA | MVP-P0 | PROPOSED | QA Engineer | Content | 3 | 18 | 2.7 | 20.7 | Not Started
050 | E02 | Arabic Content System | F02.8.T1 | Analysis & Design | MVP-P0 | TBD QUANTITY | Content Team | Content | 5 | 30 | 4.5 | 34.5 | Not Started
051 | E02 | Arabic Content System | F02.8.T2 | Implementation | MVP-P0 | TBD QUANTITY | Content Team | Content | 7 | 42 | 6.3 | 48.3 | Not Started
052 | E02 | Arabic Content System | F02.8.T3 | Validation & QA | MVP-P0 | TBD QUANTITY | QA Engineer | Content | 5 | 30 | 4.5 | 34.5 | Not Started
054 | E03 | Game Engine | F03.1.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Game Engineer | Engineering | 5 | 30 | 4.5 | 34.5 | Not Started
055 | E03 | Game Engine | F03.1.T2 | Implementation | MVP-P0 | CONFIRMED | Game Engineer | Engineering | 7 | 42 | 6.3 | 48.3 | Not Started
056 | E03 | Game Engine | F03.1.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Engineering | 5 | 30 | 4.5 | 34.5 | Not Started
058 | E03 | Game Engine | F03.2.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Game Engineer | Engineering | 5 | 30 | 4.5 | 34.5 | Not Started
059 | E03 | Game Engine | F03.2.T2 | Implementation | MVP-P0 | CONFIRMED | Game Engineer | Engineering | 7 | 42 | 6.3 | 48.3 | Not Started
060 | E03 | Game Engine | F03.2.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Engineering | 5 | 30 | 4.5 | 34.5 | Not Started
062 | E03 | Game Engine | F03.3.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Game Engineer | Engineering | 5 | 30 | 4.5 | 34.5 | Not Started
063 | E03 | Game Engine | F03.3.T2 | Implementation | MVP-P0 | CONFIRMED | Game Engineer | Engineering | 7 | 42 | 6.3 | 48.3 | Not Started
064 | E03 | Game Engine | F03.3.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Engineering | 5 | 30 | 4.5 | 34.5 | Not Started
066 | E03 | Game Engine | F03.4.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Game Engineer | Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
067 | E03 | Game Engine | F03.4.T2 | Implementation | MVP-P0 | CONFIRMED | Game Engineer | Engineering | 4 | 24 | 3.6 | 27.6 | Not Started
068 | E03 | Game Engine | F03.4.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
070 | E03 | Game Engine | F03.5.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Game Engineer | Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
071 | E03 | Game Engine | F03.5.T2 | Implementation | MVP-P0 | CONFIRMED | Game Engineer | Engineering | 4 | 24 | 3.6 | 27.6 | Not Started
072 | E03 | Game Engine | F03.5.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
074 | E03 | Game Engine | F03.6.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Game Engineer | Engineering | 5 | 30 | 4.5 | 34.5 | Not Started
075 | E03 | Game Engine | F03.6.T2 | Implementation | MVP-P0 | CONFIRMED | Game Engineer | Engineering | 7 | 42 | 6.3 | 48.3 | Not Started
076 | E03 | Game Engine | F03.6.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Engineering | 5 | 30 | 4.5 | 34.5 | Not Started
078 | E03 | Game Engine | F03.7.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Game Engineer | Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
079 | E03 | Game Engine | F03.7.T2 | Implementation | MVP-P0 | CONFIRMED | Game Engineer | Engineering | 4 | 24 | 3.6 | 27.6 | Not Started
080 | E03 | Game Engine | F03.7.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
082 | E03 | Game Engine | F03.8.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Game Engineer | Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
083 | E03 | Game Engine | F03.8.T2 | Implementation | MVP-P0 | CONFIRMED | Game Engineer | Engineering | 4 | 24 | 3.6 | 27.6 | Not Started
084 | E03 | Game Engine | F03.8.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
086 | E03 | Game Engine | F03.9.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Game Engineer | Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
087 | E03 | Game Engine | F03.9.T2 | Implementation | MVP-P0 | CONFIRMED | Game Engineer | Engineering | 4 | 24 | 3.6 | 27.6 | Not Started
088 | E03 | Game Engine | F03.9.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
090 | E03 | Game Engine | F03.10.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Game Engineer | Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
091 | E03 | Game Engine | F03.10.T2 | Implementation | MVP-P0 | CONFIRMED | Game Engineer | Engineering | 4 | 24 | 3.6 | 27.6 | Not Started
092 | E03 | Game Engine | F03.10.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
094 | E03 | Game Engine | F03.11.T1 | Analysis & Design | MVP-P0 | PROPOSED | Game Engineer | Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
095 | E03 | Game Engine | F03.11.T2 | Implementation | MVP-P0 | PROPOSED | Game Engineer | Engineering | 4 | 24 | 3.6 | 27.6 | Not Started
096 | E03 | Game Engine | F03.11.T3 | Validation & QA | MVP-P0 | PROPOSED | QA Engineer | Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
098 | E03 | Game Engine | F03.12.T1 | Analysis & Design | MVP-P0 | PROPOSED | Game Engineer | Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
099 | E03 | Game Engine | F03.12.T2 | Implementation | MVP-P0 | PROPOSED | Game Engineer | Engineering | 4 | 24 | 3.6 | 27.6 | Not Started
100 | E03 | Game Engine | F03.12.T3 | Validation & QA | MVP-P0 | PROPOSED | QA Engineer | Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
102 | E04 | Solver | F04.1.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Solver Engineer | Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
103 | E04 | Solver | F04.1.T2 | Implementation | MVP-P0 | CONFIRMED | Solver Engineer | Engineering | 4 | 24 | 3.6 | 27.6 | Not Started
104 | E04 | Solver | F04.1.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
106 | E04 | Solver | F04.2.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Solver Engineer | Engineering | 5 | 30 | 4.5 | 34.5 | Not Started
107 | E04 | Solver | F04.2.T2 | Implementation | MVP-P0 | CONFIRMED | Solver Engineer | Engineering | 7 | 42 | 6.3 | 48.3 | Not Started
108 | E04 | Solver | F04.2.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Engineering | 5 | 30 | 4.5 | 34.5 | Not Started
110 | E04 | Solver | F04.3.T1 | Analysis & Design | MVP-P0 | PROPOSED | Solver Engineer | Engineering | 5 | 30 | 4.5 | 34.5 | Not Started
111 | E04 | Solver | F04.3.T2 | Implementation | MVP-P0 | PROPOSED | Solver Engineer | Engineering | 7 | 42 | 6.3 | 48.3 | Not Started
112 | E04 | Solver | F04.3.T3 | Validation & QA | MVP-P0 | PROPOSED | QA Engineer | Engineering | 5 | 30 | 4.5 | 34.5 | Not Started
114 | E04 | Solver | F04.4.T1 | Analysis & Design | MVP-P0 | PROPOSED | Solver Engineer | Engineering | 5 | 30 | 4.5 | 34.5 | Not Started
115 | E04 | Solver | F04.4.T2 | Implementation | MVP-P0 | PROPOSED | Solver Engineer | Engineering | 7 | 42 | 6.3 | 48.3 | Not Started
116 | E04 | Solver | F04.4.T3 | Validation & QA | MVP-P0 | PROPOSED | QA Engineer | Engineering | 5 | 30 | 4.5 | 34.5 | Not Started
118 | E04 | Solver | F04.5.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Solver Engineer | Engineering | 5 | 30 | 4.5 | 34.5 | Not Started
119 | E04 | Solver | F04.5.T2 | Implementation | MVP-P0 | CONFIRMED | Solver Engineer | Engineering | 7 | 42 | 6.3 | 48.3 | Not Started
120 | E04 | Solver | F04.5.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Engineering | 5 | 30 | 4.5 | 34.5 | Not Started
122 | E04 | Solver | F04.6.T1 | Analysis & Design | MVP-P0 | CONFIRMED/TBD | Solver Engineer | Engineering | 5 | 30 | 4.5 | 34.5 | Not Started
123 | E04 | Solver | F04.6.T2 | Implementation | MVP-P0 | CONFIRMED/TBD | Solver Engineer | Engineering | 7 | 42 | 6.3 | 48.3 | Not Started
124 | E04 | Solver | F04.6.T3 | Validation & QA | MVP-P0 | CONFIRMED/TBD | QA Engineer | Engineering | 5 | 30 | 4.5 | 34.5 | Not Started
126 | E04 | Solver | F04.7.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Solver Engineer | Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
127 | E04 | Solver | F04.7.T2 | Implementation | MVP-P0 | CONFIRMED | Solver Engineer | Engineering | 4 | 24 | 3.6 | 27.6 | Not Started
128 | E04 | Solver | F04.7.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
130 | E04 | Solver | F04.8.T1 | Analysis & Design | MVP-P0 | CONFIRMED/TBD | Solver Engineer | Engineering | 5 | 30 | 4.5 | 34.5 | Not Started
131 | E04 | Solver | F04.8.T2 | Implementation | MVP-P0 | CONFIRMED/TBD | Solver Engineer | Engineering | 7 | 42 | 6.3 | 48.3 | Not Started
132 | E04 | Solver | F04.8.T3 | Validation & QA | MVP-P0 | CONFIRMED/TBD | QA Engineer | Engineering | 5 | 30 | 4.5 | 34.5 | Not Started
134 | E04 | Solver | F04.9.T1 | Analysis & Design | MVP-P0 | PROPOSED | Solver Engineer | Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
135 | E04 | Solver | F04.9.T2 | Implementation | MVP-P0 | PROPOSED | Solver Engineer | Engineering | 4 | 24 | 3.6 | 27.6 | Not Started
136 | E04 | Solver | F04.9.T3 | Validation & QA | MVP-P0 | PROPOSED | QA Engineer | Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
138 | E04 | Solver | F04.10.T1 | Analysis & Design | MVP-P0 | PROPOSED | Solver Engineer | Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
139 | E04 | Solver | F04.10.T2 | Implementation | MVP-P0 | PROPOSED | Solver Engineer | Engineering | 4 | 24 | 3.6 | 27.6 | Not Started
140 | E04 | Solver | F04.10.T3 | Validation & QA | MVP-P0 | PROPOSED | QA Engineer | Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
142 | E05 | Level Generator & Difficulty | F05.1.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Game Designer/Engineer | Game Design/Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
143 | E05 | Level Generator & Difficulty | F05.1.T2 | Implementation | MVP-P0 | CONFIRMED | Game Designer/Engineer | Game Design/Engineering | 4 | 24 | 3.6 | 27.6 | Not Started
144 | E05 | Level Generator & Difficulty | F05.1.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Game Design/Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
146 | E05 | Level Generator & Difficulty | F05.2.T1 | Analysis & Design | MVP-P0 | PROPOSED | Game Engineer | Game Design/Engineering | 5 | 30 | 4.5 | 34.5 | Not Started
147 | E05 | Level Generator & Difficulty | F05.2.T2 | Implementation | MVP-P0 | PROPOSED | Game Engineer | Game Design/Engineering | 7 | 42 | 6.3 | 48.3 | Not Started
148 | E05 | Level Generator & Difficulty | F05.2.T3 | Validation & QA | MVP-P0 | PROPOSED | QA Engineer | Game Design/Engineering | 5 | 30 | 4.5 | 34.5 | Not Started
150 | E05 | Level Generator & Difficulty | F05.3.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Game Engineer | Game Design/Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
151 | E05 | Level Generator & Difficulty | F05.3.T2 | Implementation | MVP-P0 | CONFIRMED | Game Engineer | Game Design/Engineering | 4 | 24 | 3.6 | 27.6 | Not Started
152 | E05 | Level Generator & Difficulty | F05.3.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Game Design/Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
154 | E05 | Level Generator & Difficulty | F05.4.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Game Engineer | Game Design/Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
155 | E05 | Level Generator & Difficulty | F05.4.T2 | Implementation | MVP-P0 | CONFIRMED | Game Engineer | Game Design/Engineering | 4 | 24 | 3.6 | 27.6 | Not Started
156 | E05 | Level Generator & Difficulty | F05.4.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Game Design/Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
158 | E05 | Level Generator & Difficulty | F05.5.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Game Engineer | Game Design/Engineering | 5 | 30 | 4.5 | 34.5 | Not Started
159 | E05 | Level Generator & Difficulty | F05.5.T2 | Implementation | MVP-P0 | CONFIRMED | Game Engineer | Game Design/Engineering | 7 | 42 | 6.3 | 48.3 | Not Started
160 | E05 | Level Generator & Difficulty | F05.5.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Game Design/Engineering | 5 | 30 | 4.5 | 34.5 | Not Started
162 | E05 | Level Generator & Difficulty | F05.6.T1 | Analysis & Design | MVP-P0 | PROPOSED | Game Engineer | Game Design/Engineering | 5 | 30 | 4.5 | 34.5 | Not Started
163 | E05 | Level Generator & Difficulty | F05.6.T2 | Implementation | MVP-P0 | PROPOSED | Game Engineer | Game Design/Engineering | 7 | 42 | 6.3 | 48.3 | Not Started
164 | E05 | Level Generator & Difficulty | F05.6.T3 | Validation & QA | MVP-P0 | PROPOSED | QA Engineer | Game Design/Engineering | 5 | 30 | 4.5 | 34.5 | Not Started
166 | E05 | Level Generator & Difficulty | F05.7.T1 | Analysis & Design | MVP-P0 | CONFIRMED/PROPOSED | Game Engineer | Game Design/Engineering | 2 | 12 | 1.8 | 13.8 | Not Started
167 | E05 | Level Generator & Difficulty | F05.7.T2 | Implementation | MVP-P0 | CONFIRMED/PROPOSED | Game Engineer | Game Design/Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
168 | E05 | Level Generator & Difficulty | F05.7.T3 | Validation & QA | MVP-P0 | CONFIRMED/PROPOSED | QA Engineer | Game Design/Engineering | 2 | 12 | 1.8 | 13.8 | Not Started
170 | E05 | Level Generator & Difficulty | F05.8.T1 | Analysis & Design | MVP-P0 | CONFIRMED CONCEPT | Game Engineer | Game Design/Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
171 | E05 | Level Generator & Difficulty | F05.8.T2 | Implementation | MVP-P0 | CONFIRMED CONCEPT | Game Engineer | Game Design/Engineering | 4 | 24 | 3.6 | 27.6 | Not Started
172 | E05 | Level Generator & Difficulty | F05.8.T3 | Validation & QA | MVP-P0 | CONFIRMED CONCEPT | QA Engineer | Game Design/Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
174 | E05 | Level Generator & Difficulty | F05.9.T1 | Analysis & Design | MVP-P0 | CONFIRMED | QA/Solver Engineer | Game Design/Engineering | 5 | 30 | 4.5 | 34.5 | Not Started
175 | E05 | Level Generator & Difficulty | F05.9.T2 | Implementation | MVP-P0 | CONFIRMED | QA/Solver Engineer | Game Design/Engineering | 7 | 42 | 6.3 | 48.3 | Not Started
176 | E05 | Level Generator & Difficulty | F05.9.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Game Design/Engineering | 5 | 30 | 4.5 | 34.5 | Not Started
178 | E05 | Level Generator & Difficulty | F05.10.T1 | Analysis & Design | MVP-P0 | TBD | Game Engineer | Game Design/Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
179 | E05 | Level Generator & Difficulty | F05.10.T2 | Implementation | MVP-P0 | TBD | Game Engineer | Game Design/Engineering | 4 | 24 | 3.6 | 27.6 | Not Started
180 | E05 | Level Generator & Difficulty | F05.10.T3 | Validation & QA | MVP-P0 | TBD | QA Engineer | Game Design/Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
182 | E06 | Tutorial & Onboarding | F06.1.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Product Engineer | Product/UX | 2 | 12 | 1.8 | 13.8 | Not Started
183 | E06 | Tutorial & Onboarding | F06.1.T2 | Implementation | MVP-P0 | CONFIRMED | Product Engineer | Product/UX | 3 | 18 | 2.7 | 20.7 | Not Started
184 | E06 | Tutorial & Onboarding | F06.1.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/UX | 2 | 12 | 1.8 | 13.8 | Not Started
186 | E06 | Tutorial & Onboarding | F06.2.T1 | Analysis & Design | MVP-P0 | PROPOSED | Game Engineer | Product/UX | 3 | 18 | 2.7 | 20.7 | Not Started
187 | E06 | Tutorial & Onboarding | F06.2.T2 | Implementation | MVP-P0 | PROPOSED | Game Engineer | Product/UX | 4 | 24 | 3.6 | 27.6 | Not Started
188 | E06 | Tutorial & Onboarding | F06.2.T3 | Validation & QA | MVP-P0 | PROPOSED | QA Engineer | Product/UX | 3 | 18 | 2.7 | 20.7 | Not Started
190 | E06 | Tutorial & Onboarding | F06.3.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Game Designer | Product/UX | 3 | 18 | 2.7 | 20.7 | Not Started
191 | E06 | Tutorial & Onboarding | F06.3.T2 | Implementation | MVP-P0 | CONFIRMED | Game Designer | Product/UX | 4 | 24 | 3.6 | 27.6 | Not Started
192 | E06 | Tutorial & Onboarding | F06.3.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/UX | 3 | 18 | 2.7 | 20.7 | Not Started
194 | E06 | Tutorial & Onboarding | F06.4.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Game Designer | Product/UX | 3 | 18 | 2.7 | 20.7 | Not Started
195 | E06 | Tutorial & Onboarding | F06.4.T2 | Implementation | MVP-P0 | CONFIRMED | Game Designer | Product/UX | 4 | 24 | 3.6 | 27.6 | Not Started
196 | E06 | Tutorial & Onboarding | F06.4.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/UX | 3 | 18 | 2.7 | 20.7 | Not Started
198 | E06 | Tutorial & Onboarding | F06.5.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Game Designer | Product/UX | 3 | 18 | 2.7 | 20.7 | Not Started
199 | E06 | Tutorial & Onboarding | F06.5.T2 | Implementation | MVP-P0 | CONFIRMED | Game Designer | Product/UX | 4 | 24 | 3.6 | 27.6 | Not Started
200 | E06 | Tutorial & Onboarding | F06.5.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/UX | 3 | 18 | 2.7 | 20.7 | Not Started
202 | E06 | Tutorial & Onboarding | F06.6.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Game Designer | Product/UX | 3 | 18 | 2.7 | 20.7 | Not Started
203 | E06 | Tutorial & Onboarding | F06.6.T2 | Implementation | MVP-P0 | CONFIRMED | Game Designer | Product/UX | 4 | 24 | 3.6 | 27.6 | Not Started
204 | E06 | Tutorial & Onboarding | F06.6.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/UX | 3 | 18 | 2.7 | 20.7 | Not Started
206 | E06 | Tutorial & Onboarding | F06.7.T1 | Analysis & Design | MVP-P0 | PROPOSED | Analytics Engineer | Product/UX | 2 | 12 | 1.8 | 13.8 | Not Started
207 | E06 | Tutorial & Onboarding | F06.7.T2 | Implementation | MVP-P0 | PROPOSED | Analytics Engineer | Product/UX | 3 | 18 | 2.7 | 20.7 | Not Started
208 | E06 | Tutorial & Onboarding | F06.7.T3 | Validation & QA | MVP-P0 | PROPOSED | QA Engineer | Product/UX | 2 | 12 | 1.8 | 13.8 | Not Started
210 | E07 | Main Journey & Chapters | F07.1.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Product Engineer | Product/Game Design | 3 | 18 | 2.7 | 20.7 | Not Started
211 | E07 | Main Journey & Chapters | F07.1.T2 | Implementation | MVP-P0 | CONFIRMED | Product Engineer | Product/Game Design | 4 | 24 | 3.6 | 27.6 | Not Started
212 | E07 | Main Journey & Chapters | F07.1.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/Game Design | 3 | 18 | 2.7 | 20.7 | Not Started
214 | E07 | Main Journey & Chapters | F07.2.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Product Engineer | Product/Game Design | 2 | 12 | 1.8 | 13.8 | Not Started
215 | E07 | Main Journey & Chapters | F07.2.T2 | Implementation | MVP-P0 | CONFIRMED | Product Engineer | Product/Game Design | 3 | 18 | 2.7 | 20.7 | Not Started
216 | E07 | Main Journey & Chapters | F07.2.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/Game Design | 2 | 12 | 1.8 | 13.8 | Not Started
218 | E07 | Main Journey & Chapters | F07.3.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Product Engineer | Product/Game Design | 3 | 18 | 2.7 | 20.7 | Not Started
219 | E07 | Main Journey & Chapters | F07.3.T2 | Implementation | MVP-P0 | CONFIRMED | Product Engineer | Product/Game Design | 4 | 24 | 3.6 | 27.6 | Not Started
220 | E07 | Main Journey & Chapters | F07.3.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/Game Design | 3 | 18 | 2.7 | 20.7 | Not Started
222 | E07 | Main Journey & Chapters | F07.4.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Product Engineer | Product/Game Design | 3 | 18 | 2.7 | 20.7 | Not Started
223 | E07 | Main Journey & Chapters | F07.4.T2 | Implementation | MVP-P0 | CONFIRMED | Product Engineer | Product/Game Design | 4 | 24 | 3.6 | 27.6 | Not Started
224 | E07 | Main Journey & Chapters | F07.4.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/Game Design | 3 | 18 | 2.7 | 20.7 | Not Started
226 | E07 | Main Journey & Chapters | F07.5.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Product Engineer | Product/Game Design | 3 | 18 | 2.7 | 20.7 | Not Started
227 | E07 | Main Journey & Chapters | F07.5.T2 | Implementation | MVP-P0 | CONFIRMED | Product Engineer | Product/Game Design | 4 | 24 | 3.6 | 27.6 | Not Started
228 | E07 | Main Journey & Chapters | F07.5.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/Game Design | 3 | 18 | 2.7 | 20.7 | Not Started
230 | E07 | Main Journey & Chapters | F07.6.T1 | Analysis & Design | MVP-P0 | CONFIRMED CONCEPT | Game Designer | Product/Game Design | 3 | 18 | 2.7 | 20.7 | Not Started
231 | E07 | Main Journey & Chapters | F07.6.T2 | Implementation | MVP-P0 | CONFIRMED CONCEPT | Game Designer | Product/Game Design | 4 | 24 | 3.6 | 27.6 | Not Started
232 | E07 | Main Journey & Chapters | F07.6.T3 | Validation & QA | MVP-P0 | CONFIRMED CONCEPT | QA Engineer | Product/Game Design | 3 | 18 | 2.7 | 20.7 | Not Started
234 | E07 | Main Journey & Chapters | F07.7.T1 | Analysis & Design | MVP-P0 | PROPOSED UX | UI Engineer | Product/Game Design | 5 | 30 | 4.5 | 34.5 | Not Started
235 | E07 | Main Journey & Chapters | F07.7.T2 | Implementation | MVP-P0 | PROPOSED UX | UI Engineer | Product/Game Design | 7 | 42 | 6.3 | 48.3 | Not Started
236 | E07 | Main Journey & Chapters | F07.7.T3 | Validation & QA | MVP-P0 | PROPOSED UX | QA Engineer | Product/Game Design | 5 | 30 | 4.5 | 34.5 | Not Started
238 | E08 | Economy & Rewards | F08.1.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Backend Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
239 | E08 | Economy & Rewards | F08.1.T2 | Implementation | MVP-P0 | CONFIRMED | Backend Engineer | Product/Backend | 4 | 24 | 3.6 | 27.6 | Not Started
240 | E08 | Economy & Rewards | F08.1.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
242 | E08 | Economy & Rewards | F08.2.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Game/Backend Engineer | Product/Backend | 2 | 12 | 1.8 | 13.8 | Not Started
243 | E08 | Economy & Rewards | F08.2.T2 | Implementation | MVP-P0 | CONFIRMED | Game/Backend Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
244 | E08 | Economy & Rewards | F08.2.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/Backend | 2 | 12 | 1.8 | 13.8 | Not Started
246 | E08 | Economy & Rewards | F08.3.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Backend Engineer | Product/Backend | 2 | 12 | 1.8 | 13.8 | Not Started
247 | E08 | Economy & Rewards | F08.3.T2 | Implementation | MVP-P0 | CONFIRMED | Backend Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
248 | E08 | Economy & Rewards | F08.3.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/Backend | 2 | 12 | 1.8 | 13.8 | Not Started
250 | E08 | Economy & Rewards | F08.4.T1 | Analysis & Design | MVP-P0 | PROPOSED ARCH | Backend Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
251 | E08 | Economy & Rewards | F08.4.T2 | Implementation | MVP-P0 | PROPOSED ARCH | Backend Engineer | Product/Backend | 4 | 24 | 3.6 | 27.6 | Not Started
252 | E08 | Economy & Rewards | F08.4.T3 | Validation & QA | MVP-P0 | PROPOSED ARCH | QA Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
254 | E08 | Economy & Rewards | F08.5.T1 | Analysis & Design | MVP-P0 | PROPOSED | Backend Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
255 | E08 | Economy & Rewards | F08.5.T2 | Implementation | MVP-P0 | PROPOSED | Backend Engineer | Product/Backend | 4 | 24 | 3.6 | 27.6 | Not Started
256 | E08 | Economy & Rewards | F08.5.T3 | Validation & QA | MVP-P0 | PROPOSED | QA Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
258 | E08 | Economy & Rewards | F08.6.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Analytics Engineer | Product/Backend | 2 | 12 | 1.8 | 13.8 | Not Started
259 | E08 | Economy & Rewards | F08.6.T2 | Implementation | MVP-P0 | CONFIRMED | Analytics Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
260 | E08 | Economy & Rewards | F08.6.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/Backend | 2 | 12 | 1.8 | 13.8 | Not Started
262 | E09 | Gameplay Assistance & Recovery | F09.1.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Product Engineer | Engineering/Product | 3 | 18 | 2.7 | 20.7 | Not Started
263 | E09 | Gameplay Assistance & Recovery | F09.1.T2 | Implementation | MVP-P0 | CONFIRMED | Product Engineer | Engineering/Product | 4 | 24 | 3.6 | 27.6 | Not Started
264 | E09 | Gameplay Assistance & Recovery | F09.1.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Engineering/Product | 3 | 18 | 2.7 | 20.7 | Not Started
266 | E09 | Gameplay Assistance & Recovery | F09.2.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Product Engineer | Engineering/Product | 3 | 18 | 2.7 | 20.7 | Not Started
267 | E09 | Gameplay Assistance & Recovery | F09.2.T2 | Implementation | MVP-P0 | CONFIRMED | Product Engineer | Engineering/Product | 4 | 24 | 3.6 | 27.6 | Not Started
268 | E09 | Gameplay Assistance & Recovery | F09.2.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Engineering/Product | 3 | 18 | 2.7 | 20.7 | Not Started
270 | E09 | Gameplay Assistance & Recovery | F09.3.T1 | Analysis & Design | MVP-P0 | CONFIRMED | UI Engineer | Engineering/Product | 2 | 12 | 1.8 | 13.8 | Not Started
271 | E09 | Gameplay Assistance & Recovery | F09.3.T2 | Implementation | MVP-P0 | CONFIRMED | UI Engineer | Engineering/Product | 3 | 18 | 2.7 | 20.7 | Not Started
272 | E09 | Gameplay Assistance & Recovery | F09.3.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Engineering/Product | 2 | 12 | 1.8 | 13.8 | Not Started
274 | E09 | Gameplay Assistance & Recovery | F09.4.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Game Engineer | Engineering/Product | 2 | 12 | 1.8 | 13.8 | Not Started
275 | E09 | Gameplay Assistance & Recovery | F09.4.T2 | Implementation | MVP-P0 | CONFIRMED | Game Engineer | Engineering/Product | 3 | 18 | 2.7 | 20.7 | Not Started
276 | E09 | Gameplay Assistance & Recovery | F09.4.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Engineering/Product | 2 | 12 | 1.8 | 13.8 | Not Started
278 | E09 | Gameplay Assistance & Recovery | F09.5.T1 | Analysis & Design | MVP-P0 | CONFIRMED | UI Engineer | Engineering/Product | 2 | 12 | 1.8 | 13.8 | Not Started
279 | E09 | Gameplay Assistance & Recovery | F09.5.T2 | Implementation | MVP-P0 | CONFIRMED | UI Engineer | Engineering/Product | 3 | 18 | 2.7 | 20.7 | Not Started
280 | E09 | Gameplay Assistance & Recovery | F09.5.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Engineering/Product | 2 | 12 | 1.8 | 13.8 | Not Started
282 | E09 | Gameplay Assistance & Recovery | F09.6.T1 | Analysis & Design | MVP-P0 | TBD BEHAVIOR | Game Engineer | Engineering/Product | 3 | 18 | 2.7 | 20.7 | Not Started
283 | E09 | Gameplay Assistance & Recovery | F09.6.T2 | Implementation | MVP-P0 | TBD BEHAVIOR | Game Engineer | Engineering/Product | 4 | 24 | 3.6 | 27.6 | Not Started
284 | E09 | Gameplay Assistance & Recovery | F09.6.T3 | Validation & QA | MVP-P0 | TBD BEHAVIOR | QA Engineer | Engineering/Product | 3 | 18 | 2.7 | 20.7 | Not Started
286 | E09 | Gameplay Assistance & Recovery | F09.7.T1 | Analysis & Design | MVP-P0 | PROPOSED | Backend Engineer | Engineering/Product | 2 | 12 | 1.8 | 13.8 | Not Started
287 | E09 | Gameplay Assistance & Recovery | F09.7.T2 | Implementation | MVP-P0 | PROPOSED | Backend Engineer | Engineering/Product | 3 | 18 | 2.7 | 20.7 | Not Started
288 | E09 | Gameplay Assistance & Recovery | F09.7.T3 | Validation & QA | MVP-P0 | PROPOSED | QA Engineer | Engineering/Product | 2 | 12 | 1.8 | 13.8 | Not Started
290 | E10 | Monetization | F10.1.T1 | Analysis & Design | MVP-P0 | CONFIRMED/PROPOSED ARCH | Mobile Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
291 | E10 | Monetization | F10.1.T2 | Implementation | MVP-P0 | CONFIRMED/PROPOSED ARCH | Mobile Engineer | Product/Backend | 4 | 24 | 3.6 | 27.6 | Not Started
292 | E10 | Monetization | F10.1.T3 | Validation & QA | MVP-P0 | CONFIRMED/PROPOSED ARCH | QA Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
294 | E10 | Monetization | F10.2.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Mobile/Backend Engineer | Product/Backend | 2 | 12 | 1.8 | 13.8 | Not Started
295 | E10 | Monetization | F10.2.T2 | Implementation | MVP-P0 | CONFIRMED | Mobile/Backend Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
296 | E10 | Monetization | F10.2.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/Backend | 2 | 12 | 1.8 | 13.8 | Not Started
298 | E10 | Monetization | F10.3.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Mobile/Backend Engineer | Product/Backend | 2 | 12 | 1.8 | 13.8 | Not Started
299 | E10 | Monetization | F10.3.T2 | Implementation | MVP-P0 | CONFIRMED | Mobile/Backend Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
300 | E10 | Monetization | F10.3.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/Backend | 2 | 12 | 1.8 | 13.8 | Not Started
302 | E10 | Monetization | F10.4.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Mobile/Backend Engineer | Product/Backend | 2 | 12 | 1.8 | 13.8 | Not Started
303 | E10 | Monetization | F10.4.T2 | Implementation | MVP-P0 | CONFIRMED | Mobile/Backend Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
304 | E10 | Monetization | F10.4.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/Backend | 2 | 12 | 1.8 | 13.8 | Not Started
306 | E10 | Monetization | F10.5.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Mobile/Backend Engineer | Product/Backend | 2 | 12 | 1.8 | 13.8 | Not Started
307 | E10 | Monetization | F10.5.T2 | Implementation | MVP-P0 | CONFIRMED | Mobile/Backend Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
308 | E10 | Monetization | F10.5.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/Backend | 2 | 12 | 1.8 | 13.8 | Not Started
310 | E10 | Monetization | F10.6.T1 | Analysis & Design | MVP-P0 | CONFIRMED CONCEPT | Product Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
311 | E10 | Monetization | F10.6.T2 | Implementation | MVP-P0 | CONFIRMED CONCEPT | Product Engineer | Product/Backend | 4 | 24 | 3.6 | 27.6 | Not Started
312 | E10 | Monetization | F10.6.T3 | Validation & QA | MVP-P0 | CONFIRMED CONCEPT | QA Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
314 | E10 | Monetization | F10.7.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Backend/Mobile Engineer | Product/Backend | 2 | 12 | 1.8 | 13.8 | Not Started
315 | E10 | Monetization | F10.7.T2 | Implementation | MVP-P0 | CONFIRMED | Backend/Mobile Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
316 | E10 | Monetization | F10.7.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/Backend | 2 | 12 | 1.8 | 13.8 | Not Started
318 | E10 | Monetization | F10.8.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Mobile Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
319 | E10 | Monetization | F10.8.T2 | Implementation | MVP-P0 | CONFIRMED | Mobile Engineer | Product/Backend | 4 | 24 | 3.6 | 27.6 | Not Started
320 | E10 | Monetization | F10.8.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
322 | E10 | Monetization | F10.9.T1 | Analysis & Design | MVP-P0 | PROPOSED ARCH | Backend Engineer | Product/Backend | 5 | 30 | 4.5 | 34.5 | Not Started
323 | E10 | Monetization | F10.9.T2 | Implementation | MVP-P0 | PROPOSED ARCH | Backend Engineer | Product/Backend | 7 | 42 | 6.3 | 48.3 | Not Started
324 | E10 | Monetization | F10.9.T3 | Validation & QA | MVP-P0 | PROPOSED ARCH | QA Engineer | Product/Backend | 5 | 30 | 4.5 | 34.5 | Not Started
326 | E10 | Monetization | F10.10.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Mobile/Backend Engineer | Product/Backend | 2 | 12 | 1.8 | 13.8 | Not Started
327 | E10 | Monetization | F10.10.T2 | Implementation | MVP-P0 | CONFIRMED | Mobile/Backend Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
328 | E10 | Monetization | F10.10.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/Backend | 2 | 12 | 1.8 | 13.8 | Not Started
330 | E10 | Monetization | F10.11.T1 | Analysis & Design | MVP-P0 | CONFIRMED SCOPE | UI Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
331 | E10 | Monetization | F10.11.T2 | Implementation | MVP-P0 | CONFIRMED SCOPE | UI Engineer | Product/Backend | 4 | 24 | 3.6 | 27.6 | Not Started
332 | E10 | Monetization | F10.11.T3 | Validation & QA | MVP-P0 | CONFIRMED SCOPE | QA Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
334 | E11 | Identity, Account & Cloud Save | F11.1.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Backend/Mobile Engineer | Backend | 3 | 18 | 2.7 | 20.7 | Not Started
335 | E11 | Identity, Account & Cloud Save | F11.1.T2 | Implementation | MVP-P0 | CONFIRMED | Backend/Mobile Engineer | Backend | 4 | 24 | 3.6 | 27.6 | Not Started
336 | E11 | Identity, Account & Cloud Save | F11.1.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Backend | 3 | 18 | 2.7 | 20.7 | Not Started
338 | E11 | Identity, Account & Cloud Save | F11.2.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Backend Engineer | Backend | 3 | 18 | 2.7 | 20.7 | Not Started
339 | E11 | Identity, Account & Cloud Save | F11.2.T2 | Implementation | MVP-P0 | CONFIRMED | Backend Engineer | Backend | 4 | 24 | 3.6 | 27.6 | Not Started
340 | E11 | Identity, Account & Cloud Save | F11.2.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Backend | 3 | 18 | 2.7 | 20.7 | Not Started
342 | E11 | Identity, Account & Cloud Save | F11.3.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Mobile/Backend Engineer | Backend | 3 | 18 | 2.7 | 20.7 | Not Started
343 | E11 | Identity, Account & Cloud Save | F11.3.T2 | Implementation | MVP-P0 | CONFIRMED | Mobile/Backend Engineer | Backend | 4 | 24 | 3.6 | 27.6 | Not Started
344 | E11 | Identity, Account & Cloud Save | F11.3.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Backend | 3 | 18 | 2.7 | 20.7 | Not Started
346 | E11 | Identity, Account & Cloud Save | F11.4.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Mobile/Backend Engineer | Backend | 3 | 18 | 2.7 | 20.7 | Not Started
347 | E11 | Identity, Account & Cloud Save | F11.4.T2 | Implementation | MVP-P0 | CONFIRMED | Mobile/Backend Engineer | Backend | 4 | 24 | 3.6 | 27.6 | Not Started
348 | E11 | Identity, Account & Cloud Save | F11.4.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Backend | 3 | 18 | 2.7 | 20.7 | Not Started
350 | E11 | Identity, Account & Cloud Save | F11.5.T1 | Analysis & Design | MVP-P0 | PROPOSED | Backend Engineer | Backend | 3 | 18 | 2.7 | 20.7 | Not Started
351 | E11 | Identity, Account & Cloud Save | F11.5.T2 | Implementation | MVP-P0 | PROPOSED | Backend Engineer | Backend | 4 | 24 | 3.6 | 27.6 | Not Started
352 | E11 | Identity, Account & Cloud Save | F11.5.T3 | Validation & QA | MVP-P0 | PROPOSED | QA Engineer | Backend | 3 | 18 | 2.7 | 20.7 | Not Started
354 | E11 | Identity, Account & Cloud Save | F11.6.T1 | Analysis & Design | MVP-P0 | PROPOSED | Backend Engineer | Backend | 3 | 18 | 2.7 | 20.7 | Not Started
355 | E11 | Identity, Account & Cloud Save | F11.6.T2 | Implementation | MVP-P0 | PROPOSED | Backend Engineer | Backend | 4 | 24 | 3.6 | 27.6 | Not Started
356 | E11 | Identity, Account & Cloud Save | F11.6.T3 | Validation & QA | MVP-P0 | PROPOSED | QA Engineer | Backend | 3 | 18 | 2.7 | 20.7 | Not Started
358 | E11 | Identity, Account & Cloud Save | F11.7.T1 | Analysis & Design | MVP-P0 | TBD | Product Engineer | Backend | 3 | 18 | 2.7 | 20.7 | Not Started
359 | E11 | Identity, Account & Cloud Save | F11.7.T2 | Implementation | MVP-P0 | TBD | Product Engineer | Backend | 4 | 24 | 3.6 | 27.6 | Not Started
360 | E11 | Identity, Account & Cloud Save | F11.7.T3 | Validation & QA | MVP-P0 | TBD | QA Engineer | Backend | 3 | 18 | 2.7 | 20.7 | Not Started
362 | E11 | Identity, Account & Cloud Save | F11.8.T1 | Analysis & Design | MVP-P0 | PROPOSED | Mobile Engineer | Backend | 3 | 18 | 2.7 | 20.7 | Not Started
363 | E11 | Identity, Account & Cloud Save | F11.8.T2 | Implementation | MVP-P0 | PROPOSED | Mobile Engineer | Backend | 4 | 24 | 3.6 | 27.6 | Not Started
364 | E11 | Identity, Account & Cloud Save | F11.8.T3 | Validation & QA | MVP-P0 | PROPOSED | QA Engineer | Backend | 3 | 18 | 2.7 | 20.7 | Not Started
366 | E12 | Backend Platform (Firebase) | F12.1.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Backend Engineer | Backend/Cloud | 5 | 30 | 4.5 | 34.5 | Not Started
367 | E12 | Backend Platform (Firebase) | F12.1.T2 | Implementation | MVP-P0 | CONFIRMED | Backend Engineer | Backend/Cloud | 7 | 42 | 6.3 | 48.3 | Not Started
368 | E12 | Backend Platform (Firebase) | F12.1.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Backend/Cloud | 5 | 30 | 4.5 | 34.5 | Not Started
370 | E12 | Backend Platform (Firebase) | F12.2.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Backend Engineer | Backend/Cloud | 3 | 18 | 2.7 | 20.7 | Not Started
371 | E12 | Backend Platform (Firebase) | F12.2.T2 | Implementation | MVP-P0 | CONFIRMED | Backend Engineer | Backend/Cloud | 4 | 24 | 3.6 | 27.6 | Not Started
372 | E12 | Backend Platform (Firebase) | F12.2.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Backend/Cloud | 3 | 18 | 2.7 | 20.7 | Not Started
374 | E12 | Backend Platform (Firebase) | F12.3.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Backend Engineer | Backend/Cloud | 5 | 30 | 4.5 | 34.5 | Not Started
375 | E12 | Backend Platform (Firebase) | F12.3.T2 | Implementation | MVP-P0 | CONFIRMED | Backend Engineer | Backend/Cloud | 7 | 42 | 6.3 | 48.3 | Not Started
376 | E12 | Backend Platform (Firebase) | F12.3.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Backend/Cloud | 5 | 30 | 4.5 | 34.5 | Not Started
378 | E12 | Backend Platform (Firebase) | F12.4.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Backend Engineer | Backend/Cloud | 5 | 30 | 4.5 | 34.5 | Not Started
379 | E12 | Backend Platform (Firebase) | F12.4.T2 | Implementation | MVP-P0 | CONFIRMED | Backend Engineer | Backend/Cloud | 7 | 42 | 6.3 | 48.3 | Not Started
380 | E12 | Backend Platform (Firebase) | F12.4.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Backend/Cloud | 5 | 30 | 4.5 | 34.5 | Not Started
382 | E12 | Backend Platform (Firebase) | F12.5.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Backend Engineer | Backend/Cloud | 3 | 18 | 2.7 | 20.7 | Not Started
383 | E12 | Backend Platform (Firebase) | F12.5.T2 | Implementation | MVP-P0 | CONFIRMED | Backend Engineer | Backend/Cloud | 4 | 24 | 3.6 | 27.6 | Not Started
384 | E12 | Backend Platform (Firebase) | F12.5.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Backend/Cloud | 3 | 18 | 2.7 | 20.7 | Not Started
386 | E12 | Backend Platform (Firebase) | F12.6.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Backend Engineer | Backend/Cloud | 2 | 12 | 1.8 | 13.8 | Not Started
387 | E12 | Backend Platform (Firebase) | F12.6.T2 | Implementation | MVP-P0 | CONFIRMED | Backend Engineer | Backend/Cloud | 3 | 18 | 2.7 | 20.7 | Not Started
388 | E12 | Backend Platform (Firebase) | F12.6.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Backend/Cloud | 2 | 12 | 1.8 | 13.8 | Not Started
390 | E12 | Backend Platform (Firebase) | F12.7.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Backend Engineer | Backend/Cloud | 3 | 18 | 2.7 | 20.7 | Not Started
391 | E12 | Backend Platform (Firebase) | F12.7.T2 | Implementation | MVP-P0 | CONFIRMED | Backend Engineer | Backend/Cloud | 4 | 24 | 3.6 | 27.6 | Not Started
392 | E12 | Backend Platform (Firebase) | F12.7.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Backend/Cloud | 3 | 18 | 2.7 | 20.7 | Not Started
394 | E12 | Backend Platform (Firebase) | F12.8.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Backend Engineer | Backend/Cloud | 3 | 18 | 2.7 | 20.7 | Not Started
395 | E12 | Backend Platform (Firebase) | F12.8.T2 | Implementation | MVP-P0 | CONFIRMED | Backend Engineer | Backend/Cloud | 4 | 24 | 3.6 | 27.6 | Not Started
396 | E12 | Backend Platform (Firebase) | F12.8.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Backend/Cloud | 3 | 18 | 2.7 | 20.7 | Not Started
398 | E12 | Backend Platform (Firebase) | F12.9.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Backend Engineer | Backend/Cloud | 2 | 12 | 1.8 | 13.8 | Not Started
399 | E12 | Backend Platform (Firebase) | F12.9.T2 | Implementation | MVP-P0 | CONFIRMED | Backend Engineer | Backend/Cloud | 3 | 18 | 2.7 | 20.7 | Not Started
400 | E12 | Backend Platform (Firebase) | F12.9.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Backend/Cloud | 2 | 12 | 1.8 | 13.8 | Not Started
402 | E13 | Admin / CMS | F13.1.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Backend/Admin Engineer | Admin/Content | 3 | 18 | 2.7 | 20.7 | Not Started
403 | E13 | Admin / CMS | F13.1.T2 | Implementation | MVP-P0 | CONFIRMED | Backend/Admin Engineer | Admin/Content | 4 | 24 | 3.6 | 27.6 | Not Started
404 | E13 | Admin / CMS | F13.1.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Admin/Content | 3 | 18 | 2.7 | 20.7 | Not Started
406 | E13 | Admin / CMS | F13.2.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Admin Engineer | Admin/Content | 5 | 30 | 4.5 | 34.5 | Not Started
407 | E13 | Admin / CMS | F13.2.T2 | Implementation | MVP-P0 | CONFIRMED | Admin Engineer | Admin/Content | 7 | 42 | 6.3 | 48.3 | Not Started
408 | E13 | Admin / CMS | F13.2.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Admin/Content | 5 | 30 | 4.5 | 34.5 | Not Started
410 | E13 | Admin / CMS | F13.3.T1 | Analysis & Design | MVP-P0 | PROPOSED | Admin Engineer | Admin/Content | 3 | 18 | 2.7 | 20.7 | Not Started
411 | E13 | Admin / CMS | F13.3.T2 | Implementation | MVP-P0 | PROPOSED | Admin Engineer | Admin/Content | 4 | 24 | 3.6 | 27.6 | Not Started
412 | E13 | Admin / CMS | F13.3.T3 | Validation & QA | MVP-P0 | PROPOSED | QA Engineer | Admin/Content | 3 | 18 | 2.7 | 20.7 | Not Started
414 | E13 | Admin / CMS | F13.4.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Admin Engineer | Admin/Content | 5 | 30 | 4.5 | 34.5 | Not Started
415 | E13 | Admin / CMS | F13.4.T2 | Implementation | MVP-P0 | CONFIRMED | Admin Engineer | Admin/Content | 7 | 42 | 6.3 | 48.3 | Not Started
416 | E13 | Admin / CMS | F13.4.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Admin/Content | 5 | 30 | 4.5 | 34.5 | Not Started
418 | E13 | Admin / CMS | F13.5.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Admin Engineer | Admin/Content | 5 | 30 | 4.5 | 34.5 | Not Started
419 | E13 | Admin / CMS | F13.5.T2 | Implementation | MVP-P0 | CONFIRMED | Admin Engineer | Admin/Content | 7 | 42 | 6.3 | 48.3 | Not Started
420 | E13 | Admin / CMS | F13.5.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Admin/Content | 5 | 30 | 4.5 | 34.5 | Not Started
422 | E13 | Admin / CMS | F13.6.T1 | Analysis & Design | MVP-P0 | PROPOSED | Admin/Game Engineer | Admin/Content | 5 | 30 | 4.5 | 34.5 | Not Started
423 | E13 | Admin / CMS | F13.6.T2 | Implementation | MVP-P0 | PROPOSED | Admin/Game Engineer | Admin/Content | 7 | 42 | 6.3 | 48.3 | Not Started
424 | E13 | Admin / CMS | F13.6.T3 | Validation & QA | MVP-P0 | PROPOSED | QA Engineer | Admin/Content | 5 | 30 | 4.5 | 34.5 | Not Started
426 | E13 | Admin / CMS | F13.7.T1 | Analysis & Design | MVP-P0 | PROPOSED | Backend/Admin Engineer | Admin/Content | 5 | 30 | 4.5 | 34.5 | Not Started
427 | E13 | Admin / CMS | F13.7.T2 | Implementation | MVP-P0 | PROPOSED | Backend/Admin Engineer | Admin/Content | 7 | 42 | 6.3 | 48.3 | Not Started
428 | E13 | Admin / CMS | F13.7.T3 | Validation & QA | MVP-P0 | PROPOSED | QA Engineer | Admin/Content | 5 | 30 | 4.5 | 34.5 | Not Started
430 | E13 | Admin / CMS | F13.8.T1 | Analysis & Design | MVP-P0 | PROPOSED | Admin Engineer | Admin/Content | 3 | 18 | 2.7 | 20.7 | Not Started
431 | E13 | Admin / CMS | F13.8.T2 | Implementation | MVP-P0 | PROPOSED | Admin Engineer | Admin/Content | 4 | 24 | 3.6 | 27.6 | Not Started
432 | E13 | Admin / CMS | F13.8.T3 | Validation & QA | MVP-P0 | PROPOSED | QA Engineer | Admin/Content | 3 | 18 | 2.7 | 20.7 | Not Started
434 | E13 | Admin / CMS | F13.9.T1 | Analysis & Design | MVP-P0 | CONFIRMED/REQUIRED | Backend Engineer | Admin/Content | 3 | 18 | 2.7 | 20.7 | Not Started
435 | E13 | Admin / CMS | F13.9.T2 | Implementation | MVP-P0 | CONFIRMED/REQUIRED | Backend Engineer | Admin/Content | 4 | 24 | 3.6 | 27.6 | Not Started
436 | E13 | Admin / CMS | F13.9.T3 | Validation & QA | MVP-P0 | CONFIRMED/REQUIRED | QA Engineer | Admin/Content | 3 | 18 | 2.7 | 20.7 | Not Started
438 | E13 | Admin / CMS | F13.10.T1 | Analysis & Design | MVP-P0 | PROPOSED MVP | Admin Engineer | Admin/Content | 3 | 18 | 2.7 | 20.7 | Not Started
439 | E13 | Admin / CMS | F13.10.T2 | Implementation | MVP-P0 | PROPOSED MVP | Admin Engineer | Admin/Content | 4 | 24 | 3.6 | 27.6 | Not Started
440 | E13 | Admin / CMS | F13.10.T3 | Validation & QA | MVP-P0 | PROPOSED MVP | QA Engineer | Admin/Content | 3 | 18 | 2.7 | 20.7 | Not Started
442 | E14 | Analytics & Observability | F14.1.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Mobile Engineer | Analytics/Engineering | 2 | 12 | 1.8 | 13.8 | Not Started
443 | E14 | Analytics & Observability | F14.1.T2 | Implementation | MVP-P0 | CONFIRMED | Mobile Engineer | Analytics/Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
444 | E14 | Analytics & Observability | F14.1.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Analytics/Engineering | 2 | 12 | 1.8 | 13.8 | Not Started
446 | E14 | Analytics & Observability | F14.2.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Analytics Engineer | Analytics/Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
447 | E14 | Analytics & Observability | F14.2.T2 | Implementation | MVP-P0 | CONFIRMED | Analytics Engineer | Analytics/Engineering | 4 | 24 | 3.6 | 27.6 | Not Started
448 | E14 | Analytics & Observability | F14.2.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Analytics/Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
450 | E14 | Analytics & Observability | F14.3.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Analytics Engineer | Analytics/Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
451 | E14 | Analytics & Observability | F14.3.T2 | Implementation | MVP-P0 | CONFIRMED | Analytics Engineer | Analytics/Engineering | 4 | 24 | 3.6 | 27.6 | Not Started
452 | E14 | Analytics & Observability | F14.3.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Analytics/Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
454 | E14 | Analytics & Observability | F14.4.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Analytics/Solver Engineer | Analytics/Engineering | 2 | 12 | 1.8 | 13.8 | Not Started
455 | E14 | Analytics & Observability | F14.4.T2 | Implementation | MVP-P0 | CONFIRMED | Analytics/Solver Engineer | Analytics/Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
456 | E14 | Analytics & Observability | F14.4.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Analytics/Engineering | 2 | 12 | 1.8 | 13.8 | Not Started
458 | E14 | Analytics & Observability | F14.5.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Analytics Engineer | Analytics/Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
459 | E14 | Analytics & Observability | F14.5.T2 | Implementation | MVP-P0 | CONFIRMED | Analytics Engineer | Analytics/Engineering | 4 | 24 | 3.6 | 27.6 | Not Started
460 | E14 | Analytics & Observability | F14.5.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Analytics/Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
462 | E14 | Analytics & Observability | F14.6.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Analytics Engineer | Analytics/Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
463 | E14 | Analytics & Observability | F14.6.T2 | Implementation | MVP-P0 | CONFIRMED | Analytics Engineer | Analytics/Engineering | 4 | 24 | 3.6 | 27.6 | Not Started
464 | E14 | Analytics & Observability | F14.6.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Analytics/Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
466 | E14 | Analytics & Observability | F14.7.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Mobile Engineer | Analytics/Engineering | 2 | 12 | 1.8 | 13.8 | Not Started
467 | E14 | Analytics & Observability | F14.7.T2 | Implementation | MVP-P0 | CONFIRMED | Mobile Engineer | Analytics/Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
468 | E14 | Analytics & Observability | F14.7.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Analytics/Engineering | 2 | 12 | 1.8 | 13.8 | Not Started
470 | E14 | Analytics & Observability | F14.8.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Analyst | Analytics/Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
471 | E14 | Analytics & Observability | F14.8.T2 | Implementation | MVP-P0 | CONFIRMED | Analyst | Analytics/Engineering | 4 | 24 | 3.6 | 27.6 | Not Started
472 | E14 | Analytics & Observability | F14.8.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Analytics/Engineering | 3 | 18 | 2.7 | 20.7 | Not Started
474 | E15 | Daily Reward | F15.1.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Backend Engineer | Product/Backend | 2 | 12 | 1.8 | 13.8 | Not Started
475 | E15 | Daily Reward | F15.1.T2 | Implementation | MVP-P0 | CONFIRMED | Backend Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
476 | E15 | Daily Reward | F15.1.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/Backend | 2 | 12 | 1.8 | 13.8 | Not Started
478 | E15 | Daily Reward | F15.2.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Backend Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
479 | E15 | Daily Reward | F15.2.T2 | Implementation | MVP-P0 | CONFIRMED | Backend Engineer | Product/Backend | 4 | 24 | 3.6 | 27.6 | Not Started
480 | E15 | Daily Reward | F15.2.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
482 | E15 | Daily Reward | F15.3.T1 | Analysis & Design | MVP-P0 | CONFIRMED | UI Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
483 | E15 | Daily Reward | F15.3.T2 | Implementation | MVP-P0 | CONFIRMED | UI Engineer | Product/Backend | 4 | 24 | 3.6 | 27.6 | Not Started
484 | E15 | Daily Reward | F15.3.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
486 | E15 | Daily Reward | F15.4.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Analytics Engineer | Product/Backend | 2 | 12 | 1.8 | 13.8 | Not Started
487 | E15 | Daily Reward | F15.4.T2 | Implementation | MVP-P0 | CONFIRMED | Analytics Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
488 | E15 | Daily Reward | F15.4.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/Backend | 2 | 12 | 1.8 | 13.8 | Not Started
490 | E16 | Daily Challenge | F16.1.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Backend/Game Designer | Product/Game Design | 3 | 18 | 2.7 | 20.7 | Not Started
491 | E16 | Daily Challenge | F16.1.T2 | Implementation | MVP-P0 | CONFIRMED | Backend/Game Designer | Product/Game Design | 4 | 24 | 3.6 | 27.6 | Not Started
492 | E16 | Daily Challenge | F16.1.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/Game Design | 3 | 18 | 2.7 | 20.7 | Not Started
494 | E16 | Daily Challenge | F16.2.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Solver/Backend Engineer | Product/Game Design | 5 | 30 | 4.5 | 34.5 | Not Started
495 | E16 | Daily Challenge | F16.2.T2 | Implementation | MVP-P0 | CONFIRMED | Solver/Backend Engineer | Product/Game Design | 7 | 42 | 6.3 | 48.3 | Not Started
496 | E16 | Daily Challenge | F16.2.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/Game Design | 5 | 30 | 4.5 | 34.5 | Not Started
498 | E16 | Daily Challenge | F16.3.T1 | Analysis & Design | MVP-P0 | CONFIRMED | UI Engineer | Product/Game Design | 5 | 30 | 4.5 | 34.5 | Not Started
499 | E16 | Daily Challenge | F16.3.T2 | Implementation | MVP-P0 | CONFIRMED | UI Engineer | Product/Game Design | 7 | 42 | 6.3 | 48.3 | Not Started
500 | E16 | Daily Challenge | F16.3.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/Game Design | 5 | 30 | 4.5 | 34.5 | Not Started
502 | E16 | Daily Challenge | F16.4.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Backend Engineer | Product/Game Design | 3 | 18 | 2.7 | 20.7 | Not Started
503 | E16 | Daily Challenge | F16.4.T2 | Implementation | MVP-P0 | CONFIRMED | Backend Engineer | Product/Game Design | 4 | 24 | 3.6 | 27.6 | Not Started
504 | E16 | Daily Challenge | F16.4.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/Game Design | 3 | 18 | 2.7 | 20.7 | Not Started
506 | E16 | Daily Challenge | F16.5.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Analytics Engineer | Product/Game Design | 2 | 12 | 1.8 | 13.8 | Not Started
507 | E16 | Daily Challenge | F16.5.T2 | Implementation | MVP-P0 | CONFIRMED | Analytics Engineer | Product/Game Design | 3 | 18 | 2.7 | 20.7 | Not Started
508 | E16 | Daily Challenge | F16.5.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/Game Design | 2 | 12 | 1.8 | 13.8 | Not Started
510 | E17 | Daily Streak & Smart Notifications | F17.1.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Backend Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
511 | E17 | Daily Streak & Smart Notifications | F17.1.T2 | Implementation | MVP-P0 | CONFIRMED | Backend Engineer | Product/Backend | 4 | 24 | 3.6 | 27.6 | Not Started
512 | E17 | Daily Streak & Smart Notifications | F17.1.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
514 | E17 | Daily Streak & Smart Notifications | F17.2.T1 | Analysis & Design | MVP-P0 | CONFIRMED | UI Engineer | Product/Backend | 2 | 12 | 1.8 | 13.8 | Not Started
515 | E17 | Daily Streak & Smart Notifications | F17.2.T2 | Implementation | MVP-P0 | CONFIRMED | UI Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
516 | E17 | Daily Streak & Smart Notifications | F17.2.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/Backend | 2 | 12 | 1.8 | 13.8 | Not Started
518 | E17 | Daily Streak & Smart Notifications | F17.3.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Mobile/Backend Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
519 | E17 | Daily Streak & Smart Notifications | F17.3.T2 | Implementation | MVP-P0 | CONFIRMED | Mobile/Backend Engineer | Product/Backend | 4 | 24 | 3.6 | 27.6 | Not Started
520 | E17 | Daily Streak & Smart Notifications | F17.3.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
522 | E17 | Daily Streak & Smart Notifications | F17.4.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Backend Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
523 | E17 | Daily Streak & Smart Notifications | F17.4.T2 | Implementation | MVP-P0 | CONFIRMED | Backend Engineer | Product/Backend | 4 | 24 | 3.6 | 27.6 | Not Started
524 | E17 | Daily Streak & Smart Notifications | F17.4.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
526 | E17 | Daily Streak & Smart Notifications | F17.5.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Mobile Engineer | Product/Backend | 2 | 12 | 1.8 | 13.8 | Not Started
527 | E17 | Daily Streak & Smart Notifications | F17.5.T2 | Implementation | MVP-P0 | CONFIRMED | Mobile Engineer | Product/Backend | 3 | 18 | 2.7 | 20.7 | Not Started
528 | E17 | Daily Streak & Smart Notifications | F17.5.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | Product/Backend | 2 | 12 | 1.8 | 13.8 | Not Started
530 | E18 | QA & Automated Validation | F18.1.T1 | Analysis & Design | MVP-P0 | CONFIRMED | QA/Game Engineer | QA | 5 | 30 | 4.5 | 34.5 | Not Started
531 | E18 | QA & Automated Validation | F18.1.T2 | Implementation | MVP-P0 | CONFIRMED | QA/Game Engineer | QA | 7 | 42 | 6.3 | 48.3 | Not Started
532 | E18 | QA & Automated Validation | F18.1.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | QA | 5 | 30 | 4.5 | 34.5 | Not Started
534 | E18 | QA & Automated Validation | F18.2.T1 | Analysis & Design | MVP-P0 | PROPOSED | QA Engineer | QA | 5 | 30 | 4.5 | 34.5 | Not Started
535 | E18 | QA & Automated Validation | F18.2.T2 | Implementation | MVP-P0 | PROPOSED | QA Engineer | QA | 7 | 42 | 6.3 | 48.3 | Not Started
536 | E18 | QA & Automated Validation | F18.2.T3 | Validation & QA | MVP-P0 | PROPOSED | QA Engineer | QA | 5 | 30 | 4.5 | 34.5 | Not Started
538 | E18 | QA & Automated Validation | F18.3.T1 | Analysis & Design | MVP-P0 | CONFIRMED STRATEGY | QA/Solver Engineer | QA | 5 | 30 | 4.5 | 34.5 | Not Started
539 | E18 | QA & Automated Validation | F18.3.T2 | Implementation | MVP-P0 | CONFIRMED STRATEGY | QA/Solver Engineer | QA | 7 | 42 | 6.3 | 48.3 | Not Started
540 | E18 | QA & Automated Validation | F18.3.T3 | Validation & QA | MVP-P0 | CONFIRMED STRATEGY | QA Engineer | QA | 5 | 30 | 4.5 | 34.5 | Not Started
542 | E18 | QA & Automated Validation | F18.4.T1 | Analysis & Design | MVP-P0 | CONFIRMED | QA Engineer | QA | 5 | 30 | 4.5 | 34.5 | Not Started
543 | E18 | QA & Automated Validation | F18.4.T2 | Implementation | MVP-P0 | CONFIRMED | QA Engineer | QA | 7 | 42 | 6.3 | 48.3 | Not Started
544 | E18 | QA & Automated Validation | F18.4.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | QA | 5 | 30 | 4.5 | 34.5 | Not Started
546 | E18 | QA & Automated Validation | F18.5.T1 | Analysis & Design | MVP-P0 | CONFIRMED | QA Engineer | QA | 5 | 30 | 4.5 | 34.5 | Not Started
547 | E18 | QA & Automated Validation | F18.5.T2 | Implementation | MVP-P0 | CONFIRMED | QA Engineer | QA | 7 | 42 | 6.3 | 48.3 | Not Started
548 | E18 | QA & Automated Validation | F18.5.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | QA | 5 | 30 | 4.5 | 34.5 | Not Started
550 | E18 | QA & Automated Validation | F18.6.T1 | Analysis & Design | MVP-P0 | CONFIRMED | Arabic Reviewer/QA | QA | 3 | 18 | 2.7 | 20.7 | Not Started
551 | E18 | QA & Automated Validation | F18.6.T2 | Implementation | MVP-P0 | CONFIRMED | Arabic Reviewer/QA | QA | 4 | 24 | 3.6 | 27.6 | Not Started
552 | E18 | QA & Automated Validation | F18.6.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | QA | 3 | 18 | 2.7 | 20.7 | Not Started
554 | E18 | QA & Automated Validation | F18.7.T1 | Analysis & Design | MVP-P0 | CONFIRMED | QA Engineer | QA | 3 | 18 | 2.7 | 20.7 | Not Started
555 | E18 | QA & Automated Validation | F18.7.T2 | Implementation | MVP-P0 | CONFIRMED | QA Engineer | QA | 4 | 24 | 3.6 | 27.6 | Not Started
556 | E18 | QA & Automated Validation | F18.7.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | QA | 3 | 18 | 2.7 | 20.7 | Not Started
558 | E18 | QA & Automated Validation | F18.8.T1 | Analysis & Design | MVP-P0 | CONFIRMED | QA Engineer | QA | 3 | 18 | 2.7 | 20.7 | Not Started
559 | E18 | QA & Automated Validation | F18.8.T2 | Implementation | MVP-P0 | CONFIRMED | QA Engineer | QA | 4 | 24 | 3.6 | 27.6 | Not Started
560 | E18 | QA & Automated Validation | F18.8.T3 | Validation & QA | MVP-P0 | CONFIRMED | QA Engineer | QA | 3 | 18 | 2.7 | 20.7 | Not Started
562 | E18 | QA & Automated Validation | F18.9.T1 | Analysis & Design | MVP-P0 | REQUIRED | QA Engineer | QA | 3 | 18 | 2.7 | 20.7 | Not Started
563 | E18 | QA & Automated Validation | F18.9.T2 | Implementation | MVP-P0 | REQUIRED | QA Engineer | QA | 4 | 24 | 3.6 | 27.6 | Not Started
564 | E18 | QA & Automated Validation | F18.9.T3 | Validation & QA | MVP-P0 | REQUIRED | QA Engineer | QA | 3 | 18 | 2.7 | 20.7 | Not Started
566 | E18 | QA & Automated Validation | F18.10.T1 | Analysis & Design | MVP-P0 | REQUIRED | QA Engineer | QA | 5 | 30 | 4.5 | 34.5 | Not Started
567 | E18 | QA & Automated Validation | F18.10.T2 | Implementation | MVP-P0 | REQUIRED | QA Engineer | QA | 7 | 42 | 6.3 | 48.3 | Not Started
568 | E18 | QA & Automated Validation | F18.10.T3 | Validation & QA | MVP-P0 | REQUIRED | QA Engineer | QA | 5 | 30 | 4.5 | 34.5 | Not Started
570 | E19 | DevOps, Environments & Release | F19.1.T1 | Analysis & Design | MVP-P0 | PROPOSED | DevOps/Tech Lead | DevOps | 2 | 12 | 1.8 | 13.8 | Not Started
571 | E19 | DevOps, Environments & Release | F19.1.T2 | Implementation | MVP-P0 | PROPOSED | DevOps/Tech Lead | DevOps | 3 | 18 | 2.7 | 20.7 | Not Started
572 | E19 | DevOps, Environments & Release | F19.1.T3 | Validation & QA | MVP-P0 | PROPOSED | QA Engineer | DevOps | 2 | 12 | 1.8 | 13.8 | Not Started
574 | E19 | DevOps, Environments & Release | F19.2.T1 | Analysis & Design | MVP-P0 | PROPOSED | DevOps Engineer | DevOps | 3 | 18 | 2.7 | 20.7 | Not Started
575 | E19 | DevOps, Environments & Release | F19.2.T2 | Implementation | MVP-P0 | PROPOSED | DevOps Engineer | DevOps | 4 | 24 | 3.6 | 27.6 | Not Started
576 | E19 | DevOps, Environments & Release | F19.2.T3 | Validation & QA | MVP-P0 | PROPOSED | QA Engineer | DevOps | 3 | 18 | 2.7 | 20.7 | Not Started
578 | E19 | DevOps, Environments & Release | F19.3.T1 | Analysis & Design | MVP-P0 | PROPOSED | DevOps Engineer | DevOps | 3 | 18 | 2.7 | 20.7 | Not Started
579 | E19 | DevOps, Environments & Release | F19.3.T2 | Implementation | MVP-P0 | PROPOSED | DevOps Engineer | DevOps | 4 | 24 | 3.6 | 27.6 | Not Started
580 | E19 | DevOps, Environments & Release | F19.3.T3 | Validation & QA | MVP-P0 | PROPOSED | QA Engineer | DevOps | 3 | 18 | 2.7 | 20.7 | Not Started
582 | E19 | DevOps, Environments & Release | F19.4.T1 | Analysis & Design | MVP-P0 | PROPOSED | DevOps Engineer | DevOps | 3 | 18 | 2.7 | 20.7 | Not Started
583 | E19 | DevOps, Environments & Release | F19.4.T2 | Implementation | MVP-P0 | PROPOSED | DevOps Engineer | DevOps | 4 | 24 | 3.6 | 27.6 | Not Started
584 | E19 | DevOps, Environments & Release | F19.4.T3 | Validation & QA | MVP-P0 | PROPOSED | QA Engineer | DevOps | 3 | 18 | 2.7 | 20.7 | Not Started
586 | E19 | DevOps, Environments & Release | F19.5.T1 | Analysis & Design | MVP-P0 | REQUIRED | DevOps Engineer | DevOps | 2 | 12 | 1.8 | 13.8 | Not Started
587 | E19 | DevOps, Environments & Release | F19.5.T2 | Implementation | MVP-P0 | REQUIRED | DevOps Engineer | DevOps | 3 | 18 | 2.7 | 20.7 | Not Started
588 | E19 | DevOps, Environments & Release | F19.5.T3 | Validation & QA | MVP-P0 | REQUIRED | QA Engineer | DevOps | 2 | 12 | 1.8 | 13.8 | Not Started
590 | E19 | DevOps, Environments & Release | F19.6.T1 | Analysis & Design | MVP-P0 | REQUIRED | DevOps Engineer | DevOps | 3 | 18 | 2.7 | 20.7 | Not Started
591 | E19 | DevOps, Environments & Release | F19.6.T2 | Implementation | MVP-P0 | REQUIRED | DevOps Engineer | DevOps | 4 | 24 | 3.6 | 27.6 | Not Started
592 | E19 | DevOps, Environments & Release | F19.6.T3 | Validation & QA | MVP-P0 | REQUIRED | QA Engineer | DevOps | 3 | 18 | 2.7 | 20.7 | Not Started
594 | E19 | DevOps, Environments & Release | F19.7.T1 | Analysis & Design | MVP-P0 | REQUIRED | DevOps Engineer | DevOps | 3 | 18 | 2.7 | 20.7 | Not Started
595 | E19 | DevOps, Environments & Release | F19.7.T2 | Implementation | MVP-P0 | REQUIRED | DevOps Engineer | DevOps | 4 | 24 | 3.6 | 27.6 | Not Started
596 | E19 | DevOps, Environments & Release | F19.7.T3 | Validation & QA | MVP-P0 | REQUIRED | QA Engineer | DevOps | 3 | 18 | 2.7 | 20.7 | Not Started
598 | E19 | DevOps, Environments & Release | F19.8.T1 | Analysis & Design | MVP-P0 | REQUIRED | Mobile/DevOps Engineer | DevOps | 3 | 18 | 2.7 | 20.7 | Not Started
599 | E19 | DevOps, Environments & Release | F19.8.T2 | Implementation | MVP-P0 | REQUIRED | Mobile/DevOps Engineer | DevOps | 4 | 24 | 3.6 | 27.6 | Not Started
600 | E19 | DevOps, Environments & Release | F19.8.T3 | Validation & QA | MVP-P0 | REQUIRED | QA Engineer | DevOps | 3 | 18 | 2.7 | 20.7 | Not Started
602 | E20 | Security, Privacy & Accessibility | F20.1.T1 | Analysis & Design | MVP-P0 | REQUIRED | Backend Engineer | Engineering/Product | 3 | 18 | 2.7 | 20.7 | Not Started
603 | E20 | Security, Privacy & Accessibility | F20.1.T2 | Implementation | MVP-P0 | REQUIRED | Backend Engineer | Engineering/Product | 4 | 24 | 3.6 | 27.6 | Not Started
604 | E20 | Security, Privacy & Accessibility | F20.1.T3 | Validation & QA | MVP-P0 | REQUIRED | QA Engineer | Engineering/Product | 3 | 18 | 2.7 | 20.7 | Not Started
606 | E20 | Security, Privacy & Accessibility | F20.2.T1 | Analysis & Design | MVP-P0 | REQUIRED | Backend Engineer | Engineering/Product | 3 | 18 | 2.7 | 20.7 | Not Started
607 | E20 | Security, Privacy & Accessibility | F20.2.T2 | Implementation | MVP-P0 | REQUIRED | Backend Engineer | Engineering/Product | 4 | 24 | 3.6 | 27.6 | Not Started
608 | E20 | Security, Privacy & Accessibility | F20.2.T3 | Validation & QA | MVP-P0 | REQUIRED | QA Engineer | Engineering/Product | 3 | 18 | 2.7 | 20.7 | Not Started
610 | E20 | Security, Privacy & Accessibility | F20.3.T1 | Analysis & Design | MVP-P0 | REQUIRED | Product/Backend | Engineering/Product | 2 | 12 | 1.8 | 13.8 | Not Started
611 | E20 | Security, Privacy & Accessibility | F20.3.T2 | Implementation | MVP-P0 | REQUIRED | Product/Backend | Engineering/Product | 3 | 18 | 2.7 | 20.7 | Not Started
612 | E20 | Security, Privacy & Accessibility | F20.3.T3 | Validation & QA | MVP-P0 | REQUIRED | QA Engineer | Engineering/Product | 2 | 12 | 1.8 | 13.8 | Not Started
614 | E20 | Security, Privacy & Accessibility | F20.4.T1 | Analysis & Design | MVP-P0 | TBD PROVIDERS | Product/Mobile Engineer | Engineering/Product | 3 | 18 | 2.7 | 20.7 | Not Started
615 | E20 | Security, Privacy & Accessibility | F20.4.T2 | Implementation | MVP-P0 | TBD PROVIDERS | Product/Mobile Engineer | Engineering/Product | 4 | 24 | 3.6 | 27.6 | Not Started
616 | E20 | Security, Privacy & Accessibility | F20.4.T3 | Validation & QA | MVP-P0 | TBD PROVIDERS | QA Engineer | Engineering/Product | 3 | 18 | 2.7 | 20.7 | Not Started
618 | E20 | Security, Privacy & Accessibility | F20.5.T1 | Analysis & Design | MVP-P0 | REQUIRED | Mobile/UI Engineer | Engineering/Product | 3 | 18 | 2.7 | 20.7 | Not Started
619 | E20 | Security, Privacy & Accessibility | F20.5.T2 | Implementation | MVP-P0 | REQUIRED | Mobile/UI Engineer | Engineering/Product | 4 | 24 | 3.6 | 27.6 | Not Started
620 | E20 | Security, Privacy & Accessibility | F20.5.T3 | Validation & QA | MVP-P0 | REQUIRED | QA Engineer | Engineering/Product | 3 | 18 | 2.7 | 20.7 | Not Started
622 | E20 | Security, Privacy & Accessibility | F20.6.T1 | Analysis & Design | MVP-P0 | REQUIRED | QA/Security | Engineering/Product | 3 | 18 | 2.7 | 20.7 | Not Started
623 | E20 | Security, Privacy & Accessibility | F20.6.T2 | Implementation | MVP-P0 | REQUIRED | QA/Security | Engineering/Product | 4 | 24 | 3.6 | 27.6 | Not Started
624 | E20 | Security, Privacy & Accessibility | F20.6.T3 | Validation & QA | MVP-P0 | REQUIRED | QA Engineer | Engineering/Product | 3 | 18 | 2.7 | 20.7 | Not Started

## Epic Estimates
Epic Estimation Summary
Formula-driven summary of task-only effort. Planned Hours include the editable contingency from Assumptions.
Epic ID | Epic | Phase | Workstream | Task Count | Story Points | Base Hours | Contingency Hours | Planned Hours | % of P0/P1 | Dependencies | Primary Delivery Window | Status | Notes
E01 | Product & UX Foundation | MVP-P0 | Product/UX | 15 | 44 | 264 | 39.6 | 303.6 | 0.026051 | See Dependencies sheet |  | Not Started | CONFIRMED/PROPOSED
E02 | Arabic Content System | MVP-P0 | Content | 24 | 81 | 486 | 72.9 | 558.9 | 0.047957 | See Dependencies sheet |  | Not Started | CONFIRMED
E03 | Game Engine | MVP-P0 | Engineering | 36 | 148 | 888 | 133.2 | 1021.2 | 0.087626 | See Dependencies sheet |  | Not Started | CONFIRMED
E04 | Solver | MVP-P0 | Engineering | 30 | 142 | 852 | 127.8 | 979.8 | 0.084073 | See Dependencies sheet |  | Not Started | CONFIRMED
E05 | Level Generator & Difficulty | MVP-P0 | Game Design/Engineering | 30 | 125 | 750 | 112.5 | 862.5 | 0.074008 | See Dependencies sheet |  | Not Started | CONFIRMED
E06 | Tutorial & Onboarding | MVP-P0 | Product/UX | 21 | 64 | 384 | 57.6 | 441.6 | 0.037892 | See Dependencies sheet |  | Not Started | CONFIRMED
E07 | Main Journey & Chapters | MVP-P0 | Product/Game Design | 21 | 74 | 444 | 66.6 | 510.6 | 0.043813 | See Dependencies sheet |  | Not Started | CONFIRMED
E08 | Economy & Rewards | MVP-P0 | Product/Backend | 18 | 51 | 306 | 45.9 | 351.9 | 0.030195 | See Dependencies sheet |  | Not Started | CONFIRMED
E09 | Gameplay Assistance & Recovery | MVP-P0 | Engineering/Product | 21 | 58 | 348 | 52.2 | 400.2 | 0.03434 | See Dependencies sheet |  | Not Started | CONFIRMED
E10 | Monetization | MVP-P0 | Product/Backend | 33 | 99 | 594 | 89.1 | 683.1 | 0.058615 | See Dependencies sheet |  | Not Started | CONFIRMED
E11 | Identity, Account & Cloud Save | MVP-P0 | Backend | 24 | 80 | 480 | 72 | 552 | 0.047365 | See Dependencies sheet |  | Not Started | CONFIRMED
E12 | Backend Platform (Firebase) | MVP-P0 | Backend/Cloud | 27 | 105 | 630 | 94.5 | 724.5 | 0.062167 | See Dependencies sheet |  | Not Started | CONFIRMED Firebase-first; Azure/ASP.NET/PG out of MVP (scope reduction/reallocation)
E13 | Admin / CMS | MVP-P0 | Admin/Content | 30 | 135 | 810 | 121.5 | 931.5 | 0.079929 | See Dependencies sheet |  | Not Started | CONFIRMED
E14 | Analytics & Observability | MVP-P0 | Analytics/Engineering | 24 | 71 | 426 | 63.9 | 489.9 | 0.042037 | See Dependencies sheet |  | Not Started | CONFIRMED
E15 | Daily Reward | MVP-P0 | Product/Backend | 12 | 34 | 204 | 30.6 | 234.6 | 0.02013 | See Dependencies sheet |  | Not Started | CONFIRMED launch P0 (Decision Align v1.1)
E16 | Daily Challenge | MVP-P0 | Product/Game Design | 15 | 61 | 366 | 54.9 | 420.9 | 0.036116 | See Dependencies sheet |  | Not Started | CONFIRMED launch P0 (Decision Align v1.1)
E17 | Daily Streak & Smart Notifications | MVP-P0 | Product/Backend | 15 | 44 | 264 | 39.6 | 303.6 | 0.026051 | See Dependencies sheet |  | Not Started | CONFIRMED launch P0 (Decision Align v1.1)
E18 | QA & Automated Validation | MVP-P0 | QA | 30 | 142 | 852 | 127.8 | 979.8 | 0.084073 | See Dependencies sheet |  | Not Started | CONFIRMED
E19 | DevOps, Environments & Release | MVP-P0 | DevOps | 24 | 74 | 444 | 66.6 | 510.6 | 0.043813 | See Dependencies sheet |  | Not Started | PROPOSED ARCH
E20 | Security, Privacy & Accessibility | MVP-P0 | Engineering/Product | 18 | 57 | 342 | 51.3 | 393.3 | 0.033748 | See Dependencies sheet |  | Not Started | CONFIRMED/REQUIRED

## Delivery Scenarios
Delivery Duration Scenarios
Scenario durations are capacity-based planning estimates, not committed dates. Decision Align v1.1 moved Daily into P0 (increases P0 hours; reduces former P1). Staffing/calendar TBD.
Scenario | FTE | Effective h/week | P0 Planned Hours | P0 Duration (weeks) | P1 Planned Hours | P1 Duration (weeks) | Total Duration Sequential | Parallelization Note | Decision State
Solo / AI-Assisted | 1 | 30 | 11654.1 | 388.47 | 0 | 0 | 388.47 | Actual calendar duration may be shorter than effort/FTE because design, content, backend, QA and engineering can overlap. Dates remain TBD. | PROPOSED capacity model only
Lean Team | 3 | 90 | 11654.1 | 129.49 | 0 | 0 | 129.49 | Actual calendar duration may be shorter than effort/FTE because design, content, backend, QA and engineering can overlap. Dates remain TBD. | PROPOSED capacity model only
Recommended Team | 5 | 150 | 11654.1 | 77.694 | 0 | 0 | 77.694 | Actual calendar duration may be shorter than effort/FTE because design, content, backend, QA and engineering can overlap. Dates remain TBD. | PROPOSED capacity model only

## Delivery Roadmap
Estimation & Delivery Roadmap
Milestone roadmap after Decision Align v1.1. Start/End Week values are relative project weeks only — not calendar dates. Staffing TBD.
Milestone | Scope / Epic IDs | Outcome | Effort Hours | Parallel Factor | Effective Calendar Effort | Scenario | Weekly Capacity | Duration Weeks | Start Week | End Week | Status | Decision State
M0 Foundations | E01 | Approved implementation foundation and UX baseline | 303.6 | 0.7 | 212.52 | Recommended Team | 150 | 1.4168 | 1 | 2.4168 | Not Started | PROPOSED
M1 Playable Core | E03 | Complete playable rules engine with fixed QA boards | 1021.2 | 0.9 | 919.08 | Recommended Team | 150 | 6.1272 | 2.1334 | 8.2606 | Not Started | PROPOSED
M2 Solver-Validated Game | E04,E05 | Randomized Solver-validated gameplay + difficulty/generation | 1842.3 | 0.7 | 1289.61 | Recommended Team | 150 | 8.5974 | 7.0352 | 15.6326 | Not Started | PROPOSED
M3 Product Loop | E06,E07,E08,E09 | Tutorial, Journey, rewards, assistance and local resume | 1704.3 | 0.75 | 1278.225 | Recommended Team | 150 | 8.5215 | 13.9131 | 22.4346 | Not Started | PROPOSED
M4 Online Platform | E11,E12,E14 | Identity, Firebase/GCP serverless, cloud sync, telemetry and content delivery | 1766.4 | 0.7 | 1236.48 | Recommended Team | 150 | 8.2432 | 20.7303 | 28.9735 | Not Started | CONFIRMED
M5 CMS & Monetization | E10,E13 | Store/ad flows plus operational CMS/publishing | 1614.6 | 0.75 | 1210.95 | Recommended Team | 150 | 8.073 | 27.3249 | 35.3979 | Not Started | PROPOSED
M6 Release Hardening | E02,E18,E19,E20 | Launch content, automated validation, DevOps, security/compliance hardening | 2442.6 | 0.65 | 1587.69 | Recommended Team | 150 | 10.5846 | 33.7833 | 44.3679 | Not Started | PROPOSED
M7 Launch Daily Engagement (P0) | E15,E16,E17 | Daily Reward, Daily Challenge, Streak and smart notifications (launch P0) | 959.1 | 0.8 | 767.28 | Recommended Team | 150 | 5.1152 | 42.251 | 47.3662 | Not Started | CONFIRMED

## Role & Cost Plan
Role Effort & Cost Plan
Role hours are derived from task Story Points. Hourly rates are intentionally left at 0 and highlighted for input; cost becomes formula-driven after rates are entered.
Role | Task Count | Story Points | Base Hours | Contingency Hours | Planned Hours | Hourly Rate | Estimated Cost | Suggested FTE | Weeks at Suggested FTE | Decision State
QA Engineer | 170 | 569 | 3414 | 512.1 | 3926.1 | 0 | 0 | 0 |  | TBD
Game Engineer | 46 | 192 | 1152 | 172.8 | 1324.8 | 0 | 0 | 0 |  | TBD
Backend Engineer | 52 | 192 | 1152 | 172.8 | 1324.8 | 0 | 0 | 0 |  | TBD
Solver Engineer | 20 | 100 | 600 | 90 | 690 | 0 | 0 | 0 |  | TBD
Product Engineer | 20 | 66 | 396 | 59.4 | 455.4 | 0 | 0 | 0 |  | TBD
Admin Engineer | 12 | 57 | 342 | 51.3 | 393.3 | 0 | 0 | 0 |  | TBD
UI Engineer | 14 | 53 | 318 | 47.7 | 365.7 | 0 | 0 | 0 |  | TBD
Analytics Engineer | 16 | 48 | 288 | 43.2 | 331.2 | 0 | 0 | 0 |  | TBD
Mobile/Backend Engineer | 16 | 46 | 276 | 41.4 | 317.4 | 0 | 0 | 0 |  | TBD
DevOps Engineer | 12 | 40 | 240 | 36 | 276 | 0 | 0 | 0 |  | TBD
Mobile Engineer | 12 | 36 | 216 | 32.4 | 248.4 | 0 | 0 | 0 |  | TBD
Game Designer | 10 | 35 | 210 | 31.5 | 241.5 | 0 | 0 | 0 |  | TBD
QA/Solver Engineer | 4 | 24 | 144 | 21.6 | 165.6 | 0 | 0 | 0 |  | TBD
Content Designer | 6 | 21 | 126 | 18.9 | 144.9 | 0 | 0 | 0 |  | TBD
Backend/Admin Engineer | 4 | 19 | 114 | 17.1 | 131.1 | 0 | 0 | 0 |  | TBD
UX Designer | 4 | 12 | 72 | 10.8 | 82.8 | 0 | 0 | 0 |  | TBD
Content Team | 2 | 12 | 72 | 10.8 | 82.8 | 0 | 0 | 0 |  | TBD
Backend/Mobile Engineer | 4 | 12 | 72 | 10.8 | 82.8 | 0 | 0 | 0 |  | TBD
Admin/Game Engineer | 2 | 12 | 72 | 10.8 | 82.8 | 0 | 0 | 0 |  | TBD
Solver/Backend Engineer | 2 | 12 | 72 | 10.8 | 82.8 | 0 | 0 | 0 |  | TBD
QA/Game Engineer | 2 | 12 | 72 | 10.8 | 82.8 | 0 | 0 | 0 |  | TBD
UX/Game Designer | 2 | 7 | 42 | 6.3 | 48.3 | 0 | 0 | 0 |  | TBD
UI Designer | 2 | 7 | 42 | 6.3 | 48.3 | 0 | 0 | 0 |  | TBD
Content Architect | 2 | 7 | 42 | 6.3 | 48.3 | 0 | 0 | 0 |  | TBD
Content Engineer | 2 | 7 | 42 | 6.3 | 48.3 | 0 | 0 | 0 |  | TBD
Game Designer/Engineer | 2 | 7 | 42 | 6.3 | 48.3 | 0 | 0 | 0 |  | TBD
Analyst | 2 | 7 | 42 | 6.3 | 48.3 | 0 | 0 | 0 |  | TBD
Backend/Game Designer | 2 | 7 | 42 | 6.3 | 48.3 | 0 | 0 | 0 |  | TBD
Arabic Reviewer/QA | 2 | 7 | 42 | 6.3 | 48.3 | 0 | 0 | 0 |  | TBD
Mobile/DevOps Engineer | 2 | 7 | 42 | 6.3 | 48.3 | 0 | 0 | 0 |  | TBD
Product/Mobile Engineer | 2 | 7 | 42 | 6.3 | 48.3 | 0 | 0 | 0 |  | TBD
Mobile/UI Engineer | 2 | 7 | 42 | 6.3 | 48.3 | 0 | 0 | 0 |  | TBD
QA/Security | 2 | 7 | 42 | 6.3 | 48.3 | 0 | 0 | 0 |  | TBD
Product Owner | 2 | 5 | 30 | 4.5 | 34.5 | 0 | 0 | 0 |  | TBD
Content Lead | 2 | 5 | 30 | 4.5 | 34.5 | 0 | 0 | 0 |  | TBD
Arabic Reviewer | 2 | 5 | 30 | 4.5 | 34.5 | 0 | 0 | 0 |  | TBD
Game/Backend Engineer | 2 | 5 | 30 | 4.5 | 34.5 | 0 | 0 | 0 |  | TBD
Analytics/Solver Engineer | 2 | 5 | 30 | 4.5 | 34.5 | 0 | 0 | 0 |  | TBD
DevOps/Tech Lead | 2 | 5 | 30 | 4.5 | 34.5 | 0 | 0 | 0 |  | TBD
Product/Backend | 2 | 5 | 30 | 4.5 | 34.5 | 0 | 0 | 0 |  | TBD
Cost is zero until hourly rates are entered. Suggested FTE cells also default to zero because staffing has not been approved.

## Dependencies
Delivery Dependency Register
Dependencies are sequencing guidance derived from the architecture/specifications and should be refined when technical stack decisions are approved.
From | Depends On | Dependency | Type | Criticality | Can Overlap? | Notes
E04 Solver | E03 Game Engine | Shared authoritative state/rules | Technical | Critical | Partial | Solver prototypes can begin after core state/rules stabilize.
E05 Level Generator | E04 Solver | Solvability/reference/difficulty validation | Technical | Critical | Partial | Generator shell can start before solver final tuning.
E07 Main Journey | E05 Level Generator | Validated attempts | Functional | Critical | Partial | Journey UI can progress with fixtures.
E08 Economy | E03 Game Engine | Reward/streak domain events | Functional | High | Yes | Backend wallet can be developed in parallel.
E09 Assistance | E04 Solver | Hint/dead-end | Technical | Critical | Partial | UI can use mocked solver responses.
E10 Monetization | E08 Economy | Transaction-safe grants/spends | Transactional | Critical | Yes | SDK adapter work can overlap.
E11 Cloud Save | E08/E12 | Economy/progression reconciliation + Firebase backend | Data | Critical | Partial | Local persistence can begin early.
E13 CMS | E02/E04/E05 | Content schema + Solver/Level tooling | Functional | Critical | Yes | CRUD can precede full simulation tooling.
E14 Analytics | All P0 domains | Events and operational telemetry | Data | High | Yes | Instrumentation should be incremental.
E18 QA | E03/E04/E05 | Rules/Solver/generator | Quality | Critical | Yes | Starts from M1 and continues throughout.
E19 DevOps | E12 Backend | Deployment/runtime environments | Platform | High | Yes | GitHub Actions + Firebase/GCP; no Azure/K8s MVP baseline.
E20 Security | E10/E11/E12/E13 | Payments, identity, API and admin controls | Security | Critical | Yes | Security design starts early; hardening continues to release.

## Risk Register
Estimation & Delivery Risks
These risks directly affect delivery duration or estimate confidence. Ratings are proposed and should be reviewed after prototype/stack approval.
Risk ID | Risk | Estimate Impact | Likelihood | Impact | Rating | Mitigation | Estimate Reserve | Owner Role | Status
R01 | Solver complexity exceeds initial assumptions | High | Medium | Critical | High | Prototype first; benchmark; optimize/fallback | Contingency + solver spike | Solver Engineer | Open
R02 | Launch content quantity remains undefined | High | High | High | High | Approve launch content volume early | Separate content capacity buffer | Content Lead | Open
R03 | Rescue behavior previously TBD — now confirmed Solver-Guided Recovery | Medium | Medium | High | High | Resolve before assistance/economy freeze | Do not estimate implementation as final | Game Designer | Mitigated
R04 | Cloud sync conflict policy (domain-specific) — approved; implementation risk remains | Medium | Medium | High | High | Approve authority/merge model before cloud implementation | Follow Register v1.1 conflict matrix | Backend Engineer | Open
R05 | Firebase/GCP quotas or cost surprises after serverless rebase | Medium | Medium | High | High | Approve ADRs before production coding | Enable budget alerts; tune quotas before PROD; avoid always-on Azure rebuild unless justified | Tech Lead | Open
R06 | QA effort is unusually high because random-state game needs simulation | High | High | High | High | Keep automation integral to development | Already visible as explicit QA tasks | QA Lead | Open
R07 | Solo/small-team delivery creates role bottlenecks | High | High | High | High | Use scenario planning; outsource/reduce scope where needed | Capacity scenario | Product Owner | Open
R08 | Store/ads/privacy integration changes late | Medium | Medium | High | High | Select providers early; recheck policies before submission | Release reserve | Mobile Engineer | Open

## Decision Register
Delivery-Critical Decisions — aligned to Final Decision Register v1.1
Most architecture/economy items are now CONFIRMED. Remaining TBD: real-money prices, Firebase quotas/billing, staffing, calendar dates.
Decision | Area | Current Proposal | Affects Milestone | Estimate Impact | Status | Action
Client framework | Architecture | Flutter + Riverpod + Drift/SQLite | M0/M1 | Medium | CONFIRMED | Closed by Register v1.1
Solver algorithm/runtime | Solver | Pure client library first; benchmark variants | M1/M2 | High | TBD | Prototype on target devices.
Backend/cloud stack | Backend | Firebase-first (Auth/Firestore/Storage/Functions/Run/FCM/Remote Config); ASP.NET+PG DEFERRED; Azure SUPERSEDED | M0/M4 | Medium | CONFIRMED | Always-on Azure infra out of MVP (scope reduction)
Launch content quantity | Content | 5 Chapters / 250 Level Definitions | M6 | High | CONFIRMED | Register v1.1
Rescue behavior | Gameplay/Economy | Solver-Guided Recovery; 200 Coins; max 1; no Mid-Level Reshuffle MVP | M3/M5 | Medium | CONFIRMED | Register v1.1
Economy values | Economy | Confirmed Register v1.1 amounts | M3/M5 | Medium | CONFIRMED | Real-money prices still TBD
Daily inclusion in launch | Scope | Daily Reward/Challenge/Streak/Notifications are launch P0; Events post-launch | M7 | High | CONFIRMED | Moved from P1 to P0
Minimum OS/device support | Platform | iOS 15 / Android API 26; portrait only | M0/M6 | Medium | CONFIRMED | Register v1.1
Analytics/Ads/IAP providers | Integrations | Firebase Analytics+BigQuery+Crashlytics; AdMob+Mediation; IAP via Functions/Run | M5/M6 | Medium | CONFIRMED | Real-money prices & mediation mix details TBD
Offline transactional policy | Cloud/Economy | Offline Coin spend with queued idempotent reconciliation; ads/IAP require network | M3/M4 | Medium | CONFIRMED | Register v1.1
Firebase quotas/billing | Ops | Budgets/alerts required; exact limits TBD | M4/M6 | Medium | TBD | Do not invent numeric quotas
Staffing/calendar | Delivery | Team size, rates, dates TBD | All | High | TBD | Do not invent dates/staffing

## Executive Summary
MVP Estimation & Delivery Executive Summary
Decision Align v1.1 Firebase-first rebase. Daily moved into P0. Hours recalculated from task SP; cost remains 0 until rates entered. No committed calendar dates.
KPI | P0 | P1 | Total |  | Scenario | FTE | Eff. h/week | P0 Weeks | P0+P1 Weeks
Task Count | 468 | 0 | 468 |  | Solo / AI-Assisted | 1 | 30 | 388.47 | 388.47
Story Points | 1689 | 0 | 1689 |  | Lean Team | 3 | 90 | 129.49 | 129.49
Base Hours | 10134 | 0 | 10134 |  | Recommended Team | 5 | 150 | 77.694 | 77.694
Contingency Hours | 1520.1 | 0 | 1520.1
Planned Hours | 11654.1 | 0 | 11654.1
Role-based Estimated Cost |  |  | 0
Milestone | Outcome | Effort Hours | Duration Weeks | Start Week | End Week
M0 Foundations | Approved implementation foundation and UX baseline | 303.6 | 1.4168 | 1 | 2.4168
M1 Playable Core | Complete playable rules engine with fixed QA boards | 1021.2 | 6.1272 | 2.1334 | 8.2606
M2 Solver-Validated Game | Randomized Solver-validated gameplay + difficulty/generation | 1842.3 | 8.5974 | 7.0352 | 15.6326
M3 Product Loop | Tutorial, Journey, rewards, assistance and local resume | 1704.3 | 8.5215 | 13.9131 | 22.4346
M4 Online Platform | Identity, Firebase/GCP serverless, cloud sync, telemetry and content delivery | 1766.4 | 8.2432 | 20.7303 | 28.9735
M5 CMS & Monetization | Store/ad flows plus operational CMS/publishing | 1614.6 | 8.073 | 27.3249 | 35.3979
M6 Release Hardening | Launch content, automated validation, DevOps, security/compliance hardening | 2442.6 | 10.5846 | 33.7833 | 44.3679
M7 Launch Daily Engagement (P0) | Daily Reward, Daily Challenge, Streak and smart notifications (launch P0) | 959.1 | 5.1152 | 42.251 | 47.3662
Planning Interpretation
1 | Task-only estimate | Parent Feature Story Points are excluded from duration/cost totals to avoid double counting.
2 | Contingency | Default 15% reserve is editable and explicitly PROPOSED.
3 | Calendar vs effort | Scenario weeks are pure capacity math; milestone roadmap applies overlap factors to represent parallel work.
4 | P1 | Daily engagement is kept separate so it can be launch scope or immediate post-launch without rewriting P0.
5 | Costs | All role/hourly rates default to zero until explicitly entered.

## Decision Align v1.1
Decision Align v1.1 — Firebase-First Rebase
Source | Final Decision Register v1.1
Applied | 2026-08-21
Recalculated | Value
P0 Planned Hours | 11654.1
P1 Planned Hours | 0
P0 Tasks | 468
P1 Tasks | 0
P0 Story Points | 1689
P1 Story Points | 0
Notes | E12 retargeted to Firebase serverless (reallocation away from always-on Azure/ASP.NET/PG). Daily E15–E17 moved into P0. No invented staffing counts or calendar dates. Real-money prices and Firebase quotas/billing remain TBD.