## Lookups
Status | Priority | Phase | Decision State | Risk Rating | Release Status
Not Started | Critical | MVP-P0 | CONFIRMED | Critical | Not Started
In Progress | High | MVP-P1 | CONFIRMED CONCEPT | High | In Progress
Blocked | Medium | Post-MVP | CONFIRMED FULL PRODUCT | Medium | Blocked
Ready for QA | Low |  | CONFIRMED SCOPE | Low | Done
Done |  |  | CONFIRMED STRATEGY
Deferred |  |  | CONFIRMED/PROPOSED
CONFIRMED/PROPOSED ARCH
CONFIRMED/REQUIRED
CONFIRMED/TBD
PROPOSED
PROPOSED ARCH
PROPOSED MVP
PROPOSED UX
REQUIRED
TBD
TBD BEHAVIOR
TBD PROVIDERS
TBD QUANTITY

## Estimation Inputs
Estimation & Planning Inputs
Yellow cells are editable. All starting values are PROPOSED placeholders, not approved commercial commitments.
Input | Value | Status / Guidance
Hours per Story Point | 6 | PROPOSED — calibrate after first sprint
Hourly Rate | 0 | TBD — enter blended hourly rate
Working Hours / Day | 8 | PROPOSED default
Working Days / Week | 5 | PROPOSED default
Team Capacity Factor | 0.8 | PROPOSED
Contingency % | 0.15 | PROPOSED
Currency | EGP | TBD / editable

## Product Backlog
MVP Product Backlog / WBS
Detailed Feature → Technical Task baseline. Decision Align v1.1 Firebase-first rebase applied. Story Points are planning placeholders; Hours = SP × Hours/SP from Estimation Inputs; Cost stays 0 until rate entered. Calendar dates/staffing remain TBD.
WBS | Epic ID | Epic | Item ID | Item | Type | Description | Phase | Priority | Decision State | Primary Role | Story Points | Hours | Cost | Status | Dependencies | Parent | Acceptance Criteria | Notes | Workstream
001 | E01 | Product & UX Foundation | F01.1 | Information Architecture | Feature | Define MVP navigation/screen hierarchy | MVP-P0 | High | PROPOSED | Product Owner | 5 | 30 | 0 | Not Started |  | E01 | Feature behavior matches the approved specification and has test evidence. |  | Product/UX
002 | E01 | Product & UX Foundation | F01.1.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Information Architecture. | MVP-P0 | High | PROPOSED | Product Owner | 2 | 12 | 0 | Not Started |  | F01.1 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
003 | E01 | Product & UX Foundation | F01.1.T2 | Implementation | Task | Implement Information Architecture with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED | Product Owner | 3 | 18 | 0 | Not Started |  | F01.1 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
004 | E01 | Product & UX Foundation | F01.1.T3 | Validation & QA | Task | Add automated/manual validation for Information Architecture; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED | QA Engineer | 2 | 12 | 0 | Not Started |  | F01.1 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
005 | E01 | Product & UX Foundation | F01.2 | Gameplay Interaction Specification | Feature | Define drag/drop states, target feedback and overlay precedence | MVP-P0 | High | PROPOSED | UX/Game Designer | 8 | 48 | 0 | Not Started |  | E01 | Feature behavior matches the approved specification and has test evidence. |  | Product/UX
006 | E01 | Product & UX Foundation | F01.2.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Gameplay Interaction Specification. | MVP-P0 | High | PROPOSED | UX/Game Designer | 3 | 18 | 0 | Not Started |  | F01.2 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
007 | E01 | Product & UX Foundation | F01.2.T2 | Implementation | Task | Implement Gameplay Interaction Specification with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED | UX/Game Designer | 4 | 24 | 0 | Not Started |  | F01.2 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
008 | E01 | Product & UX Foundation | F01.2.T3 | Validation & QA | Task | Add automated/manual validation for Gameplay Interaction Specification; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED | QA Engineer | 3 | 18 | 0 | Not Started |  | F01.2 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
009 | E01 | Product & UX Foundation | F01.3 | Low-Fidelity Wireframes | Feature | Wireframe onboarding, Home, Journey, Gameplay, completion, Shop, Account, Settings | MVP-P0 | High | PROPOSED | UX Designer | 8 | 48 | 0 | Not Started |  | E01 | Feature behavior matches the approved specification and has test evidence. |  | Product/UX
010 | E01 | Product & UX Foundation | F01.3.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Low-Fidelity Wireframes. | MVP-P0 | High | PROPOSED | UX Designer | 3 | 18 | 0 | Not Started |  | F01.3 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
011 | E01 | Product & UX Foundation | F01.3.T2 | Implementation | Task | Implement Low-Fidelity Wireframes with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED | UX Designer | 4 | 24 | 0 | Not Started |  | F01.3 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
012 | E01 | Product & UX Foundation | F01.3.T3 | Validation & QA | Task | Add automated/manual validation for Low-Fidelity Wireframes; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED | QA Engineer | 3 | 18 | 0 | Not Started |  | F01.3 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
013 | E01 | Product & UX Foundation | F01.4 | Design System Foundation | Feature | Define card, button, modal, typography, spacing, RTL and state components | MVP-P0 | High | PROPOSED | UI Designer | 8 | 48 | 0 | Not Started |  | E01 | Feature behavior matches the approved specification and has test evidence. |  | Product/UX
014 | E01 | Product & UX Foundation | F01.4.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Design System Foundation. | MVP-P0 | High | PROPOSED | UI Designer | 3 | 18 | 0 | Not Started |  | F01.4 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
015 | E01 | Product & UX Foundation | F01.4.T2 | Implementation | Task | Implement Design System Foundation with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED | UI Designer | 4 | 24 | 0 | Not Started |  | F01.4 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
016 | E01 | Product & UX Foundation | F01.4.T3 | Validation & QA | Task | Add automated/manual validation for Design System Foundation; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED | QA Engineer | 3 | 18 | 0 | Not Started |  | F01.4 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
017 | E01 | Product & UX Foundation | F01.5 | Accessibility UX Baseline | Feature | Define contrast, touch target, text scaling and screen-reader expectations | MVP-P0 | High | PROPOSED | UX Designer | 5 | 30 | 0 | Not Started |  | E01 | Feature behavior matches the approved specification and has test evidence. |  | Product/UX
018 | E01 | Product & UX Foundation | F01.5.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Accessibility UX Baseline. | MVP-P0 | High | PROPOSED | UX Designer | 2 | 12 | 0 | Not Started |  | F01.5 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
019 | E01 | Product & UX Foundation | F01.5.T2 | Implementation | Task | Implement Accessibility UX Baseline with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED | UX Designer | 3 | 18 | 0 | Not Started |  | F01.5 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
020 | E01 | Product & UX Foundation | F01.5.T3 | Validation & QA | Task | Add automated/manual validation for Accessibility UX Baseline; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED | QA Engineer | 2 | 12 | 0 | Not Started |  | F01.5 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
021 | E02 | Arabic Content System | F02.1 | Content Metadata Schema | Feature | Association, Member, Variant, alias, tag, status and version metadata | MVP-P0 | High | CONFIRMED/PROPOSED | Content Architect | 8 | 48 | 0 | Not Started |  | E02 | Feature behavior matches the approved specification and has test evidence. |  | Content
022 | E02 | Arabic Content System | F02.1.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Content Metadata Schema. | MVP-P0 | High | CONFIRMED/PROPOSED | Content Architect | 3 | 18 | 0 | Not Started |  | F02.1 | Done when implementation/validation is traceable to the parent feature. |  | Content
023 | E02 | Arabic Content System | F02.1.T2 | Implementation | Task | Implement Content Metadata Schema with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED/PROPOSED | Content Architect | 4 | 24 | 0 | Not Started |  | F02.1 | Done when implementation/validation is traceable to the parent feature. |  | Content
024 | E02 | Arabic Content System | F02.1.T3 | Validation & QA | Task | Add automated/manual validation for Content Metadata Schema; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED/PROPOSED | QA Engineer | 3 | 18 | 0 | Not Started |  | F02.1 | Done when implementation/validation is traceable to the parent feature. |  | Content
025 | E02 | Arabic Content System | F02.2 | Arabic Editorial Workflow | Feature | Language and semantic review states and reviewer notes | MVP-P0 | High | PROPOSED | Content Lead | 5 | 30 | 0 | Not Started |  | E02 | Feature behavior matches the approved specification and has test evidence. |  | Content
026 | E02 | Arabic Content System | F02.2.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Arabic Editorial Workflow. | MVP-P0 | High | PROPOSED | Content Lead | 2 | 12 | 0 | Not Started |  | F02.2 | Done when implementation/validation is traceable to the parent feature. |  | Content
027 | E02 | Arabic Content System | F02.2.T2 | Implementation | Task | Implement Arabic Editorial Workflow with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED | Content Lead | 3 | 18 | 0 | Not Started |  | F02.2 | Done when implementation/validation is traceable to the parent feature. |  | Content
028 | E02 | Arabic Content System | F02.2.T3 | Validation & QA | Task | Add automated/manual validation for Arabic Editorial Workflow; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED | QA Engineer | 2 | 12 | 0 | Not Started |  | F02.2 | Done when implementation/validation is traceable to the parent feature. |  | Content
029 | E02 | Arabic Content System | F02.3 | Association Authoring | Feature | Full relation, card clue, relation type and difficulty metadata | MVP-P0 | High | CONFIRMED | Content Designer | 8 | 48 | 0 | Not Started |  | E02 | Feature behavior matches the approved specification and has test evidence. |  | Content
030 | E02 | Arabic Content System | F02.3.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Association Authoring. | MVP-P0 | High | CONFIRMED | Content Designer | 3 | 18 | 0 | Not Started |  | F02.3 | Done when implementation/validation is traceable to the parent feature. |  | Content
031 | E02 | Arabic Content System | F02.3.T2 | Implementation | Task | Implement Association Authoring with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Content Designer | 4 | 24 | 0 | Not Started |  | F02.3 | Done when implementation/validation is traceable to the parent feature. |  | Content
032 | E02 | Arabic Content System | F02.3.T3 | Validation & QA | Task | Add automated/manual validation for Association Authoring; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F02.3 | Done when implementation/validation is traceable to the parent feature. |  | Content
033 | E02 | Arabic Content System | F02.4 | Member Authoring | Feature | Text, number, symbol, emoji and illustration member records | MVP-P0 | High | CONFIRMED | Content Designer | 8 | 48 | 0 | Not Started |  | E02 | Feature behavior matches the approved specification and has test evidence. |  | Content
034 | E02 | Arabic Content System | F02.4.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Member Authoring. | MVP-P0 | High | CONFIRMED | Content Designer | 3 | 18 | 0 | Not Started |  | F02.4 | Done when implementation/validation is traceable to the parent feature. |  | Content
035 | E02 | Arabic Content System | F02.4.T2 | Implementation | Task | Implement Member Authoring with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Content Designer | 4 | 24 | 0 | Not Started |  | F02.4 | Done when implementation/validation is traceable to the parent feature. |  | Content
036 | E02 | Arabic Content System | F02.4.T3 | Validation & QA | Task | Add automated/manual validation for Member Authoring; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F02.4 | Done when implementation/validation is traceable to the parent feature. |  | Content
037 | E02 | Arabic Content System | F02.5 | Variant Authoring | Feature | Curate homogeneous member sets for 3/4/5-card groups | MVP-P0 | High | CONFIRMED | Content Designer | 8 | 48 | 0 | Not Started |  | E02 | Feature behavior matches the approved specification and has test evidence. |  | Content
038 | E02 | Arabic Content System | F02.5.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Variant Authoring. | MVP-P0 | High | CONFIRMED | Content Designer | 3 | 18 | 0 | Not Started |  | F02.5 | Done when implementation/validation is traceable to the parent feature. |  | Content
039 | E02 | Arabic Content System | F02.5.T2 | Implementation | Task | Implement Variant Authoring with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Content Designer | 4 | 24 | 0 | Not Started |  | F02.5 | Done when implementation/validation is traceable to the parent feature. |  | Content
040 | E02 | Arabic Content System | F02.5.T3 | Validation & QA | Task | Add automated/manual validation for Variant Authoring; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F02.5 | Done when implementation/validation is traceable to the parent feature. |  | Content
041 | E02 | Arabic Content System | F02.6 | Arabic Validation Rules | Feature | Normalization/search warnings and suspicious-character checks | MVP-P0 | High | PROPOSED | Arabic Reviewer | 5 | 30 | 0 | Not Started |  | E02 | Feature behavior matches the approved specification and has test evidence. |  | Content
042 | E02 | Arabic Content System | F02.6.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Arabic Validation Rules. | MVP-P0 | High | PROPOSED | Arabic Reviewer | 2 | 12 | 0 | Not Started |  | F02.6 | Done when implementation/validation is traceable to the parent feature. |  | Content
043 | E02 | Arabic Content System | F02.6.T2 | Implementation | Task | Implement Arabic Validation Rules with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED | Arabic Reviewer | 3 | 18 | 0 | Not Started |  | F02.6 | Done when implementation/validation is traceable to the parent feature. |  | Content
044 | E02 | Arabic Content System | F02.6.T3 | Validation & QA | Task | Add automated/manual validation for Arabic Validation Rules; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED | QA Engineer | 2 | 12 | 0 | Not Started |  | F02.6 | Done when implementation/validation is traceable to the parent feature. |  | Content
045 | E02 | Arabic Content System | F02.7 | Duplicate & Conflict Checks | Feature | Exact duplicates, variant overlap and same-level conflicts | MVP-P0 | High | PROPOSED | Content Engineer | 8 | 48 | 0 | Not Started |  | E02 | Feature behavior matches the approved specification and has test evidence. |  | Content
046 | E02 | Arabic Content System | F02.7.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Duplicate & Conflict Checks. | MVP-P0 | High | PROPOSED | Content Engineer | 3 | 18 | 0 | Not Started |  | F02.7 | Done when implementation/validation is traceable to the parent feature. |  | Content
047 | E02 | Arabic Content System | F02.7.T2 | Implementation | Task | Implement Duplicate & Conflict Checks with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED | Content Engineer | 4 | 24 | 0 | Not Started |  | F02.7 | Done when implementation/validation is traceable to the parent feature. |  | Content
048 | E02 | Arabic Content System | F02.7.T3 | Validation & QA | Task | Add automated/manual validation for Duplicate & Conflict Checks; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED | QA Engineer | 3 | 18 | 0 | Not Started |  | F02.7 | Done when implementation/validation is traceable to the parent feature. |  | Content
049 | E02 | Arabic Content System | F02.8 | Launch Content Production | Feature | Produce and human-review initial content set | MVP-P0 | High | TBD QUANTITY | Content Team | 13 | 78 | 0 | Not Started |  | E02 | Feature behavior matches the approved specification and has test evidence. |  | Content
050 | E02 | Arabic Content System | F02.8.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Launch Content Production. | MVP-P0 | High | TBD QUANTITY | Content Team | 5 | 30 | 0 | Not Started |  | F02.8 | Done when implementation/validation is traceable to the parent feature. |  | Content
051 | E02 | Arabic Content System | F02.8.T2 | Implementation | Task | Implement Launch Content Production with versioned/configurable behavior where required. | MVP-P0 | High | TBD QUANTITY | Content Team | 7 | 42 | 0 | Not Started |  | F02.8 | Done when implementation/validation is traceable to the parent feature. |  | Content
052 | E02 | Arabic Content System | F02.8.T3 | Validation & QA | Task | Add automated/manual validation for Launch Content Production; cover error, retry and regression cases. | MVP-P0 | High | TBD QUANTITY | QA Engineer | 5 | 30 | 0 | Not Started |  | F02.8 | Done when implementation/validation is traceable to the parent feature. |  | Content
053 | E03 | Game Engine | F03.1 | Core Domain Models | Feature | Cards, Associations, MovableUnits, Stacks, Tableau, Stock and Slots | MVP-P0 | High | CONFIRMED | Game Engineer | 13 | 78 | 0 | Not Started |  | E03 | Feature behavior matches the approved specification and has test evidence. |  | Engineering
054 | E03 | Game Engine | F03.1.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Core Domain Models. | MVP-P0 | High | CONFIRMED | Game Engineer | 5 | 30 | 0 | Not Started |  | F03.1 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
055 | E03 | Game Engine | F03.1.T2 | Implementation | Task | Implement Core Domain Models with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Game Engineer | 7 | 42 | 0 | Not Started |  | F03.1 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
056 | E03 | Game Engine | F03.1.T3 | Validation & QA | Task | Add automated/manual validation for Core Domain Models; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 5 | 30 | 0 | Not Started |  | F03.1 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
057 | E03 | Game Engine | F03.2 | Rule Engine | Feature | Shared move legality rules | MVP-P0 | High | CONFIRMED | Game Engineer | 13 | 78 | 0 | Not Started |  | E03 | Feature behavior matches the approved specification and has test evidence. |  | Engineering
058 | E03 | Game Engine | F03.2.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Rule Engine. | MVP-P0 | High | CONFIRMED | Game Engineer | 5 | 30 | 0 | Not Started |  | F03.2 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
059 | E03 | Game Engine | F03.2.T2 | Implementation | Task | Implement Rule Engine with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Game Engineer | 7 | 42 | 0 | Not Started |  | F03.2 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
060 | E03 | Game Engine | F03.2.T3 | Validation & QA | Task | Add automated/manual validation for Rule Engine; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 5 | 30 | 0 | Not Started |  | F03.2 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
061 | E03 | Game Engine | F03.3 | Move Executor | Feature | Atomic state transitions and move-cost accounting | MVP-P0 | High | CONFIRMED | Game Engineer | 13 | 78 | 0 | Not Started |  | E03 | Feature behavior matches the approved specification and has test evidence. |  | Engineering
062 | E03 | Game Engine | F03.3.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Move Executor. | MVP-P0 | High | CONFIRMED | Game Engineer | 5 | 30 | 0 | Not Started |  | F03.3 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
063 | E03 | Game Engine | F03.3.T2 | Implementation | Task | Implement Move Executor with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Game Engineer | 7 | 42 | 0 | Not Started |  | F03.3 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
064 | E03 | Game Engine | F03.3.T3 | Validation & QA | Task | Add automated/manual validation for Move Executor; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 5 | 30 | 0 | Not Started |  | F03.3 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
065 | E03 | Game Engine | F03.4 | Stack Engine | Feature | Member stacks, merges, atomicity and association-stack lock | MVP-P0 | High | CONFIRMED | Game Engineer | 8 | 48 | 0 | Not Started |  | E03 | Feature behavior matches the approved specification and has test evidence. |  | Engineering
066 | E03 | Game Engine | F03.4.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Stack Engine. | MVP-P0 | High | CONFIRMED | Game Engineer | 3 | 18 | 0 | Not Started |  | F03.4 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
067 | E03 | Game Engine | F03.4.T2 | Implementation | Task | Implement Stack Engine with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Game Engineer | 4 | 24 | 0 | Not Started |  | F03.4 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
068 | E03 | Game Engine | F03.4.T3 | Validation & QA | Task | Add automated/manual validation for Stack Engine; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F03.4 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
069 | E03 | Game Engine | F03.5 | Tableau Engine | Feature | Columns, empty-column moves and automatic reveal | MVP-P0 | High | CONFIRMED | Game Engineer | 8 | 48 | 0 | Not Started |  | E03 | Feature behavior matches the approved specification and has test evidence. |  | Engineering
070 | E03 | Game Engine | F03.5.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Tableau Engine. | MVP-P0 | High | CONFIRMED | Game Engineer | 3 | 18 | 0 | Not Started |  | F03.5 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
071 | E03 | Game Engine | F03.5.T2 | Implementation | Task | Implement Tableau Engine with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Game Engineer | 4 | 24 | 0 | Not Started |  | F03.5 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
072 | E03 | Game Engine | F03.5.T3 | Validation & QA | Task | Add automated/manual validation for Tableau Engine; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F03.5 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
073 | E03 | Game Engine | F03.6 | Stock Engine | Feature | 3-visible/top-playable Stock, advance and same-order Restore | MVP-P0 | High | CONFIRMED | Game Engineer | 13 | 78 | 0 | Not Started |  | E03 | Feature behavior matches the approved specification and has test evidence. |  | Engineering
074 | E03 | Game Engine | F03.6.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Stock Engine. | MVP-P0 | High | CONFIRMED | Game Engineer | 5 | 30 | 0 | Not Started |  | F03.6 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
075 | E03 | Game Engine | F03.6.T2 | Implementation | Task | Implement Stock Engine with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Game Engineer | 7 | 42 | 0 | Not Started |  | F03.6 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
076 | E03 | Game Engine | F03.6.T3 | Validation & QA | Task | Add automated/manual validation for Stock Engine; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 5 | 30 | 0 | Not Started |  | F03.6 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
077 | E03 | Game Engine | F03.7 | Association Slot Engine | Feature | Activation, member transfer, completion and slot freeing | MVP-P0 | High | CONFIRMED | Game Engineer | 8 | 48 | 0 | Not Started |  | E03 | Feature behavior matches the approved specification and has test evidence. |  | Engineering
078 | E03 | Game Engine | F03.7.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Association Slot Engine. | MVP-P0 | High | CONFIRMED | Game Engineer | 3 | 18 | 0 | Not Started |  | F03.7 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
079 | E03 | Game Engine | F03.7.T2 | Implementation | Task | Implement Association Slot Engine with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Game Engineer | 4 | 24 | 0 | Not Started |  | F03.7 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
080 | E03 | Game Engine | F03.7.T3 | Validation & QA | Task | Add automated/manual validation for Association Slot Engine; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F03.7 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
081 | E03 | Game Engine | F03.8 | Move Counter & Win Evaluator | Feature | Fixed move limit, final-move win and out-of-moves transition | MVP-P0 | High | CONFIRMED | Game Engineer | 8 | 48 | 0 | Not Started |  | E03 | Feature behavior matches the approved specification and has test evidence. |  | Engineering
082 | E03 | Game Engine | F03.8.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Move Counter & Win Evaluator. | MVP-P0 | High | CONFIRMED | Game Engineer | 3 | 18 | 0 | Not Started |  | F03.8 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
083 | E03 | Game Engine | F03.8.T2 | Implementation | Task | Implement Move Counter & Win Evaluator with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Game Engineer | 4 | 24 | 0 | Not Started |  | F03.8 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
084 | E03 | Game Engine | F03.8.T3 | Validation & QA | Task | Add automated/manual validation for Move Counter & Win Evaluator; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F03.8 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
085 | E03 | Game Engine | F03.9 | Streak Engine | Feature | 3→4→5 streak tiers, neutral actions and invalid reset | MVP-P0 | High | CONFIRMED | Game Engineer | 8 | 48 | 0 | Not Started |  | E03 | Feature behavior matches the approved specification and has test evidence. |  | Engineering
086 | E03 | Game Engine | F03.9.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Streak Engine. | MVP-P0 | High | CONFIRMED | Game Engineer | 3 | 18 | 0 | Not Started |  | F03.9 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
087 | E03 | Game Engine | F03.9.T2 | Implementation | Task | Implement Streak Engine with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Game Engineer | 4 | 24 | 0 | Not Started |  | F03.9 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
088 | E03 | Game Engine | F03.9.T3 | Validation & QA | Task | Add automated/manual validation for Streak Engine; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F03.9 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
089 | E03 | Game Engine | F03.10 | Undo Engine | Feature | Single eligible undo and completion restriction | MVP-P0 | High | CONFIRMED | Game Engineer | 8 | 48 | 0 | Not Started |  | E03 | Feature behavior matches the approved specification and has test evidence. |  | Engineering
090 | E03 | Game Engine | F03.10.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Undo Engine. | MVP-P0 | High | CONFIRMED | Game Engineer | 3 | 18 | 0 | Not Started |  | F03.10 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
091 | E03 | Game Engine | F03.10.T2 | Implementation | Task | Implement Undo Engine with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Game Engineer | 4 | 24 | 0 | Not Started |  | F03.10 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
092 | E03 | Game Engine | F03.10.T3 | Validation & QA | Task | Add automated/manual validation for Undo Engine; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F03.10 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
093 | E03 | Game Engine | F03.11 | State Serialization | Feature | Serializable state, versioning and revision hooks | MVP-P0 | High | PROPOSED | Game Engineer | 8 | 48 | 0 | Not Started |  | E03 | Feature behavior matches the approved specification and has test evidence. |  | Engineering
094 | E03 | Game Engine | F03.11.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for State Serialization. | MVP-P0 | High | PROPOSED | Game Engineer | 3 | 18 | 0 | Not Started |  | F03.11 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
095 | E03 | Game Engine | F03.11.T2 | Implementation | Task | Implement State Serialization with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED | Game Engineer | 4 | 24 | 0 | Not Started |  | F03.11 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
096 | E03 | Game Engine | F03.11.T3 | Validation & QA | Task | Add automated/manual validation for State Serialization; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED | QA Engineer | 3 | 18 | 0 | Not Started |  | F03.11 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
097 | E03 | Game Engine | F03.12 | Replay Engine | Feature | Deterministic replay for QA/debug | MVP-P0 | High | PROPOSED | Game Engineer | 8 | 48 | 0 | Not Started |  | E03 | Feature behavior matches the approved specification and has test evidence. |  | Engineering
098 | E03 | Game Engine | F03.12.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Replay Engine. | MVP-P0 | High | PROPOSED | Game Engineer | 3 | 18 | 0 | Not Started |  | F03.12 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
099 | E03 | Game Engine | F03.12.T2 | Implementation | Task | Implement Replay Engine with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED | Game Engineer | 4 | 24 | 0 | Not Started |  | F03.12 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
100 | E03 | Game Engine | F03.12.T3 | Validation & QA | Task | Add automated/manual validation for Replay Engine; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED | QA Engineer | 3 | 18 | 0 | Not Started |  | F03.12 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
101 | E04 | Solver | F04.1 | Solver State Adapter | Feature | Map engine canonical state to search state | MVP-P0 | High | CONFIRMED | Solver Engineer | 8 | 48 | 0 | Not Started |  | E04 | Feature behavior matches the approved specification and has test evidence. |  | Engineering
102 | E04 | Solver | F04.1.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Solver State Adapter. | MVP-P0 | High | CONFIRMED | Solver Engineer | 3 | 18 | 0 | Not Started |  | F04.1 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
103 | E04 | Solver | F04.1.T2 | Implementation | Task | Implement Solver State Adapter with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Solver Engineer | 4 | 24 | 0 | Not Started |  | F04.1 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
104 | E04 | Solver | F04.1.T3 | Validation & QA | Task | Add automated/manual validation for Solver State Adapter; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F04.1 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
105 | E04 | Solver | F04.2 | Legal Move Enumeration | Feature | Enumerate all legal solver actions | MVP-P0 | High | CONFIRMED | Solver Engineer | 13 | 78 | 0 | Not Started |  | E04 | Feature behavior matches the approved specification and has test evidence. |  | Engineering
106 | E04 | Solver | F04.2.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Legal Move Enumeration. | MVP-P0 | High | CONFIRMED | Solver Engineer | 5 | 30 | 0 | Not Started |  | F04.2 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
107 | E04 | Solver | F04.2.T2 | Implementation | Task | Implement Legal Move Enumeration with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Solver Engineer | 7 | 42 | 0 | Not Started |  | F04.2 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
108 | E04 | Solver | F04.2.T3 | Validation & QA | Task | Add automated/manual validation for Legal Move Enumeration; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 5 | 30 | 0 | Not Started |  | F04.2 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
109 | E04 | Solver | F04.3 | State Canonicalization | Feature | Canonicalize atomic stacks/equivalent states | MVP-P0 | High | PROPOSED | Solver Engineer | 13 | 78 | 0 | Not Started |  | E04 | Feature behavior matches the approved specification and has test evidence. |  | Engineering
110 | E04 | Solver | F04.3.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for State Canonicalization. | MVP-P0 | High | PROPOSED | Solver Engineer | 5 | 30 | 0 | Not Started |  | F04.3 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
111 | E04 | Solver | F04.3.T2 | Implementation | Task | Implement State Canonicalization with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED | Solver Engineer | 7 | 42 | 0 | Not Started |  | F04.3 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
112 | E04 | Solver | F04.3.T3 | Validation & QA | Task | Add automated/manual validation for State Canonicalization; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED | QA Engineer | 5 | 30 | 0 | Not Started |  | F04.3 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
113 | E04 | Solver | F04.4 | Visited-State / Dominance Pruning | Feature | Prevent cycles including unlimited Restore loops | MVP-P0 | High | PROPOSED | Solver Engineer | 13 | 78 | 0 | Not Started |  | E04 | Feature behavior matches the approved specification and has test evidence. |  | Engineering
114 | E04 | Solver | F04.4.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Visited-State / Dominance Pruning. | MVP-P0 | High | PROPOSED | Solver Engineer | 5 | 30 | 0 | Not Started |  | F04.4 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
115 | E04 | Solver | F04.4.T2 | Implementation | Task | Implement Visited-State / Dominance Pruning with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED | Solver Engineer | 7 | 42 | 0 | Not Started |  | F04.4 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
116 | E04 | Solver | F04.4.T3 | Validation & QA | Task | Add automated/manual validation for Visited-State / Dominance Pruning; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED | QA Engineer | 5 | 30 | 0 | Not Started |  | F04.4 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
117 | E04 | Solver | F04.5 | Move-Bounded Solvability | Feature | Find winning path within fixed Move Limit | MVP-P0 | High | CONFIRMED | Solver Engineer | 13 | 78 | 0 | Not Started |  | E04 | Feature behavior matches the approved specification and has test evidence. |  | Engineering
118 | E04 | Solver | F04.5.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Move-Bounded Solvability. | MVP-P0 | High | CONFIRMED | Solver Engineer | 5 | 30 | 0 | Not Started |  | F04.5 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
119 | E04 | Solver | F04.5.T2 | Implementation | Task | Implement Move-Bounded Solvability with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Solver Engineer | 7 | 42 | 0 | Not Started |  | F04.5 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
120 | E04 | Solver | F04.5.T3 | Validation & QA | Task | Add automated/manual validation for Move-Bounded Solvability; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 5 | 30 | 0 | Not Started |  | F04.5 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
121 | E04 | Solver | F04.6 | Reference Solution | Feature | Return solution/reference move count; exact-minimum policy configurable | MVP-P0 | High | CONFIRMED/TBD | Solver Engineer | 13 | 78 | 0 | Not Started |  | E04 | Feature behavior matches the approved specification and has test evidence. |  | Engineering
122 | E04 | Solver | F04.6.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Reference Solution. | MVP-P0 | High | CONFIRMED/TBD | Solver Engineer | 5 | 30 | 0 | Not Started |  | F04.6 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
123 | E04 | Solver | F04.6.T2 | Implementation | Task | Implement Reference Solution with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED/TBD | Solver Engineer | 7 | 42 | 0 | Not Started |  | F04.6 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
124 | E04 | Solver | F04.6.T3 | Validation & QA | Task | Add automated/manual validation for Reference Solution; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED/TBD | QA Engineer | 5 | 30 | 0 | Not Started |  | F04.6 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
125 | E04 | Solver | F04.7 | Hint Engine | Feature | Safe structured next move from winning continuation | MVP-P0 | High | CONFIRMED | Solver Engineer | 8 | 48 | 0 | Not Started |  | E04 | Feature behavior matches the approved specification and has test evidence. |  | Engineering
126 | E04 | Solver | F04.7.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Hint Engine. | MVP-P0 | High | CONFIRMED | Solver Engineer | 3 | 18 | 0 | Not Started |  | F04.7 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
127 | E04 | Solver | F04.7.T2 | Implementation | Task | Implement Hint Engine with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Solver Engineer | 4 | 24 | 0 | Not Started |  | F04.7 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
128 | E04 | Solver | F04.7.T3 | Validation & QA | Task | Add automated/manual validation for Hint Engine; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F04.7 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
129 | E04 | Solver | F04.8 | Dead-End Detection | Feature | Detect no-solution state | MVP-P0 | High | CONFIRMED/TBD | Solver Engineer | 13 | 78 | 0 | Not Started |  | E04 | Feature behavior matches the approved specification and has test evidence. |  | Engineering
130 | E04 | Solver | F04.8.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Dead-End Detection. | MVP-P0 | High | CONFIRMED/TBD | Solver Engineer | 5 | 30 | 0 | Not Started |  | F04.8 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
131 | E04 | Solver | F04.8.T2 | Implementation | Task | Implement Dead-End Detection with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED/TBD | Solver Engineer | 7 | 42 | 0 | Not Started |  | F04.8 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
132 | E04 | Solver | F04.8.T3 | Validation & QA | Task | Add automated/manual validation for Dead-End Detection; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED/TBD | QA Engineer | 5 | 30 | 0 | Not Started |  | F04.8 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
133 | E04 | Solver | F04.9 | Solver Metrics | Feature | Expose branch, Stock, Restore and pacing metrics | MVP-P0 | High | PROPOSED | Solver Engineer | 8 | 48 | 0 | Not Started |  | E04 | Feature behavior matches the approved specification and has test evidence. |  | Engineering
134 | E04 | Solver | F04.9.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Solver Metrics. | MVP-P0 | High | PROPOSED | Solver Engineer | 3 | 18 | 0 | Not Started |  | F04.9 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
135 | E04 | Solver | F04.9.T2 | Implementation | Task | Implement Solver Metrics with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED | Solver Engineer | 4 | 24 | 0 | Not Started |  | F04.9 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
136 | E04 | Solver | F04.9.T3 | Validation & QA | Task | Add automated/manual validation for Solver Metrics; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED | QA Engineer | 3 | 18 | 0 | Not Started |  | F04.9 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
137 | E04 | Solver | F04.10 | Timeout/Cancellation | Feature | Cancellation and safe inconclusive handling | MVP-P0 | High | PROPOSED | Solver Engineer | 8 | 48 | 0 | Not Started |  | E04 | Feature behavior matches the approved specification and has test evidence. |  | Engineering
138 | E04 | Solver | F04.10.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Timeout/Cancellation. | MVP-P0 | High | PROPOSED | Solver Engineer | 3 | 18 | 0 | Not Started |  | F04.10 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
139 | E04 | Solver | F04.10.T2 | Implementation | Task | Implement Timeout/Cancellation with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED | Solver Engineer | 4 | 24 | 0 | Not Started |  | F04.10 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
140 | E04 | Solver | F04.10.T3 | Validation & QA | Task | Add automated/manual validation for Timeout/Cancellation; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED | QA Engineer | 3 | 18 | 0 | Not Started |  | F04.10 | Done when implementation/validation is traceable to the parent feature. |  | Engineering
141 | E05 | Level Generator & Difficulty | F05.1 | Level Configuration Model | Feature | Association/group/Tableau/Stock/slot/move-limit configuration | MVP-P0 | High | CONFIRMED | Game Designer/Engineer | 8 | 48 | 0 | Not Started |  | E05 | Feature behavior matches the approved specification and has test evidence. |  | Game Design/Engineering
142 | E05 | Level Generator & Difficulty | F05.1.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Level Configuration Model. | MVP-P0 | High | CONFIRMED | Game Designer/Engineer | 3 | 18 | 0 | Not Started |  | F05.1 | Done when implementation/validation is traceable to the parent feature. |  | Game Design/Engineering
143 | E05 | Level Generator & Difficulty | F05.1.T2 | Implementation | Task | Implement Level Configuration Model with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Game Designer/Engineer | 4 | 24 | 0 | Not Started |  | F05.1 | Done when implementation/validation is traceable to the parent feature. |  | Game Design/Engineering
144 | E05 | Level Generator & Difficulty | F05.1.T3 | Validation & QA | Task | Add automated/manual validation for Level Configuration Model; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F05.1 | Done when implementation/validation is traceable to the parent feature. |  | Game Design/Engineering
145 | E05 | Level Generator & Difficulty | F05.2 | Content Selection | Feature | Select approved associations/variants within semantic/reuse constraints | MVP-P0 | High | PROPOSED | Game Engineer | 13 | 78 | 0 | Not Started |  | E05 | Feature behavior matches the approved specification and has test evidence. |  | Game Design/Engineering
146 | E05 | Level Generator & Difficulty | F05.2.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Content Selection. | MVP-P0 | High | PROPOSED | Game Engineer | 5 | 30 | 0 | Not Started |  | F05.2 | Done when implementation/validation is traceable to the parent feature. |  | Game Design/Engineering
147 | E05 | Level Generator & Difficulty | F05.2.T2 | Implementation | Task | Implement Content Selection with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED | Game Engineer | 7 | 42 | 0 | Not Started |  | F05.2 | Done when implementation/validation is traceable to the parent feature. |  | Game Design/Engineering
148 | E05 | Level Generator & Difficulty | F05.2.T3 | Validation & QA | Task | Add automated/manual validation for Content Selection; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED | QA Engineer | 5 | 30 | 0 | Not Started |  | F05.2 | Done when implementation/validation is traceable to the parent feature. |  | Game Design/Engineering
149 | E05 | Level Generator & Difficulty | F05.3 | Attempt Randomization | Feature | Full shuffle across Tableau and Stock | MVP-P0 | High | CONFIRMED | Game Engineer | 8 | 48 | 0 | Not Started |  | E05 | Feature behavior matches the approved specification and has test evidence. |  | Game Design/Engineering
150 | E05 | Level Generator & Difficulty | F05.3.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Attempt Randomization. | MVP-P0 | High | CONFIRMED | Game Engineer | 3 | 18 | 0 | Not Started |  | F05.3 | Done when implementation/validation is traceable to the parent feature. |  | Game Design/Engineering
151 | E05 | Level Generator & Difficulty | F05.3.T2 | Implementation | Task | Implement Attempt Randomization with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Game Engineer | 4 | 24 | 0 | Not Started |  | F05.3 | Done when implementation/validation is traceable to the parent feature. |  | Game Design/Engineering
152 | E05 | Level Generator & Difficulty | F05.3.T3 | Validation & QA | Task | Add automated/manual validation for Attempt Randomization; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F05.3 | Done when implementation/validation is traceable to the parent feature. |  | Game Design/Engineering
153 | E05 | Level Generator & Difficulty | F05.4 | Initial Deal | Feature | Exactly one face-up card per Tableau column | MVP-P0 | High | CONFIRMED | Game Engineer | 8 | 48 | 0 | Not Started |  | E05 | Feature behavior matches the approved specification and has test evidence. |  | Game Design/Engineering
154 | E05 | Level Generator & Difficulty | F05.4.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Initial Deal. | MVP-P0 | High | CONFIRMED | Game Engineer | 3 | 18 | 0 | Not Started |  | F05.4 | Done when implementation/validation is traceable to the parent feature. |  | Game Design/Engineering
155 | E05 | Level Generator & Difficulty | F05.4.T2 | Implementation | Task | Implement Initial Deal with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Game Engineer | 4 | 24 | 0 | Not Started |  | F05.4 | Done when implementation/validation is traceable to the parent feature. |  | Game Design/Engineering
156 | E05 | Level Generator & Difficulty | F05.4.T3 | Validation & QA | Task | Add automated/manual validation for Initial Deal; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F05.4 | Done when implementation/validation is traceable to the parent feature. |  | Game Design/Engineering
157 | E05 | Level Generator & Difficulty | F05.5 | Solver Acceptance Loop | Feature | Generate → solve → difficulty check → accept/reject | MVP-P0 | High | CONFIRMED | Game Engineer | 13 | 78 | 0 | Not Started |  | E05 | Feature behavior matches the approved specification and has test evidence. |  | Game Design/Engineering
158 | E05 | Level Generator & Difficulty | F05.5.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Solver Acceptance Loop. | MVP-P0 | High | CONFIRMED | Game Engineer | 5 | 30 | 0 | Not Started |  | F05.5 | Done when implementation/validation is traceable to the parent feature. |  | Game Design/Engineering
159 | E05 | Level Generator & Difficulty | F05.5.T2 | Implementation | Task | Implement Solver Acceptance Loop with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Game Engineer | 7 | 42 | 0 | Not Started |  | F05.5 | Done when implementation/validation is traceable to the parent feature. |  | Game Design/Engineering
160 | E05 | Level Generator & Difficulty | F05.5.T3 | Validation & QA | Task | Add automated/manual validation for Solver Acceptance Loop; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 5 | 30 | 0 | Not Started |  | F05.5 | Done when implementation/validation is traceable to the parent feature. |  | Game Design/Engineering
161 | E05 | Level Generator & Difficulty | F05.6 | Board Difficulty Metrics | Feature | Move Slack, slot pressure, Stock/Restore and pacing metrics | MVP-P0 | High | PROPOSED | Game Engineer | 13 | 78 | 0 | Not Started |  | E05 | Feature behavior matches the approved specification and has test evidence. |  | Game Design/Engineering
162 | E05 | Level Generator & Difficulty | F05.6.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Board Difficulty Metrics. | MVP-P0 | High | PROPOSED | Game Engineer | 5 | 30 | 0 | Not Started |  | F05.6 | Done when implementation/validation is traceable to the parent feature. |  | Game Design/Engineering
163 | E05 | Level Generator & Difficulty | F05.6.T2 | Implementation | Task | Implement Board Difficulty Metrics with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED | Game Engineer | 7 | 42 | 0 | Not Started |  | F05.6 | Done when implementation/validation is traceable to the parent feature. |  | Game Design/Engineering
164 | E05 | Level Generator & Difficulty | F05.6.T3 | Validation & QA | Task | Add automated/manual validation for Board Difficulty Metrics; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED | QA Engineer | 5 | 30 | 0 | Not Started |  | F05.6 | Done when implementation/validation is traceable to the parent feature. |  | Game Design/Engineering
165 | E05 | Level Generator & Difficulty | F05.7 | Semantic Difficulty Binding | Feature | Consume editorial semantic metadata | MVP-P0 | High | CONFIRMED/PROPOSED | Game Engineer | 5 | 30 | 0 | Not Started |  | E05 | Feature behavior matches the approved specification and has test evidence. |  | Game Design/Engineering
166 | E05 | Level Generator & Difficulty | F05.7.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Semantic Difficulty Binding. | MVP-P0 | High | CONFIRMED/PROPOSED | Game Engineer | 2 | 12 | 0 | Not Started |  | F05.7 | Done when implementation/validation is traceable to the parent feature. |  | Game Design/Engineering
167 | E05 | Level Generator & Difficulty | F05.7.T2 | Implementation | Task | Implement Semantic Difficulty Binding with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED/PROPOSED | Game Engineer | 3 | 18 | 0 | Not Started |  | F05.7 | Done when implementation/validation is traceable to the parent feature. |  | Game Design/Engineering
168 | E05 | Level Generator & Difficulty | F05.7.T3 | Validation & QA | Task | Add automated/manual validation for Semantic Difficulty Binding; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED/PROPOSED | QA Engineer | 2 | 12 | 0 | Not Started |  | F05.7 | Done when implementation/validation is traceable to the parent feature. |  | Game Design/Engineering
169 | E05 | Level Generator & Difficulty | F05.8 | Difficulty Acceptance Window | Feature | Reject boards outside target band | MVP-P0 | High | CONFIRMED CONCEPT | Game Engineer | 8 | 48 | 0 | Not Started |  | E05 | Feature behavior matches the approved specification and has test evidence. |  | Game Design/Engineering
170 | E05 | Level Generator & Difficulty | F05.8.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Difficulty Acceptance Window. | MVP-P0 | High | CONFIRMED CONCEPT | Game Engineer | 3 | 18 | 0 | Not Started |  | F05.8 | Done when implementation/validation is traceable to the parent feature. |  | Game Design/Engineering
171 | E05 | Level Generator & Difficulty | F05.8.T2 | Implementation | Task | Implement Difficulty Acceptance Window with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED CONCEPT | Game Engineer | 4 | 24 | 0 | Not Started |  | F05.8 | Done when implementation/validation is traceable to the parent feature. |  | Game Design/Engineering
172 | E05 | Level Generator & Difficulty | F05.8.T3 | Validation & QA | Task | Add automated/manual validation for Difficulty Acceptance Window; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED CONCEPT | QA Engineer | 3 | 18 | 0 | Not Started |  | F05.8 | Done when implementation/validation is traceable to the parent feature. |  | Game Design/Engineering
173 | E05 | Level Generator & Difficulty | F05.9 | Simulation Harness | Feature | Batch generate, solve, replay and export metrics | MVP-P0 | High | CONFIRMED | QA/Solver Engineer | 13 | 78 | 0 | Not Started |  | E05 | Feature behavior matches the approved specification and has test evidence. |  | Game Design/Engineering
174 | E05 | Level Generator & Difficulty | F05.9.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Simulation Harness. | MVP-P0 | High | CONFIRMED | QA/Solver Engineer | 5 | 30 | 0 | Not Started |  | F05.9 | Done when implementation/validation is traceable to the parent feature. |  | Game Design/Engineering
175 | E05 | Level Generator & Difficulty | F05.9.T2 | Implementation | Task | Implement Simulation Harness with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | QA/Solver Engineer | 7 | 42 | 0 | Not Started |  | F05.9 | Done when implementation/validation is traceable to the parent feature. |  | Game Design/Engineering
176 | E05 | Level Generator & Difficulty | F05.9.T3 | Validation & QA | Task | Add automated/manual validation for Simulation Harness; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 5 | 30 | 0 | Not Started |  | F05.9 | Done when implementation/validation is traceable to the parent feature. |  | Game Design/Engineering
177 | E05 | Level Generator & Difficulty | F05.10 | Generation Fallback | Feature | Approved fallback after excessive retries/timeouts | MVP-P0 | High | TBD | Game Engineer | 8 | 48 | 0 | Not Started |  | E05 | Feature behavior matches the approved specification and has test evidence. |  | Game Design/Engineering
178 | E05 | Level Generator & Difficulty | F05.10.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Generation Fallback. | MVP-P0 | High | TBD | Game Engineer | 3 | 18 | 0 | Not Started |  | F05.10 | Done when implementation/validation is traceable to the parent feature. |  | Game Design/Engineering
179 | E05 | Level Generator & Difficulty | F05.10.T2 | Implementation | Task | Implement Generation Fallback with versioned/configurable behavior where required. | MVP-P0 | High | TBD | Game Engineer | 4 | 24 | 0 | Not Started |  | F05.10 | Done when implementation/validation is traceable to the parent feature. |  | Game Design/Engineering
180 | E05 | Level Generator & Difficulty | F05.10.T3 | Validation & QA | Task | Add automated/manual validation for Generation Fallback; cover error, retry and regression cases. | MVP-P0 | High | TBD | QA Engineer | 3 | 18 | 0 | Not Started |  | F05.10 | Done when implementation/validation is traceable to the parent feature. |  | Game Design/Engineering
181 | E06 | Tutorial & Onboarding | F06.1 | First-Time Onboarding | Feature | Concise intro and player entry flow | MVP-P0 | High | CONFIRMED | Product Engineer | 5 | 30 | 0 | Not Started |  | E06 | Feature behavior matches the approved specification and has test evidence. |  | Product/UX
182 | E06 | Tutorial & Onboarding | F06.1.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for First-Time Onboarding. | MVP-P0 | High | CONFIRMED | Product Engineer | 2 | 12 | 0 | Not Started |  | F06.1 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
183 | E06 | Tutorial & Onboarding | F06.1.T2 | Implementation | Task | Implement First-Time Onboarding with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Product Engineer | 3 | 18 | 0 | Not Started |  | F06.1 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
184 | E06 | Tutorial & Onboarding | F06.1.T3 | Validation & QA | Task | Add automated/manual validation for First-Time Onboarding; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 2 | 12 | 0 | Not Started |  | F06.1 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
185 | E06 | Tutorial & Onboarding | F06.2 | Tutorial Controller | Feature | Script/constrain tutorial actions around core rules | MVP-P0 | High | PROPOSED | Game Engineer | 8 | 48 | 0 | Not Started |  | E06 | Feature behavior matches the approved specification and has test evidence. |  | Product/UX
186 | E06 | Tutorial & Onboarding | F06.2.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Tutorial Controller. | MVP-P0 | High | PROPOSED | Game Engineer | 3 | 18 | 0 | Not Started |  | F06.2 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
187 | E06 | Tutorial & Onboarding | F06.2.T2 | Implementation | Task | Implement Tutorial Controller with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED | Game Engineer | 4 | 24 | 0 | Not Started |  | F06.2 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
188 | E06 | Tutorial & Onboarding | F06.2.T3 | Validation & QA | Task | Add automated/manual validation for Tutorial Controller; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED | QA Engineer | 3 | 18 | 0 | Not Started |  | F06.2 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
189 | E06 | Tutorial & Onboarding | F06.3 | Tutorial Core Mechanics | Feature | Teach associations, matching, stacking and atomic stacks | MVP-P0 | High | CONFIRMED | Game Designer | 8 | 48 | 0 | Not Started |  | E06 | Feature behavior matches the approved specification and has test evidence. |  | Product/UX
190 | E06 | Tutorial & Onboarding | F06.3.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Tutorial Core Mechanics. | MVP-P0 | High | CONFIRMED | Game Designer | 3 | 18 | 0 | Not Started |  | F06.3 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
191 | E06 | Tutorial & Onboarding | F06.3.T2 | Implementation | Task | Implement Tutorial Core Mechanics with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Game Designer | 4 | 24 | 0 | Not Started |  | F06.3 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
192 | E06 | Tutorial & Onboarding | F06.3.T3 | Validation & QA | Task | Add automated/manual validation for Tutorial Core Mechanics; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F06.3 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
193 | E06 | Tutorial & Onboarding | F06.4 | Tutorial Association Activation | Feature | Teach Association Card → stack → Slot | MVP-P0 | High | CONFIRMED | Game Designer | 8 | 48 | 0 | Not Started |  | E06 | Feature behavior matches the approved specification and has test evidence. |  | Product/UX
194 | E06 | Tutorial & Onboarding | F06.4.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Tutorial Association Activation. | MVP-P0 | High | CONFIRMED | Game Designer | 3 | 18 | 0 | Not Started |  | F06.4 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
195 | E06 | Tutorial & Onboarding | F06.4.T2 | Implementation | Task | Implement Tutorial Association Activation with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Game Designer | 4 | 24 | 0 | Not Started |  | F06.4 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
196 | E06 | Tutorial & Onboarding | F06.4.T3 | Validation & QA | Task | Add automated/manual validation for Tutorial Association Activation; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F06.4 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
197 | E06 | Tutorial & Onboarding | F06.5 | Tutorial Stock & Moves | Feature | Teach Stock, Restore and Move Limit | MVP-P0 | High | CONFIRMED | Game Designer | 8 | 48 | 0 | Not Started |  | E06 | Feature behavior matches the approved specification and has test evidence. |  | Product/UX
198 | E06 | Tutorial & Onboarding | F06.5.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Tutorial Stock & Moves. | MVP-P0 | High | CONFIRMED | Game Designer | 3 | 18 | 0 | Not Started |  | F06.5 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
199 | E06 | Tutorial & Onboarding | F06.5.T2 | Implementation | Task | Implement Tutorial Stock & Moves with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Game Designer | 4 | 24 | 0 | Not Started |  | F06.5 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
200 | E06 | Tutorial & Onboarding | F06.5.T3 | Validation & QA | Task | Add automated/manual validation for Tutorial Stock & Moves; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F06.5 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
201 | E06 | Tutorial & Onboarding | F06.6 | Tutorial Undo/Hint/Streak | Feature | Teach assistance and streak reward | MVP-P0 | High | CONFIRMED | Game Designer | 8 | 48 | 0 | Not Started |  | E06 | Feature behavior matches the approved specification and has test evidence. |  | Product/UX
202 | E06 | Tutorial & Onboarding | F06.6.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Tutorial Undo/Hint/Streak. | MVP-P0 | High | CONFIRMED | Game Designer | 3 | 18 | 0 | Not Started |  | F06.6 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
203 | E06 | Tutorial & Onboarding | F06.6.T2 | Implementation | Task | Implement Tutorial Undo/Hint/Streak with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Game Designer | 4 | 24 | 0 | Not Started |  | F06.6 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
204 | E06 | Tutorial & Onboarding | F06.6.T3 | Validation & QA | Task | Add automated/manual validation for Tutorial Undo/Hint/Streak; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F06.6 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
205 | E06 | Tutorial & Onboarding | F06.7 | Tutorial Analytics | Feature | Track step completion/drop-off | MVP-P0 | High | PROPOSED | Analytics Engineer | 5 | 30 | 0 | Not Started |  | E06 | Feature behavior matches the approved specification and has test evidence. |  | Product/UX
206 | E06 | Tutorial & Onboarding | F06.7.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Tutorial Analytics. | MVP-P0 | High | PROPOSED | Analytics Engineer | 2 | 12 | 0 | Not Started |  | F06.7 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
207 | E06 | Tutorial & Onboarding | F06.7.T2 | Implementation | Task | Implement Tutorial Analytics with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED | Analytics Engineer | 3 | 18 | 0 | Not Started |  | F06.7 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
208 | E06 | Tutorial & Onboarding | F06.7.T3 | Validation & QA | Task | Add automated/manual validation for Tutorial Analytics; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED | QA Engineer | 2 | 12 | 0 | Not Started |  | F06.7 | Done when implementation/validation is traceable to the parent feature. |  | Product/UX
209 | E07 | Main Journey & Chapters | F07.1 | Journey State | Feature | Current level, highest complete and chapter state | MVP-P0 | High | CONFIRMED | Product Engineer | 8 | 48 | 0 | Not Started |  | E07 | Feature behavior matches the approved specification and has test evidence. |  | Product/Game Design
210 | E07 | Main Journey & Chapters | F07.1.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Journey State. | MVP-P0 | High | CONFIRMED | Product Engineer | 3 | 18 | 0 | Not Started |  | F07.1 | Done when implementation/validation is traceable to the parent feature. |  | Product/Game Design
211 | E07 | Main Journey & Chapters | F07.1.T2 | Implementation | Task | Implement Journey State with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Product Engineer | 4 | 24 | 0 | Not Started |  | F07.1 | Done when implementation/validation is traceable to the parent feature. |  | Product/Game Design
212 | E07 | Main Journey & Chapters | F07.1.T3 | Validation & QA | Task | Add automated/manual validation for Journey State; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F07.1 | Done when implementation/validation is traceable to the parent feature. |  | Product/Game Design
213 | E07 | Main Journey & Chapters | F07.2 | Chapter Model | Feature | Standard 50-level chapter structure | MVP-P0 | High | CONFIRMED | Product Engineer | 5 | 30 | 0 | Not Started |  | E07 | Feature behavior matches the approved specification and has test evidence. |  | Product/Game Design
214 | E07 | Main Journey & Chapters | F07.2.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Chapter Model. | MVP-P0 | High | CONFIRMED | Product Engineer | 2 | 12 | 0 | Not Started |  | F07.2 | Done when implementation/validation is traceable to the parent feature. |  | Product/Game Design
215 | E07 | Main Journey & Chapters | F07.2.T2 | Implementation | Task | Implement Chapter Model with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Product Engineer | 3 | 18 | 0 | Not Started |  | F07.2 | Done when implementation/validation is traceable to the parent feature. |  | Product/Game Design
216 | E07 | Main Journey & Chapters | F07.2.T3 | Validation & QA | Task | Add automated/manual validation for Chapter Model; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 2 | 12 | 0 | Not Started |  | F07.2 | Done when implementation/validation is traceable to the parent feature. |  | Product/Game Design
217 | E07 | Main Journey & Chapters | F07.3 | Level Start Flow | Feature | Load config/content, generate Attempt and enter gameplay | MVP-P0 | High | CONFIRMED | Product Engineer | 8 | 48 | 0 | Not Started |  | E07 | Feature behavior matches the approved specification and has test evidence. |  | Product/Game Design
218 | E07 | Main Journey & Chapters | F07.3.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Level Start Flow. | MVP-P0 | High | CONFIRMED | Product Engineer | 3 | 18 | 0 | Not Started |  | F07.3 | Done when implementation/validation is traceable to the parent feature. |  | Product/Game Design
219 | E07 | Main Journey & Chapters | F07.3.T2 | Implementation | Task | Implement Level Start Flow with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Product Engineer | 4 | 24 | 0 | Not Started |  | F07.3 | Done when implementation/validation is traceable to the parent feature. |  | Product/Game Design
220 | E07 | Main Journey & Chapters | F07.3.T3 | Validation & QA | Task | Add automated/manual validation for Level Start Flow; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F07.3 | Done when implementation/validation is traceable to the parent feature. |  | Product/Game Design
221 | E07 | Main Journey & Chapters | F07.4 | Level Completion Flow | Feature | Reward, persist completion and unlock next level | MVP-P0 | High | CONFIRMED | Product Engineer | 8 | 48 | 0 | Not Started |  | E07 | Feature behavior matches the approved specification and has test evidence. |  | Product/Game Design
222 | E07 | Main Journey & Chapters | F07.4.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Level Completion Flow. | MVP-P0 | High | CONFIRMED | Product Engineer | 3 | 18 | 0 | Not Started |  | F07.4 | Done when implementation/validation is traceable to the parent feature. |  | Product/Game Design
223 | E07 | Main Journey & Chapters | F07.4.T2 | Implementation | Task | Implement Level Completion Flow with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Product Engineer | 4 | 24 | 0 | Not Started |  | F07.4 | Done when implementation/validation is traceable to the parent feature. |  | Product/Game Design
224 | E07 | Main Journey & Chapters | F07.4.T3 | Validation & QA | Task | Add automated/manual validation for Level Completion Flow; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F07.4 | Done when implementation/validation is traceable to the parent feature. |  | Product/Game Design
225 | E07 | Main Journey & Chapters | F07.5 | Restart Flow | Feature | New shuffle with same level content/config | MVP-P0 | High | CONFIRMED | Product Engineer | 8 | 48 | 0 | Not Started |  | E07 | Feature behavior matches the approved specification and has test evidence. |  | Product/Game Design
226 | E07 | Main Journey & Chapters | F07.5.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Restart Flow. | MVP-P0 | High | CONFIRMED | Product Engineer | 3 | 18 | 0 | Not Started |  | F07.5 | Done when implementation/validation is traceable to the parent feature. |  | Product/Game Design
227 | E07 | Main Journey & Chapters | F07.5.T2 | Implementation | Task | Implement Restart Flow with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Product Engineer | 4 | 24 | 0 | Not Started |  | F07.5 | Done when implementation/validation is traceable to the parent feature. |  | Product/Game Design
228 | E07 | Main Journey & Chapters | F07.5.T3 | Validation & QA | Task | Add automated/manual validation for Restart Flow; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F07.5 | Done when implementation/validation is traceable to the parent feature. |  | Product/Game Design
229 | E07 | Main Journey & Chapters | F07.6 | Difficulty Wave Configuration | Feature | Represent chapter-level B/S target sequence | MVP-P0 | High | CONFIRMED CONCEPT | Game Designer | 8 | 48 | 0 | Not Started |  | E07 | Feature behavior matches the approved specification and has test evidence. |  | Product/Game Design
230 | E07 | Main Journey & Chapters | F07.6.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Difficulty Wave Configuration. | MVP-P0 | High | CONFIRMED CONCEPT | Game Designer | 3 | 18 | 0 | Not Started |  | F07.6 | Done when implementation/validation is traceable to the parent feature. |  | Product/Game Design
231 | E07 | Main Journey & Chapters | F07.6.T2 | Implementation | Task | Implement Difficulty Wave Configuration with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED CONCEPT | Game Designer | 4 | 24 | 0 | Not Started |  | F07.6 | Done when implementation/validation is traceable to the parent feature. |  | Product/Game Design
232 | E07 | Main Journey & Chapters | F07.6.T3 | Validation & QA | Task | Add automated/manual validation for Difficulty Wave Configuration; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED CONCEPT | QA Engineer | 3 | 18 | 0 | Not Started |  | F07.6 | Done when implementation/validation is traceable to the parent feature. |  | Product/Game Design
233 | E07 | Main Journey & Chapters | F07.7 | Journey UI | Feature | Home Continue, chapter/level progress and level entry | MVP-P0 | High | PROPOSED UX | UI Engineer | 13 | 78 | 0 | Not Started |  | E07 | Feature behavior matches the approved specification and has test evidence. |  | Product/Game Design
234 | E07 | Main Journey & Chapters | F07.7.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Journey UI. | MVP-P0 | High | PROPOSED UX | UI Engineer | 5 | 30 | 0 | Not Started |  | F07.7 | Done when implementation/validation is traceable to the parent feature. |  | Product/Game Design
235 | E07 | Main Journey & Chapters | F07.7.T2 | Implementation | Task | Implement Journey UI with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED UX | UI Engineer | 7 | 42 | 0 | Not Started |  | F07.7 | Done when implementation/validation is traceable to the parent feature. |  | Product/Game Design
236 | E07 | Main Journey & Chapters | F07.7.T3 | Validation & QA | Task | Add automated/manual validation for Journey UI; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED UX | QA Engineer | 5 | 30 | 0 | Not Started |  | F07.7 | Done when implementation/validation is traceable to the parent feature. |  | Product/Game Design
237 | E08 | Economy & Rewards | F08.1 | Wallet Domain | Feature | Coin balance and safe grant/spend abstraction | MVP-P0 | High | CONFIRMED | Backend Engineer | 8 | 48 | 0 | Not Started |  | E08 | Feature behavior matches the approved specification and has test evidence. |  | Product/Backend
238 | E08 | Economy & Rewards | F08.1.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Wallet Domain. | MVP-P0 | High | CONFIRMED | Backend Engineer | 3 | 18 | 0 | Not Started |  | F08.1 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
239 | E08 | Economy & Rewards | F08.1.T2 | Implementation | Task | Implement Wallet Domain with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Backend Engineer | 4 | 24 | 0 | Not Started |  | F08.1 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
240 | E08 | Economy & Rewards | F08.1.T3 | Validation & QA | Task | Add automated/manual validation for Wallet Domain; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F08.1 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
241 | E08 | Economy & Rewards | F08.2 | Level Reward Calculation | Feature | 50 + 2×remaining Moves + streak reward | MVP-P0 | High | CONFIRMED | Game/Backend Engineer | 5 | 30 | 0 | Not Started |  | E08 | Feature behavior matches the approved specification and has test evidence. |  | Product/Backend
242 | E08 | Economy & Rewards | F08.2.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Level Reward Calculation. | MVP-P0 | High | CONFIRMED | Game/Backend Engineer | 2 | 12 | 0 | Not Started |  | F08.2 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
243 | E08 | Economy & Rewards | F08.2.T2 | Implementation | Task | Implement Level Reward Calculation with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Game/Backend Engineer | 3 | 18 | 0 | Not Started |  | F08.2 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
244 | E08 | Economy & Rewards | F08.2.T3 | Validation & QA | Task | Add automated/manual validation for Level Reward Calculation; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 2 | 12 | 0 | Not Started |  | F08.2 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
245 | E08 | Economy & Rewards | F08.3 | Hint Balance | Feature | Persist and spend Hint resource | MVP-P0 | High | CONFIRMED | Backend Engineer | 5 | 30 | 0 | Not Started |  | E08 | Feature behavior matches the approved specification and has test evidence. |  | Product/Backend
246 | E08 | Economy & Rewards | F08.3.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Hint Balance. | MVP-P0 | High | CONFIRMED | Backend Engineer | 2 | 12 | 0 | Not Started |  | F08.3 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
247 | E08 | Economy & Rewards | F08.3.T2 | Implementation | Task | Implement Hint Balance with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Backend Engineer | 3 | 18 | 0 | Not Started |  | F08.3 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
248 | E08 | Economy & Rewards | F08.3.T3 | Validation & QA | Task | Add automated/manual validation for Hint Balance; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 2 | 12 | 0 | Not Started |  | F08.3 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
249 | E08 | Economy & Rewards | F08.4 | Reward Grant Idempotency | Feature | Prevent duplicate grants | MVP-P0 | High | PROPOSED ARCH | Backend Engineer | 8 | 48 | 0 | Not Started |  | E08 | Feature behavior matches the approved specification and has test evidence. |  | Product/Backend
250 | E08 | Economy & Rewards | F08.4.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Reward Grant Idempotency. | MVP-P0 | High | PROPOSED ARCH | Backend Engineer | 3 | 18 | 0 | Not Started |  | F08.4 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
251 | E08 | Economy & Rewards | F08.4.T2 | Implementation | Task | Implement Reward Grant Idempotency with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED ARCH | Backend Engineer | 4 | 24 | 0 | Not Started |  | F08.4 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
252 | E08 | Economy & Rewards | F08.4.T3 | Validation & QA | Task | Add automated/manual validation for Reward Grant Idempotency; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED ARCH | QA Engineer | 3 | 18 | 0 | Not Started |  | F08.4 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
253 | E08 | Economy & Rewards | F08.5 | Economy Config | Feature | Versioned configurable utility prices/grants | MVP-P0 | High | PROPOSED | Backend Engineer | 8 | 48 | 0 | Not Started |  | E08 | Feature behavior matches the approved specification and has test evidence. |  | Product/Backend
254 | E08 | Economy & Rewards | F08.5.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Economy Config. | MVP-P0 | High | PROPOSED | Backend Engineer | 3 | 18 | 0 | Not Started |  | F08.5 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
255 | E08 | Economy & Rewards | F08.5.T2 | Implementation | Task | Implement Economy Config with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED | Backend Engineer | 4 | 24 | 0 | Not Started |  | F08.5 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
256 | E08 | Economy & Rewards | F08.5.T3 | Validation & QA | Task | Add automated/manual validation for Economy Config; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED | QA Engineer | 3 | 18 | 0 | Not Started |  | F08.5 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
257 | E08 | Economy & Rewards | F08.6 | Economy Analytics | Feature | Sources, sinks, balances and utility usage | MVP-P0 | High | CONFIRMED | Analytics Engineer | 5 | 30 | 0 | Not Started |  | E08 | Feature behavior matches the approved specification and has test evidence. |  | Product/Backend
258 | E08 | Economy & Rewards | F08.6.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Economy Analytics. | MVP-P0 | High | CONFIRMED | Analytics Engineer | 2 | 12 | 0 | Not Started |  | F08.6 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
259 | E08 | Economy & Rewards | F08.6.T2 | Implementation | Task | Implement Economy Analytics with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Analytics Engineer | 3 | 18 | 0 | Not Started |  | F08.6 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
260 | E08 | Economy & Rewards | F08.6.T3 | Validation & QA | Task | Add automated/manual validation for Economy Analytics; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 2 | 12 | 0 | Not Started |  | F08.6 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
261 | E09 | Gameplay Assistance & Recovery | F09.1 | Hint Request Flow | Feature | Check resource, invoke Solver and show Hint | MVP-P0 | High | CONFIRMED | Product Engineer | 8 | 48 | 0 | Not Started |  | E09 | Feature behavior matches the approved specification and has test evidence. |  | Engineering/Product
262 | E09 | Gameplay Assistance & Recovery | F09.1.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Hint Request Flow. | MVP-P0 | High | CONFIRMED | Product Engineer | 3 | 18 | 0 | Not Started |  | F09.1 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
263 | E09 | Gameplay Assistance & Recovery | F09.1.T2 | Implementation | Task | Implement Hint Request Flow with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Product Engineer | 4 | 24 | 0 | Not Started |  | F09.1 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
264 | E09 | Gameplay Assistance & Recovery | F09.1.T3 | Validation & QA | Task | Add automated/manual validation for Hint Request Flow; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F09.1 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
265 | E09 | Gameplay Assistance & Recovery | F09.2 | Hint Acquisition | Feature | Coins or Rewarded Ad when balance insufficient | MVP-P0 | High | CONFIRMED | Product Engineer | 8 | 48 | 0 | Not Started |  | E09 | Feature behavior matches the approved specification and has test evidence. |  | Engineering/Product
266 | E09 | Gameplay Assistance & Recovery | F09.2.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Hint Acquisition. | MVP-P0 | High | CONFIRMED | Product Engineer | 3 | 18 | 0 | Not Started |  | F09.2 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
267 | E09 | Gameplay Assistance & Recovery | F09.2.T2 | Implementation | Task | Implement Hint Acquisition with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Product Engineer | 4 | 24 | 0 | Not Started |  | F09.2 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
268 | E09 | Gameplay Assistance & Recovery | F09.2.T3 | Validation & QA | Task | Add automated/manual validation for Hint Acquisition; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F09.2 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
269 | E09 | Gameplay Assistance & Recovery | F09.3 | Out-of-Moves Overlay | Feature | Stop gameplay and present choices | MVP-P0 | High | CONFIRMED | UI Engineer | 5 | 30 | 0 | Not Started |  | E09 | Feature behavior matches the approved specification and has test evidence. |  | Engineering/Product
270 | E09 | Gameplay Assistance & Recovery | F09.3.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Out-of-Moves Overlay. | MVP-P0 | High | CONFIRMED | UI Engineer | 2 | 12 | 0 | Not Started |  | F09.3 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
271 | E09 | Gameplay Assistance & Recovery | F09.3.T2 | Implementation | Task | Implement Out-of-Moves Overlay with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | UI Engineer | 3 | 18 | 0 | Not Started |  | F09.3 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
272 | E09 | Gameplay Assistance & Recovery | F09.3.T3 | Validation & QA | Task | Add automated/manual validation for Out-of-Moves Overlay; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 2 | 12 | 0 | Not Started |  | F09.3 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
273 | E09 | Gameplay Assistance & Recovery | F09.4 | Extra Moves Grant | Feature | Apply validated extra Moves and resume same board | MVP-P0 | High | CONFIRMED | Game Engineer | 5 | 30 | 0 | Not Started |  | E09 | Feature behavior matches the approved specification and has test evidence. |  | Engineering/Product
274 | E09 | Gameplay Assistance & Recovery | F09.4.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Extra Moves Grant. | MVP-P0 | High | CONFIRMED | Game Engineer | 2 | 12 | 0 | Not Started |  | F09.4 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
275 | E09 | Gameplay Assistance & Recovery | F09.4.T2 | Implementation | Task | Implement Extra Moves Grant with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Game Engineer | 3 | 18 | 0 | Not Started |  | F09.4 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
276 | E09 | Gameplay Assistance & Recovery | F09.4.T3 | Validation & QA | Task | Add automated/manual validation for Extra Moves Grant; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 2 | 12 | 0 | Not Started |  | F09.4 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
277 | E09 | Gameplay Assistance & Recovery | F09.5 | Dead-End Overlay | Feature | Undo/rescue/restart alternatives | MVP-P0 | High | CONFIRMED | UI Engineer | 5 | 30 | 0 | Not Started |  | E09 | Feature behavior matches the approved specification and has test evidence. |  | Engineering/Product
278 | E09 | Gameplay Assistance & Recovery | F09.5.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Dead-End Overlay. | MVP-P0 | High | CONFIRMED | UI Engineer | 2 | 12 | 0 | Not Started |  | F09.5 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
279 | E09 | Gameplay Assistance & Recovery | F09.5.T2 | Implementation | Task | Implement Dead-End Overlay with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | UI Engineer | 3 | 18 | 0 | Not Started |  | F09.5 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
280 | E09 | Gameplay Assistance & Recovery | F09.5.T3 | Validation & QA | Task | Add automated/manual validation for Dead-End Overlay; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 2 | 12 | 0 | Not Started |  | F09.5 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
281 | E09 | Gameplay Assistance & Recovery | F09.6 | Rescue Integration Contract | Feature | Apply Solver-validated rescue transformation | MVP-P0 | High | TBD BEHAVIOR | Game Engineer | 8 | 48 | 0 | Not Started |  | E09 | Feature behavior matches the approved specification and has test evidence. |  | Engineering/Product
282 | E09 | Gameplay Assistance & Recovery | F09.6.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Rescue Integration Contract. | MVP-P0 | High | TBD BEHAVIOR | Game Engineer | 3 | 18 | 0 | Not Started |  | F09.6 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
283 | E09 | Gameplay Assistance & Recovery | F09.6.T2 | Implementation | Task | Implement Rescue Integration Contract with versioned/configurable behavior where required. | MVP-P0 | High | TBD BEHAVIOR | Game Engineer | 4 | 24 | 0 | Not Started |  | F09.6 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
284 | E09 | Gameplay Assistance & Recovery | F09.6.T3 | Validation & QA | Task | Add automated/manual validation for Rescue Integration Contract; cover error, retry and regression cases. | MVP-P0 | High | TBD BEHAVIOR | QA Engineer | 3 | 18 | 0 | Not Started |  | F09.6 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
285 | E09 | Gameplay Assistance & Recovery | F09.7 | Technical Failure Refund | Feature | Refund failed Hint/utility technical grants | MVP-P0 | High | PROPOSED | Backend Engineer | 5 | 30 | 0 | Not Started |  | E09 | Feature behavior matches the approved specification and has test evidence. |  | Engineering/Product
286 | E09 | Gameplay Assistance & Recovery | F09.7.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Technical Failure Refund. | MVP-P0 | High | PROPOSED | Backend Engineer | 2 | 12 | 0 | Not Started |  | F09.7 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
287 | E09 | Gameplay Assistance & Recovery | F09.7.T2 | Implementation | Task | Implement Technical Failure Refund with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED | Backend Engineer | 3 | 18 | 0 | Not Started |  | F09.7 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
288 | E09 | Gameplay Assistance & Recovery | F09.7.T3 | Validation & QA | Task | Add automated/manual validation for Technical Failure Refund; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED | QA Engineer | 2 | 12 | 0 | Not Started |  | F09.7 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
289 | E10 | Monetization | F10.1 | Ads Adapter | Feature | Provider-neutral rewarded/interstitial interfaces | MVP-P0 | High | CONFIRMED/PROPOSED ARCH | Mobile Engineer | 8 | 48 | 0 | Not Started |  | E10 | Feature behavior matches the approved specification and has test evidence. |  | Product/Backend
290 | E10 | Monetization | F10.1.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Ads Adapter. | MVP-P0 | High | CONFIRMED/PROPOSED ARCH | Mobile Engineer | 3 | 18 | 0 | Not Started |  | F10.1 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
291 | E10 | Monetization | F10.1.T2 | Implementation | Task | Implement Ads Adapter with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED/PROPOSED ARCH | Mobile Engineer | 4 | 24 | 0 | Not Started |  | F10.1 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
292 | E10 | Monetization | F10.1.T3 | Validation & QA | Task | Add automated/manual validation for Ads Adapter; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED/PROPOSED ARCH | QA Engineer | 3 | 18 | 0 | Not Started |  | F10.1 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
293 | E10 | Monetization | F10.2 | Rewarded Hint Ad | Feature | Ad completion → Hint grant | MVP-P0 | High | CONFIRMED | Mobile/Backend Engineer | 5 | 30 | 0 | Not Started |  | E10 | Feature behavior matches the approved specification and has test evidence. |  | Product/Backend
294 | E10 | Monetization | F10.2.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Rewarded Hint Ad. | MVP-P0 | High | CONFIRMED | Mobile/Backend Engineer | 2 | 12 | 0 | Not Started |  | F10.2 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
295 | E10 | Monetization | F10.2.T2 | Implementation | Task | Implement Rewarded Hint Ad with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Mobile/Backend Engineer | 3 | 18 | 0 | Not Started |  | F10.2 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
296 | E10 | Monetization | F10.2.T3 | Validation & QA | Task | Add automated/manual validation for Rewarded Hint Ad; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 2 | 12 | 0 | Not Started |  | F10.2 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
297 | E10 | Monetization | F10.3 | Rewarded Extra Moves Ad | Feature | Ad completion → Extra Moves | MVP-P0 | High | CONFIRMED | Mobile/Backend Engineer | 5 | 30 | 0 | Not Started |  | E10 | Feature behavior matches the approved specification and has test evidence. |  | Product/Backend
298 | E10 | Monetization | F10.3.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Rewarded Extra Moves Ad. | MVP-P0 | High | CONFIRMED | Mobile/Backend Engineer | 2 | 12 | 0 | Not Started |  | F10.3 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
299 | E10 | Monetization | F10.3.T2 | Implementation | Task | Implement Rewarded Extra Moves Ad with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Mobile/Backend Engineer | 3 | 18 | 0 | Not Started |  | F10.3 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
300 | E10 | Monetization | F10.3.T3 | Validation & QA | Task | Add automated/manual validation for Rewarded Extra Moves Ad; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 2 | 12 | 0 | Not Started |  | F10.3 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
301 | E10 | Monetization | F10.4 | Rewarded Rescue Ad | Feature | Ad completion → Rescue authorization | MVP-P0 | High | CONFIRMED | Mobile/Backend Engineer | 5 | 30 | 0 | Not Started |  | E10 | Feature behavior matches the approved specification and has test evidence. |  | Product/Backend
302 | E10 | Monetization | F10.4.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Rewarded Rescue Ad. | MVP-P0 | High | CONFIRMED | Mobile/Backend Engineer | 2 | 12 | 0 | Not Started |  | F10.4 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
303 | E10 | Monetization | F10.4.T2 | Implementation | Task | Implement Rewarded Rescue Ad with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Mobile/Backend Engineer | 3 | 18 | 0 | Not Started |  | F10.4 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
304 | E10 | Monetization | F10.4.T3 | Validation & QA | Task | Add automated/manual validation for Rewarded Rescue Ad; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 2 | 12 | 0 | Not Started |  | F10.4 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
305 | E10 | Monetization | F10.5 | Rewarded Coins Ad | Feature | Optional ad → Coin grant with cap/config | MVP-P0 | High | CONFIRMED | Mobile/Backend Engineer | 5 | 30 | 0 | Not Started |  | E10 | Feature behavior matches the approved specification and has test evidence. |  | Product/Backend
306 | E10 | Monetization | F10.5.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Rewarded Coins Ad. | MVP-P0 | High | CONFIRMED | Mobile/Backend Engineer | 2 | 12 | 0 | Not Started |  | F10.5 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
307 | E10 | Monetization | F10.5.T2 | Implementation | Task | Implement Rewarded Coins Ad with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Mobile/Backend Engineer | 3 | 18 | 0 | Not Started |  | F10.5 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
308 | E10 | Monetization | F10.5.T3 | Validation & QA | Task | Add automated/manual validation for Rewarded Coins Ad; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 2 | 12 | 0 | Not Started |  | F10.5 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
309 | E10 | Monetization | F10.6 | Adaptive Interstitial Eligibility | Feature | Natural breaks, cooldown/cap and entitlement checks | MVP-P0 | High | CONFIRMED CONCEPT | Product Engineer | 8 | 48 | 0 | Not Started |  | E10 | Feature behavior matches the approved specification and has test evidence. |  | Product/Backend
310 | E10 | Monetization | F10.6.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Adaptive Interstitial Eligibility. | MVP-P0 | High | CONFIRMED CONCEPT | Product Engineer | 3 | 18 | 0 | Not Started |  | F10.6 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
311 | E10 | Monetization | F10.6.T2 | Implementation | Task | Implement Adaptive Interstitial Eligibility with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED CONCEPT | Product Engineer | 4 | 24 | 0 | Not Started |  | F10.6 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
312 | E10 | Monetization | F10.6.T3 | Validation & QA | Task | Add automated/manual validation for Adaptive Interstitial Eligibility; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED CONCEPT | QA Engineer | 3 | 18 | 0 | Not Started |  | F10.6 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
313 | E10 | Monetization | F10.7 | IAP Catalog | Feature | Remove Ads and Coin Pack metadata | MVP-P0 | High | CONFIRMED | Backend/Mobile Engineer | 5 | 30 | 0 | Not Started |  | E10 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: Remove Ads=interstitials only; IAP via Functions/Run; real-money prices TBD; no Mid-Level Reshuffle. | Product/Backend
314 | E10 | Monetization | F10.7.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for IAP Catalog. | MVP-P0 | High | CONFIRMED | Backend/Mobile Engineer | 2 | 12 | 0 | Not Started |  | F10.7 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
315 | E10 | Monetization | F10.7.T2 | Implementation | Task | Implement IAP Catalog with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Backend/Mobile Engineer | 3 | 18 | 0 | Not Started |  | F10.7 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
316 | E10 | Monetization | F10.7.T3 | Validation & QA | Task | Add automated/manual validation for IAP Catalog; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 2 | 12 | 0 | Not Started |  | F10.7 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
317 | E10 | Monetization | F10.8 | Purchase Flow | Feature | Native store purchase, pending/error and grant | MVP-P0 | High | CONFIRMED | Mobile Engineer | 8 | 48 | 0 | Not Started |  | E10 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: Remove Ads=interstitials only; IAP via Functions/Run; real-money prices TBD; no Mid-Level Reshuffle. | Product/Backend
318 | E10 | Monetization | F10.8.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Purchase Flow. | MVP-P0 | High | CONFIRMED | Mobile Engineer | 3 | 18 | 0 | Not Started |  | F10.8 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
319 | E10 | Monetization | F10.8.T2 | Implementation | Task | Implement Purchase Flow with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Mobile Engineer | 4 | 24 | 0 | Not Started |  | F10.8 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
320 | E10 | Monetization | F10.8.T3 | Validation & QA | Task | Add automated/manual validation for Purchase Flow; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F10.8 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
321 | E10 | Monetization | F10.9 | Server Purchase Validation | Feature | Idempotent store validation and grant | MVP-P0 | High | PROPOSED ARCH | Backend Engineer | 13 | 78 | 0 | Not Started |  | E10 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: Remove Ads=interstitials only; IAP via Functions/Run; real-money prices TBD; no Mid-Level Reshuffle. | Product/Backend
322 | E10 | Monetization | F10.9.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Server Purchase Validation. | MVP-P0 | High | PROPOSED ARCH | Backend Engineer | 5 | 30 | 0 | Not Started |  | F10.9 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
323 | E10 | Monetization | F10.9.T2 | Implementation | Task | Implement Server Purchase Validation with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED ARCH | Backend Engineer | 7 | 42 | 0 | Not Started |  | F10.9 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
324 | E10 | Monetization | F10.9.T3 | Validation & QA | Task | Add automated/manual validation for Server Purchase Validation; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED ARCH | QA Engineer | 5 | 30 | 0 | Not Started |  | F10.9 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
325 | E10 | Monetization | F10.10 | Restore Purchases | Feature | Restore Remove Ads entitlement | MVP-P0 | High | CONFIRMED | Mobile/Backend Engineer | 5 | 30 | 0 | Not Started |  | E10 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: Remove Ads=interstitials only; IAP via Functions/Run; real-money prices TBD; no Mid-Level Reshuffle. | Product/Backend
326 | E10 | Monetization | F10.10.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Restore Purchases. | MVP-P0 | High | CONFIRMED | Mobile/Backend Engineer | 2 | 12 | 0 | Not Started |  | F10.10 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
327 | E10 | Monetization | F10.10.T2 | Implementation | Task | Implement Restore Purchases with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Mobile/Backend Engineer | 3 | 18 | 0 | Not Started |  | F10.10 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
328 | E10 | Monetization | F10.10.T3 | Validation & QA | Task | Add automated/manual validation for Restore Purchases; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 2 | 12 | 0 | Not Started |  | F10.10 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
329 | E10 | Monetization | F10.11 | Shop UI | Feature | Remove Ads + simple Coin Pack catalog | MVP-P0 | High | CONFIRMED SCOPE | UI Engineer | 8 | 48 | 0 | Not Started |  | E10 | Feature behavior matches the approved specification and has test evidence. |  | Product/Backend
330 | E10 | Monetization | F10.11.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Shop UI. | MVP-P0 | High | CONFIRMED SCOPE | UI Engineer | 3 | 18 | 0 | Not Started |  | F10.11 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
331 | E10 | Monetization | F10.11.T2 | Implementation | Task | Implement Shop UI with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED SCOPE | UI Engineer | 4 | 24 | 0 | Not Started |  | F10.11 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
332 | E10 | Monetization | F10.11.T3 | Validation & QA | Task | Add automated/manual validation for Shop UI; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED SCOPE | QA Engineer | 3 | 18 | 0 | Not Started |  | F10.11 | Done when implementation/validation is traceable to the parent feature. |  | Product/Backend
333 | E11 | Identity, Account & Cloud Save | F11.1 | Anonymous Identity | Feature | Persistent Firebase Authentication anonymous-first player identity | MVP-P0 | High | CONFIRMED | Backend/Mobile Engineer | 8 | 48 | 0 | Not Started |  | E11 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: Firebase Auth. | Backend
334 | E11 | Identity, Account & Cloud Save | F11.1.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Anonymous Identity. | MVP-P0 | High | CONFIRMED | Backend/Mobile Engineer | 3 | 18 | 0 | Not Started |  | F11.1 | Done when implementation/validation is traceable to the parent feature. |  | Backend
335 | E11 | Identity, Account & Cloud Save | F11.1.T2 | Implementation | Task | Implement Anonymous Identity with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Backend/Mobile Engineer | 4 | 24 | 0 | Not Started |  | F11.1 | Done when implementation/validation is traceable to the parent feature. |  | Backend
336 | E11 | Identity, Account & Cloud Save | F11.1.T3 | Validation & QA | Task | Add automated/manual validation for Anonymous Identity; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F11.1 | Done when implementation/validation is traceable to the parent feature. |  | Backend
337 | E11 | Identity, Account & Cloud Save | F11.2 | Cloud Player Profile | Feature | Persist progression/economy-linked profile | MVP-P0 | High | CONFIRMED | Backend Engineer | 8 | 48 | 0 | Not Started |  | E11 | Feature behavior matches the approved specification and has test evidence. |  | Backend
338 | E11 | Identity, Account & Cloud Save | F11.2.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Cloud Player Profile. | MVP-P0 | High | CONFIRMED | Backend Engineer | 3 | 18 | 0 | Not Started |  | F11.2 | Done when implementation/validation is traceable to the parent feature. |  | Backend
339 | E11 | Identity, Account & Cloud Save | F11.2.T2 | Implementation | Task | Implement Cloud Player Profile with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Backend Engineer | 4 | 24 | 0 | Not Started |  | F11.2 | Done when implementation/validation is traceable to the parent feature. |  | Backend
340 | E11 | Identity, Account & Cloud Save | F11.2.T3 | Validation & QA | Task | Add automated/manual validation for Cloud Player Profile; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F11.2 | Done when implementation/validation is traceable to the parent feature. |  | Backend
341 | E11 | Identity, Account & Cloud Save | F11.3 | Apple Linking | Feature | Optional Sign in with Apple | MVP-P0 | High | CONFIRMED | Mobile/Backend Engineer | 8 | 48 | 0 | Not Started |  | E11 | Feature behavior matches the approved specification and has test evidence. |  | Backend
342 | E11 | Identity, Account & Cloud Save | F11.3.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Apple Linking. | MVP-P0 | High | CONFIRMED | Mobile/Backend Engineer | 3 | 18 | 0 | Not Started |  | F11.3 | Done when implementation/validation is traceable to the parent feature. |  | Backend
343 | E11 | Identity, Account & Cloud Save | F11.3.T2 | Implementation | Task | Implement Apple Linking with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Mobile/Backend Engineer | 4 | 24 | 0 | Not Started |  | F11.3 | Done when implementation/validation is traceable to the parent feature. |  | Backend
344 | E11 | Identity, Account & Cloud Save | F11.3.T3 | Validation & QA | Task | Add automated/manual validation for Apple Linking; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F11.3 | Done when implementation/validation is traceable to the parent feature. |  | Backend
345 | E11 | Identity, Account & Cloud Save | F11.4 | Google Linking | Feature | Optional Google link flow | MVP-P0 | High | CONFIRMED | Mobile/Backend Engineer | 8 | 48 | 0 | Not Started |  | E11 | Feature behavior matches the approved specification and has test evidence. |  | Backend
346 | E11 | Identity, Account & Cloud Save | F11.4.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Google Linking. | MVP-P0 | High | CONFIRMED | Mobile/Backend Engineer | 3 | 18 | 0 | Not Started |  | F11.4 | Done when implementation/validation is traceable to the parent feature. |  | Backend
347 | E11 | Identity, Account & Cloud Save | F11.4.T2 | Implementation | Task | Implement Google Linking with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Mobile/Backend Engineer | 4 | 24 | 0 | Not Started |  | F11.4 | Done when implementation/validation is traceable to the parent feature. |  | Backend
348 | E11 | Identity, Account & Cloud Save | F11.4.T3 | Validation & QA | Task | Add automated/manual validation for Google Linking; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F11.4 | Done when implementation/validation is traceable to the parent feature. |  | Backend
349 | E11 | Identity, Account & Cloud Save | F11.5 | Cloud Sync Revision | Feature | Revision-based synchronization | MVP-P0 | High | PROPOSED | Backend Engineer | 8 | 48 | 0 | Not Started |  | E11 | Feature behavior matches the approved specification and has test evidence. |  | Backend
350 | E11 | Identity, Account & Cloud Save | F11.5.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Cloud Sync Revision. | MVP-P0 | High | PROPOSED | Backend Engineer | 3 | 18 | 0 | Not Started |  | F11.5 | Done when implementation/validation is traceable to the parent feature. |  | Backend
351 | E11 | Identity, Account & Cloud Save | F11.5.T2 | Implementation | Task | Implement Cloud Sync Revision with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED | Backend Engineer | 4 | 24 | 0 | Not Started |  | F11.5 | Done when implementation/validation is traceable to the parent feature. |  | Backend
352 | E11 | Identity, Account & Cloud Save | F11.5.T3 | Validation & QA | Task | Add automated/manual validation for Cloud Sync Revision; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED | QA Engineer | 3 | 18 | 0 | Not Started |  | F11.5 | Done when implementation/validation is traceable to the parent feature. |  | Backend
353 | E11 | Identity, Account & Cloud Save | F11.6 | Progression Reconciliation | Feature | Idempotent completion/progression sync | MVP-P0 | High | PROPOSED | Backend Engineer | 8 | 48 | 0 | Not Started |  | E11 | Feature behavior matches the approved specification and has test evidence. |  | Backend
354 | E11 | Identity, Account & Cloud Save | F11.6.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Progression Reconciliation. | MVP-P0 | High | PROPOSED | Backend Engineer | 3 | 18 | 0 | Not Started |  | F11.6 | Done when implementation/validation is traceable to the parent feature. |  | Backend
355 | E11 | Identity, Account & Cloud Save | F11.6.T2 | Implementation | Task | Implement Progression Reconciliation with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED | Backend Engineer | 4 | 24 | 0 | Not Started |  | F11.6 | Done when implementation/validation is traceable to the parent feature. |  | Backend
356 | E11 | Identity, Account & Cloud Save | F11.6.T3 | Validation & QA | Task | Add automated/manual validation for Progression Reconciliation; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED | QA Engineer | 3 | 18 | 0 | Not Started |  | F11.6 | Done when implementation/validation is traceable to the parent feature. |  | Backend
357 | E11 | Identity, Account & Cloud Save | F11.7 | Cloud Conflict UX | Feature | Handle local/cloud conflict safely | MVP-P0 | High | TBD | Product Engineer | 8 | 48 | 0 | Not Started |  | E11 | Feature behavior matches the approved specification and has test evidence. |  | Backend
358 | E11 | Identity, Account & Cloud Save | F11.7.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Cloud Conflict UX. | MVP-P0 | High | TBD | Product Engineer | 3 | 18 | 0 | Not Started |  | F11.7 | Done when implementation/validation is traceable to the parent feature. |  | Backend
359 | E11 | Identity, Account & Cloud Save | F11.7.T2 | Implementation | Task | Implement Cloud Conflict UX with versioned/configurable behavior where required. | MVP-P0 | High | TBD | Product Engineer | 4 | 24 | 0 | Not Started |  | F11.7 | Done when implementation/validation is traceable to the parent feature. |  | Backend
360 | E11 | Identity, Account & Cloud Save | F11.7.T3 | Validation & QA | Task | Add automated/manual validation for Cloud Conflict UX; cover error, retry and regression cases. | MVP-P0 | High | TBD | QA Engineer | 3 | 18 | 0 | Not Started |  | F11.7 | Done when implementation/validation is traceable to the parent feature. |  | Backend
361 | E11 | Identity, Account & Cloud Save | F11.8 | Local Active Attempt Resume | Feature | Persist/resume current board | MVP-P0 | High | PROPOSED | Mobile Engineer | 8 | 48 | 0 | Not Started |  | E11 | Feature behavior matches the approved specification and has test evidence. |  | Backend
362 | E11 | Identity, Account & Cloud Save | F11.8.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Local Active Attempt Resume. | MVP-P0 | High | PROPOSED | Mobile Engineer | 3 | 18 | 0 | Not Started |  | F11.8 | Done when implementation/validation is traceable to the parent feature. |  | Backend
363 | E11 | Identity, Account & Cloud Save | F11.8.T2 | Implementation | Task | Implement Local Active Attempt Resume with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED | Mobile Engineer | 4 | 24 | 0 | Not Started |  | F11.8 | Done when implementation/validation is traceable to the parent feature. |  | Backend
364 | E11 | Identity, Account & Cloud Save | F11.8.T3 | Validation & QA | Task | Add automated/manual validation for Local Active Attempt Resume; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED | QA Engineer | 3 | 18 | 0 | Not Started |  | F11.8 | Done when implementation/validation is traceable to the parent feature. |  | Backend
365 | E12 | Backend Platform (Firebase) | F12.1 | Firebase Backend Foundation | Feature | Firebase project, environments (DEV/TEST/STAGING/PROD), Auth wiring, security rules baseline, Functions/Run scaffolding | MVP-P0 | High | CONFIRMED | Backend Engineer | 13 | 78 | 0 | Not Started |  | E12 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: Firebase-first. Azure/ASP.NET/PG always-on infra out of MVP (scope reduction). | Backend/Cloud
366 | E12 | Backend Platform (Firebase) | F12.1.T1 | Analysis & Design | Task | Finalize Firebase-first contracts/edge cases for Firebase Backend Foundation. | MVP-P0 | High | CONFIRMED | Backend Engineer | 5 | 30 | 0 | Not Started |  | F12.1 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Firebase-first. Azure/ASP.NET/PG always-on infra out of MVP (scope reduction). | Backend/Cloud
367 | E12 | Backend Platform (Firebase) | F12.1.T2 | Implementation | Task | Implement Firebase Backend Foundation on Firebase/GCP (no always-on Azure/ASP.NET/PG host). | MVP-P0 | High | CONFIRMED | Backend Engineer | 7 | 42 | 0 | Not Started |  | F12.1 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Firebase-first. Azure/ASP.NET/PG always-on infra out of MVP (scope reduction). | Backend/Cloud
368 | E12 | Backend Platform (Firebase) | F12.1.T3 | Validation & QA | Task | Validate Firebase Backend Foundation; cover auth, idempotency, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 5 | 30 | 0 | Not Started |  | F12.1 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Firebase-first. Azure/ASP.NET/PG always-on infra out of MVP (scope reduction). | Backend/Cloud
369 | E12 | Backend Platform (Firebase) | F12.2 | Firestore Player Profile & Progression | Feature | Cloud Firestore documents for profile/progression/sync metadata with minimized read/write patterns | MVP-P0 | High | CONFIRMED | Backend Engineer | 8 | 48 | 0 | Not Started |  | E12 | Feature behavior matches the approved specification and has test evidence. | Replace always-on API host assumptions with Firestore + security rules / Functions. | Backend/Cloud
370 | E12 | Backend Platform (Firebase) | F12.2.T1 | Analysis & Design | Task | Finalize Firebase-first contracts/edge cases for Firestore Player Profile & Progression. | MVP-P0 | High | CONFIRMED | Backend Engineer | 3 | 18 | 0 | Not Started |  | F12.2 | Done when implementation/validation is traceable to the parent feature. | Replace always-on API host assumptions with Firestore + security rules / Functions. | Backend/Cloud
371 | E12 | Backend Platform (Firebase) | F12.2.T2 | Implementation | Task | Implement Firestore Player Profile & Progression on Firebase/GCP (no always-on Azure/ASP.NET/PG host). | MVP-P0 | High | CONFIRMED | Backend Engineer | 4 | 24 | 0 | Not Started |  | F12.2 | Done when implementation/validation is traceable to the parent feature. | Replace always-on API host assumptions with Firestore + security rules / Functions. | Backend/Cloud
372 | E12 | Backend Platform (Firebase) | F12.2.T3 | Validation & QA | Task | Validate Firestore Player Profile & Progression; cover auth, idempotency, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F12.2 | Done when implementation/validation is traceable to the parent feature. | Replace always-on API host assumptions with Firestore + security rules / Functions. | Backend/Cloud
373 | E12 | Backend Platform (Firebase) | F12.3 | Cloud Functions Economy Mutations | Feature | Server-authoritative Wallet/economy mutations via Cloud Functions and/or Cloud Run | MVP-P0 | High | CONFIRMED | Backend Engineer | 13 | 78 | 0 | Not Started |  | E12 | Feature behavior matches the approved specification and has test evidence. | Trusted backend path; no client-trusted wallet writes. | Backend/Cloud
374 | E12 | Backend Platform (Firebase) | F12.3.T1 | Analysis & Design | Task | Finalize Firebase-first contracts/edge cases for Cloud Functions Economy Mutations. | MVP-P0 | High | CONFIRMED | Backend Engineer | 5 | 30 | 0 | Not Started |  | F12.3 | Done when implementation/validation is traceable to the parent feature. | Trusted backend path; no client-trusted wallet writes. | Backend/Cloud
375 | E12 | Backend Platform (Firebase) | F12.3.T2 | Implementation | Task | Implement Cloud Functions Economy Mutations on Firebase/GCP (no always-on Azure/ASP.NET/PG host). | MVP-P0 | High | CONFIRMED | Backend Engineer | 7 | 42 | 0 | Not Started |  | F12.3 | Done when implementation/validation is traceable to the parent feature. | Trusted backend path; no client-trusted wallet writes. | Backend/Cloud
376 | E12 | Backend Platform (Firebase) | F12.3.T3 | Validation & QA | Task | Validate Cloud Functions Economy Mutations; cover auth, idempotency, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 5 | 30 | 0 | Not Started |  | F12.3 | Done when implementation/validation is traceable to the parent feature. | Trusted backend path; no client-trusted wallet writes. | Backend/Cloud
377 | E12 | Backend Platform (Firebase) | F12.4 | IAP Validation (Functions/Run) | Feature | Server-side IAP validation and purchase grants via Cloud Functions / Cloud Run | MVP-P0 | High | CONFIRMED | Backend Engineer | 13 | 78 | 0 | Not Started |  | E12 | Feature behavior matches the approved specification and has test evidence. | Flutter in_app_purchase client; store + trusted backend authority. | Backend/Cloud
378 | E12 | Backend Platform (Firebase) | F12.4.T1 | Analysis & Design | Task | Finalize Firebase-first contracts/edge cases for IAP Validation (Functions/Run). | MVP-P0 | High | CONFIRMED | Backend Engineer | 5 | 30 | 0 | Not Started |  | F12.4 | Done when implementation/validation is traceable to the parent feature. | Flutter in_app_purchase client; store + trusted backend authority. | Backend/Cloud
379 | E12 | Backend Platform (Firebase) | F12.4.T2 | Implementation | Task | Implement IAP Validation (Functions/Run) on Firebase/GCP (no always-on Azure/ASP.NET/PG host). | MVP-P0 | High | CONFIRMED | Backend Engineer | 7 | 42 | 0 | Not Started |  | F12.4 | Done when implementation/validation is traceable to the parent feature. | Flutter in_app_purchase client; store + trusted backend authority. | Backend/Cloud
380 | E12 | Backend Platform (Firebase) | F12.4.T3 | Validation & QA | Task | Validate IAP Validation (Functions/Run); cover auth, idempotency, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 5 | 30 | 0 | Not Started |  | F12.4 | Done when implementation/validation is traceable to the parent feature. | Flutter in_app_purchase client; store + trusted backend authority. | Backend/Cloud
381 | E12 | Backend Platform (Firebase) | F12.5 | Content Manifest + Remote Config | Feature | Versioned content manifest delivery; Firebase Remote Config for client-facing tunables | MVP-P0 | High | CONFIRMED | Backend Engineer | 8 | 48 | 0 | Not Started |  | E12 | Feature behavior matches the approved specification and has test evidence. | Authoritative sensitive config remains server-controlled where required. | Backend/Cloud
382 | E12 | Backend Platform (Firebase) | F12.5.T1 | Analysis & Design | Task | Finalize Firebase-first contracts/edge cases for Content Manifest + Remote Config. | MVP-P0 | High | CONFIRMED | Backend Engineer | 3 | 18 | 0 | Not Started |  | F12.5 | Done when implementation/validation is traceable to the parent feature. | Authoritative sensitive config remains server-controlled where required. | Backend/Cloud
383 | E12 | Backend Platform (Firebase) | F12.5.T2 | Implementation | Task | Implement Content Manifest + Remote Config on Firebase/GCP (no always-on Azure/ASP.NET/PG host). | MVP-P0 | High | CONFIRMED | Backend Engineer | 4 | 24 | 0 | Not Started |  | F12.5 | Done when implementation/validation is traceable to the parent feature. | Authoritative sensitive config remains server-controlled where required. | Backend/Cloud
384 | E12 | Backend Platform (Firebase) | F12.5.T3 | Validation & QA | Task | Validate Content Manifest + Remote Config; cover auth, idempotency, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F12.5 | Done when implementation/validation is traceable to the parent feature. | Authoritative sensitive config remains server-controlled where required. | Backend/Cloud
385 | E12 | Backend Platform (Firebase) | F12.6 | Firebase Storage Content Assets | Feature | Remote content bundles and illustration assets via Firebase Storage (no paid CDN required for MVP) | MVP-P0 | High | CONFIRMED | Backend Engineer | 5 | 30 | 0 | Not Started |  | E12 | Feature behavior matches the approved specification and has test evidence. | Azure Blob / Front Door superseded for MVP. | Backend/Cloud
386 | E12 | Backend Platform (Firebase) | F12.6.T1 | Analysis & Design | Task | Finalize Firebase-first contracts/edge cases for Firebase Storage Content Assets. | MVP-P0 | High | CONFIRMED | Backend Engineer | 2 | 12 | 0 | Not Started |  | F12.6 | Done when implementation/validation is traceable to the parent feature. | Azure Blob / Front Door superseded for MVP. | Backend/Cloud
387 | E12 | Backend Platform (Firebase) | F12.6.T2 | Implementation | Task | Implement Firebase Storage Content Assets on Firebase/GCP (no always-on Azure/ASP.NET/PG host). | MVP-P0 | High | CONFIRMED | Backend Engineer | 3 | 18 | 0 | Not Started |  | F12.6 | Done when implementation/validation is traceable to the parent feature. | Azure Blob / Front Door superseded for MVP. | Backend/Cloud
388 | E12 | Backend Platform (Firebase) | F12.6.T3 | Validation & QA | Task | Validate Firebase Storage Content Assets; cover auth, idempotency, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 2 | 12 | 0 | Not Started |  | F12.6 | Done when implementation/validation is traceable to the parent feature. | Azure Blob / Front Door superseded for MVP. | Backend/Cloud
389 | E12 | Backend Platform (Firebase) | F12.7 | Serverless Jobs (Functions/Run) | Feature | Scheduled/triggered Cloud Functions or Cloud Run jobs for purchase reconciliation, bundle build hooks, Daily ops | MVP-P0 | High | CONFIRMED | Backend Engineer | 8 | 48 | 0 | Not Started |  | E12 | Feature behavior matches the approved specification and has test evidence. | No dedicated Message Broker / always-on worker host in MVP. | Backend/Cloud
390 | E12 | Backend Platform (Firebase) | F12.7.T1 | Analysis & Design | Task | Finalize Firebase-first contracts/edge cases for Serverless Jobs (Functions/Run). | MVP-P0 | High | CONFIRMED | Backend Engineer | 3 | 18 | 0 | Not Started |  | F12.7 | Done when implementation/validation is traceable to the parent feature. | No dedicated Message Broker / always-on worker host in MVP. | Backend/Cloud
391 | E12 | Backend Platform (Firebase) | F12.7.T2 | Implementation | Task | Implement Serverless Jobs (Functions/Run) on Firebase/GCP (no always-on Azure/ASP.NET/PG host). | MVP-P0 | High | CONFIRMED | Backend Engineer | 4 | 24 | 0 | Not Started |  | F12.7 | Done when implementation/validation is traceable to the parent feature. | No dedicated Message Broker / always-on worker host in MVP. | Backend/Cloud
392 | E12 | Backend Platform (Firebase) | F12.7.T3 | Validation & QA | Task | Validate Serverless Jobs (Functions/Run); cover auth, idempotency, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F12.7 | Done when implementation/validation is traceable to the parent feature. | No dedicated Message Broker / always-on worker host in MVP. | Backend/Cloud
393 | E12 | Backend Platform (Firebase) | F12.8 | Idempotent Grant Infrastructure | Feature | Idempotency keys for Wallet grants, Daily claims, IAP, rewarded grants | MVP-P0 | High | CONFIRMED | Backend Engineer | 8 | 48 | 0 | Not Started |  | E12 | Feature behavior matches the approved specification and has test evidence. | Firestore/Functions transaction patterns; Redis not in MVP. | Backend/Cloud
394 | E12 | Backend Platform (Firebase) | F12.8.T1 | Analysis & Design | Task | Finalize Firebase-first contracts/edge cases for Idempotent Grant Infrastructure. | MVP-P0 | High | CONFIRMED | Backend Engineer | 3 | 18 | 0 | Not Started |  | F12.8 | Done when implementation/validation is traceable to the parent feature. | Firestore/Functions transaction patterns; Redis not in MVP. | Backend/Cloud
395 | E12 | Backend Platform (Firebase) | F12.8.T2 | Implementation | Task | Implement Idempotent Grant Infrastructure on Firebase/GCP (no always-on Azure/ASP.NET/PG host). | MVP-P0 | High | CONFIRMED | Backend Engineer | 4 | 24 | 0 | Not Started |  | F12.8 | Done when implementation/validation is traceable to the parent feature. | Firestore/Functions transaction patterns; Redis not in MVP. | Backend/Cloud
396 | E12 | Backend Platform (Firebase) | F12.8.T3 | Validation & QA | Task | Validate Idempotent Grant Infrastructure; cover auth, idempotency, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F12.8 | Done when implementation/validation is traceable to the parent feature. | Firestore/Functions transaction patterns; Redis not in MVP. | Backend/Cloud
397 | E12 | Backend Platform (Firebase) | F12.9 | GCP Native Observability | Feature | Structured logs/monitoring for Cloud Functions / Cloud Run; health checks; correlation IDs | MVP-P0 | High | CONFIRMED | Backend Engineer | 5 | 30 | 0 | Not Started |  | E12 | Feature behavior matches the approved specification and has test evidence. | Azure Application Insights superseded for MVP. | Backend/Cloud
398 | E12 | Backend Platform (Firebase) | F12.9.T1 | Analysis & Design | Task | Finalize Firebase-first contracts/edge cases for GCP Native Observability. | MVP-P0 | High | CONFIRMED | Backend Engineer | 2 | 12 | 0 | Not Started |  | F12.9 | Done when implementation/validation is traceable to the parent feature. | Azure Application Insights superseded for MVP. | Backend/Cloud
399 | E12 | Backend Platform (Firebase) | F12.9.T2 | Implementation | Task | Implement GCP Native Observability on Firebase/GCP (no always-on Azure/ASP.NET/PG host). | MVP-P0 | High | CONFIRMED | Backend Engineer | 3 | 18 | 0 | Not Started |  | F12.9 | Done when implementation/validation is traceable to the parent feature. | Azure Application Insights superseded for MVP. | Backend/Cloud
400 | E12 | Backend Platform (Firebase) | F12.9.T3 | Validation & QA | Task | Validate GCP Native Observability; cover auth, idempotency, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 2 | 12 | 0 | Not Started |  | F12.9 | Done when implementation/validation is traceable to the parent feature. | Azure Application Insights superseded for MVP. | Backend/Cloud
401 | E13 | Admin / CMS | F13.1 | Admin Auth (Entra ID) + RBAC | Feature | Angular CMS auth via Microsoft Entra ID + MFA; roles/permissions; Firebase/GCP access via security boundaries | MVP-P0 | High | CONFIRMED | Backend/Admin Engineer | 8 | 48 | 0 | Not Started |  | E13 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: Angular + Entra; audit 2y; ASP.NET+PG deferred. | Admin/Content
402 | E13 | Admin / CMS | F13.1.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Admin Authentication/RBAC. | MVP-P0 | High | CONFIRMED | Backend/Admin Engineer | 3 | 18 | 0 | Not Started |  | F13.1 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Angular + Entra ID + MFA. | Admin/Content
403 | E13 | Admin / CMS | F13.1.T2 | Implementation | Task | Implement Admin Authentication/RBAC with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Backend/Admin Engineer | 4 | 24 | 0 | Not Started |  | F13.1 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Angular + Entra ID + MFA. | Admin/Content
404 | E13 | Admin / CMS | F13.1.T3 | Validation & QA | Task | Add automated/manual validation for Admin Authentication/RBAC; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F13.1 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Angular + Entra ID + MFA. | Admin/Content
405 | E13 | Admin / CMS | F13.2 | Content CRUD | Feature | Association/Member/Variant screens and APIs | MVP-P0 | High | CONFIRMED | Admin Engineer | 13 | 78 | 0 | Not Started |  | E13 | Feature behavior matches the approved specification and has test evidence. |  | Admin/Content
406 | E13 | Admin / CMS | F13.2.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Content CRUD. | MVP-P0 | High | CONFIRMED | Admin Engineer | 5 | 30 | 0 | Not Started |  | F13.2 | Done when implementation/validation is traceable to the parent feature. |  | Admin/Content
407 | E13 | Admin / CMS | F13.2.T2 | Implementation | Task | Implement Content CRUD with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Admin Engineer | 7 | 42 | 0 | Not Started |  | F13.2 | Done when implementation/validation is traceable to the parent feature. |  | Admin/Content
408 | E13 | Admin / CMS | F13.2.T3 | Validation & QA | Task | Add automated/manual validation for Content CRUD; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 5 | 30 | 0 | Not Started |  | F13.2 | Done when implementation/validation is traceable to the parent feature. |  | Admin/Content
409 | E13 | Admin / CMS | F13.3 | Arabic Review Workflow | Feature | Review queues, notes, statuses and history | MVP-P0 | High | PROPOSED | Admin Engineer | 8 | 48 | 0 | Not Started |  | E13 | Feature behavior matches the approved specification and has test evidence. |  | Admin/Content
410 | E13 | Admin / CMS | F13.3.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Arabic Review Workflow. | MVP-P0 | High | PROPOSED | Admin Engineer | 3 | 18 | 0 | Not Started |  | F13.3 | Done when implementation/validation is traceable to the parent feature. |  | Admin/Content
411 | E13 | Admin / CMS | F13.3.T2 | Implementation | Task | Implement Arabic Review Workflow with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED | Admin Engineer | 4 | 24 | 0 | Not Started |  | F13.3 | Done when implementation/validation is traceable to the parent feature. |  | Admin/Content
412 | E13 | Admin / CMS | F13.3.T3 | Validation & QA | Task | Add automated/manual validation for Arabic Review Workflow; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED | QA Engineer | 3 | 18 | 0 | Not Started |  | F13.3 | Done when implementation/validation is traceable to the parent feature. |  | Admin/Content
413 | E13 | Admin / CMS | F13.4 | Level Config Editor | Feature | Level/template/content-selection configuration | MVP-P0 | High | CONFIRMED | Admin Engineer | 13 | 78 | 0 | Not Started |  | E13 | Feature behavior matches the approved specification and has test evidence. |  | Admin/Content
414 | E13 | Admin / CMS | F13.4.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Level Config Editor. | MVP-P0 | High | CONFIRMED | Admin Engineer | 5 | 30 | 0 | Not Started |  | F13.4 | Done when implementation/validation is traceable to the parent feature. |  | Admin/Content
415 | E13 | Admin / CMS | F13.4.T2 | Implementation | Task | Implement Level Config Editor with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Admin Engineer | 7 | 42 | 0 | Not Started |  | F13.4 | Done when implementation/validation is traceable to the parent feature. |  | Admin/Content
416 | E13 | Admin / CMS | F13.4.T3 | Validation & QA | Task | Add automated/manual validation for Level Config Editor; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 5 | 30 | 0 | Not Started |  | F13.4 | Done when implementation/validation is traceable to the parent feature. |  | Admin/Content
417 | E13 | Admin / CMS | F13.5 | Solver Validation UI | Feature | Generate sample, solve and display metrics | MVP-P0 | High | CONFIRMED | Admin Engineer | 13 | 78 | 0 | Not Started |  | E13 | Feature behavior matches the approved specification and has test evidence. |  | Admin/Content
418 | E13 | Admin / CMS | F13.5.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Solver Validation UI. | MVP-P0 | High | CONFIRMED | Admin Engineer | 5 | 30 | 0 | Not Started |  | F13.5 | Done when implementation/validation is traceable to the parent feature. |  | Admin/Content
419 | E13 | Admin / CMS | F13.5.T2 | Implementation | Task | Implement Solver Validation UI with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Admin Engineer | 7 | 42 | 0 | Not Started |  | F13.5 | Done when implementation/validation is traceable to the parent feature. |  | Admin/Content
420 | E13 | Admin / CMS | F13.5.T3 | Validation & QA | Task | Add automated/manual validation for Solver Validation UI; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 5 | 30 | 0 | Not Started |  | F13.5 | Done when implementation/validation is traceable to the parent feature. |  | Admin/Content
421 | E13 | Admin / CMS | F13.6 | Playable Preview | Feature | Admin test-play generated board | MVP-P0 | High | PROPOSED | Admin/Game Engineer | 13 | 78 | 0 | Not Started |  | E13 | Feature behavior matches the approved specification and has test evidence. |  | Admin/Content
422 | E13 | Admin / CMS | F13.6.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Playable Preview. | MVP-P0 | High | PROPOSED | Admin/Game Engineer | 5 | 30 | 0 | Not Started |  | F13.6 | Done when implementation/validation is traceable to the parent feature. |  | Admin/Content
423 | E13 | Admin / CMS | F13.6.T2 | Implementation | Task | Implement Playable Preview with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED | Admin/Game Engineer | 7 | 42 | 0 | Not Started |  | F13.6 | Done when implementation/validation is traceable to the parent feature. |  | Admin/Content
424 | E13 | Admin / CMS | F13.6.T3 | Validation & QA | Task | Add automated/manual validation for Playable Preview; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED | QA Engineer | 5 | 30 | 0 | Not Started |  | F13.6 | Done when implementation/validation is traceable to the parent feature. |  | Admin/Content
425 | E13 | Admin / CMS | F13.7 | Content Bundle Publish | Feature | Build, validate, publish and rollback bundle | MVP-P0 | High | PROPOSED | Backend/Admin Engineer | 13 | 78 | 0 | Not Started |  | E13 | Feature behavior matches the approved specification and has test evidence. |  | Admin/Content
426 | E13 | Admin / CMS | F13.7.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Content Bundle Publish. | MVP-P0 | High | PROPOSED | Backend/Admin Engineer | 5 | 30 | 0 | Not Started |  | F13.7 | Done when implementation/validation is traceable to the parent feature. |  | Admin/Content
427 | E13 | Admin / CMS | F13.7.T2 | Implementation | Task | Implement Content Bundle Publish with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED | Backend/Admin Engineer | 7 | 42 | 0 | Not Started |  | F13.7 | Done when implementation/validation is traceable to the parent feature. |  | Admin/Content
428 | E13 | Admin / CMS | F13.7.T3 | Validation & QA | Task | Add automated/manual validation for Content Bundle Publish; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED | QA Engineer | 5 | 30 | 0 | Not Started |  | F13.7 | Done when implementation/validation is traceable to the parent feature. |  | Admin/Content
429 | E13 | Admin / CMS | F13.8 | Economy/Remote Config | Feature | Versioned safe configuration UI | MVP-P0 | High | PROPOSED | Admin Engineer | 8 | 48 | 0 | Not Started |  | E13 | Feature behavior matches the approved specification and has test evidence. |  | Admin/Content
430 | E13 | Admin / CMS | F13.8.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Economy/Remote Config. | MVP-P0 | High | PROPOSED | Admin Engineer | 3 | 18 | 0 | Not Started |  | F13.8 | Done when implementation/validation is traceable to the parent feature. |  | Admin/Content
431 | E13 | Admin / CMS | F13.8.T2 | Implementation | Task | Implement Economy/Remote Config with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED | Admin Engineer | 4 | 24 | 0 | Not Started |  | F13.8 | Done when implementation/validation is traceable to the parent feature. |  | Admin/Content
432 | E13 | Admin / CMS | F13.8.T3 | Validation & QA | Task | Add automated/manual validation for Economy/Remote Config; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED | QA Engineer | 3 | 18 | 0 | Not Started |  | F13.8 | Done when implementation/validation is traceable to the parent feature. |  | Admin/Content
433 | E13 | Admin / CMS | F13.9 | Audit Log | Feature | Audit sensitive admin actions; retain audit logs for 2 years | MVP-P0 | High | CONFIRMED | Backend Engineer | 8 | 48 | 0 | Not Started |  | E13 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: audit retention 2 years. | Admin/Content
434 | E13 | Admin / CMS | F13.9.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Audit Log. | MVP-P0 | High | CONFIRMED | Backend Engineer | 3 | 18 | 0 | Not Started |  | F13.9 | Done when implementation/validation is traceable to the parent feature. |  | Admin/Content
435 | E13 | Admin / CMS | F13.9.T2 | Implementation | Task | Implement Audit Log with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Backend Engineer | 4 | 24 | 0 | Not Started |  | F13.9 | Done when implementation/validation is traceable to the parent feature. |  | Admin/Content
436 | E13 | Admin / CMS | F13.9.T3 | Validation & QA | Task | Add automated/manual validation for Audit Log; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F13.9 | Done when implementation/validation is traceable to the parent feature. |  | Admin/Content
437 | E13 | Admin / CMS | F13.10 | Basic Player Support | Feature | Profile/wallet/purchase/sync diagnostics | MVP-P0 | High | PROPOSED MVP | Admin Engineer | 8 | 48 | 0 | Not Started |  | E13 | Feature behavior matches the approved specification and has test evidence. |  | Admin/Content
438 | E13 | Admin / CMS | F13.10.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Basic Player Support. | MVP-P0 | High | PROPOSED MVP | Admin Engineer | 3 | 18 | 0 | Not Started |  | F13.10 | Done when implementation/validation is traceable to the parent feature. |  | Admin/Content
439 | E13 | Admin / CMS | F13.10.T2 | Implementation | Task | Implement Basic Player Support with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED MVP | Admin Engineer | 4 | 24 | 0 | Not Started |  | F13.10 | Done when implementation/validation is traceable to the parent feature. |  | Admin/Content
440 | E13 | Admin / CMS | F13.10.T3 | Validation & QA | Task | Add automated/manual validation for Basic Player Support; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED MVP | QA Engineer | 3 | 18 | 0 | Not Started |  | F13.10 | Done when implementation/validation is traceable to the parent feature. |  | Admin/Content
441 | E14 | Analytics & Observability | F14.1 | Firebase Analytics Integration | Feature | Firebase Analytics + domain event mapper; BigQuery export enabled | MVP-P0 | High | CONFIRMED | Mobile Engineer | 5 | 30 | 0 | Not Started |  | E14 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: Firebase Analytics + BigQuery; Azure App Insights superseded. | Analytics/Engineering
442 | E14 | Analytics & Observability | F14.1.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Analytics Abstraction. | MVP-P0 | High | CONFIRMED | Mobile Engineer | 2 | 12 | 0 | Not Started |  | F14.1 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Firebase Analytics + BigQuery. | Analytics/Engineering
443 | E14 | Analytics & Observability | F14.1.T2 | Implementation | Task | Implement Analytics Abstraction with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Mobile Engineer | 3 | 18 | 0 | Not Started |  | F14.1 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Firebase Analytics + BigQuery. | Analytics/Engineering
444 | E14 | Analytics & Observability | F14.1.T3 | Validation & QA | Task | Add automated/manual validation for Analytics Abstraction; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 2 | 12 | 0 | Not Started |  | F14.1 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Firebase Analytics + BigQuery. | Analytics/Engineering
445 | E14 | Analytics & Observability | F14.2 | Core Funnel Events | Feature | Onboarding, tutorial and level lifecycle | MVP-P0 | High | CONFIRMED | Analytics Engineer | 8 | 48 | 0 | Not Started |  | E14 | Feature behavior matches the approved specification and has test evidence. |  | Analytics/Engineering
446 | E14 | Analytics & Observability | F14.2.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Core Funnel Events. | MVP-P0 | High | CONFIRMED | Analytics Engineer | 3 | 18 | 0 | Not Started |  | F14.2 | Done when implementation/validation is traceable to the parent feature. |  | Analytics/Engineering
447 | E14 | Analytics & Observability | F14.2.T2 | Implementation | Task | Implement Core Funnel Events with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Analytics Engineer | 4 | 24 | 0 | Not Started |  | F14.2 | Done when implementation/validation is traceable to the parent feature. |  | Analytics/Engineering
448 | E14 | Analytics & Observability | F14.2.T3 | Validation & QA | Task | Add automated/manual validation for Core Funnel Events; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F14.2 | Done when implementation/validation is traceable to the parent feature. |  | Analytics/Engineering
449 | E14 | Analytics & Observability | F14.3 | Attempt Summary | Feature | Aggregated gameplay counters per Attempt | MVP-P0 | High | PROPOSED | Analytics Engineer | 8 | 48 | 0 | Not Started |  | E14 | Feature behavior matches the approved specification and has test evidence. |  | Analytics/Engineering
450 | E14 | Analytics & Observability | F14.3.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Attempt Summary. | MVP-P0 | High | PROPOSED | Analytics Engineer | 3 | 18 | 0 | Not Started |  | F14.3 | Done when implementation/validation is traceable to the parent feature. |  | Analytics/Engineering
451 | E14 | Analytics & Observability | F14.3.T2 | Implementation | Task | Implement Attempt Summary with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED | Analytics Engineer | 4 | 24 | 0 | Not Started |  | F14.3 | Done when implementation/validation is traceable to the parent feature. |  | Analytics/Engineering
452 | E14 | Analytics & Observability | F14.3.T3 | Validation & QA | Task | Add automated/manual validation for Attempt Summary; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED | QA Engineer | 3 | 18 | 0 | Not Started |  | F14.3 | Done when implementation/validation is traceable to the parent feature. |  | Analytics/Engineering
453 | E14 | Analytics & Observability | F14.4 | Solver Metrics Telemetry | Feature | Generation, Hint and dead-end metrics | MVP-P0 | High | CONFIRMED | Analytics/Solver Engineer | 5 | 30 | 0 | Not Started |  | E14 | Feature behavior matches the approved specification and has test evidence. |  | Analytics/Engineering
454 | E14 | Analytics & Observability | F14.4.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Solver Metrics Telemetry. | MVP-P0 | High | CONFIRMED | Analytics/Solver Engineer | 2 | 12 | 0 | Not Started |  | F14.4 | Done when implementation/validation is traceable to the parent feature. |  | Analytics/Engineering
455 | E14 | Analytics & Observability | F14.4.T2 | Implementation | Task | Implement Solver Metrics Telemetry with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Analytics/Solver Engineer | 3 | 18 | 0 | Not Started |  | F14.4 | Done when implementation/validation is traceable to the parent feature. |  | Analytics/Engineering
456 | E14 | Analytics & Observability | F14.4.T3 | Validation & QA | Task | Add automated/manual validation for Solver Metrics Telemetry; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 2 | 12 | 0 | Not Started |  | F14.4 | Done when implementation/validation is traceable to the parent feature. |  | Analytics/Engineering
457 | E14 | Analytics & Observability | F14.5 | Economy/Monetization Events | Feature | Wallet, ads, IAP and utility funnels | MVP-P0 | High | CONFIRMED | Analytics Engineer | 8 | 48 | 0 | Not Started |  | E14 | Feature behavior matches the approved specification and has test evidence. |  | Analytics/Engineering
458 | E14 | Analytics & Observability | F14.5.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Economy/Monetization Events. | MVP-P0 | High | CONFIRMED | Analytics Engineer | 3 | 18 | 0 | Not Started |  | F14.5 | Done when implementation/validation is traceable to the parent feature. |  | Analytics/Engineering
459 | E14 | Analytics & Observability | F14.5.T2 | Implementation | Task | Implement Economy/Monetization Events with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Analytics Engineer | 4 | 24 | 0 | Not Started |  | F14.5 | Done when implementation/validation is traceable to the parent feature. |  | Analytics/Engineering
460 | E14 | Analytics & Observability | F14.5.T3 | Validation & QA | Task | Add automated/manual validation for Economy/Monetization Events; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F14.5 | Done when implementation/validation is traceable to the parent feature. |  | Analytics/Engineering
461 | E14 | Analytics & Observability | F14.6 | Content/Difficulty Events | Feature | Association IDs, B/S scores and quality signals | MVP-P0 | High | CONFIRMED | Analytics Engineer | 8 | 48 | 0 | Not Started |  | E14 | Feature behavior matches the approved specification and has test evidence. |  | Analytics/Engineering
462 | E14 | Analytics & Observability | F14.6.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Content/Difficulty Events. | MVP-P0 | High | CONFIRMED | Analytics Engineer | 3 | 18 | 0 | Not Started |  | F14.6 | Done when implementation/validation is traceable to the parent feature. |  | Analytics/Engineering
463 | E14 | Analytics & Observability | F14.6.T2 | Implementation | Task | Implement Content/Difficulty Events with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Analytics Engineer | 4 | 24 | 0 | Not Started |  | F14.6 | Done when implementation/validation is traceable to the parent feature. |  | Analytics/Engineering
464 | E14 | Analytics & Observability | F14.6.T3 | Validation & QA | Task | Add automated/manual validation for Content/Difficulty Events; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F14.6 | Done when implementation/validation is traceable to the parent feature. |  | Analytics/Engineering
465 | E14 | Analytics & Observability | F14.7 | Firebase Crashlytics | Feature | Crashlytics with Engine/Solver/app version context | MVP-P0 | High | CONFIRMED | Mobile Engineer | 5 | 30 | 0 | Not Started |  | E14 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: Crashlytics confirmed. | Analytics/Engineering
466 | E14 | Analytics & Observability | F14.7.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Crash Reporting. | MVP-P0 | High | CONFIRMED | Mobile Engineer | 2 | 12 | 0 | Not Started |  | F14.7 | Done when implementation/validation is traceable to the parent feature. |  | Analytics/Engineering
467 | E14 | Analytics & Observability | F14.7.T2 | Implementation | Task | Implement Crash Reporting with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Mobile Engineer | 3 | 18 | 0 | Not Started |  | F14.7 | Done when implementation/validation is traceable to the parent feature. |  | Analytics/Engineering
468 | E14 | Analytics & Observability | F14.7.T3 | Validation & QA | Task | Add automated/manual validation for Crash Reporting; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 2 | 12 | 0 | Not Started |  | F14.7 | Done when implementation/validation is traceable to the parent feature. |  | Analytics/Engineering
469 | E14 | Analytics & Observability | F14.8 | Operational Dashboards | Feature | Gameplay/solver/economy dashboards on Firebase Analytics + BigQuery; GCP-native serverless logs | MVP-P0 | High | CONFIRMED | Analyst | 8 | 48 | 0 | Not Started |  | E14 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: GCP-native observability; not Azure App Insights. | Analytics/Engineering
470 | E14 | Analytics & Observability | F14.8.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Operational Dashboards. | MVP-P0 | High | CONFIRMED | Analyst | 3 | 18 | 0 | Not Started |  | F14.8 | Done when implementation/validation is traceable to the parent feature. |  | Analytics/Engineering
471 | E14 | Analytics & Observability | F14.8.T2 | Implementation | Task | Implement Operational Dashboards with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Analyst | 4 | 24 | 0 | Not Started |  | F14.8 | Done when implementation/validation is traceable to the parent feature. |  | Analytics/Engineering
472 | E14 | Analytics & Observability | F14.8.T3 | Validation & QA | Task | Add automated/manual validation for Operational Dashboards; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F14.8 | Done when implementation/validation is traceable to the parent feature. |  | Analytics/Engineering
473 | E15 | Daily Reward | F15.1 | Daily Reward Config | Feature | Versioned reward calendar/config | MVP-P0 | Medium | CONFIRMED | Backend Engineer | 5 | 30 | 0 | Not Started |  | E15 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
474 | E15 | Daily Reward | F15.1.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Daily Reward Config. | MVP-P0 | Medium | CONFIRMED | Backend Engineer | 2 | 12 | 0 | Not Started |  | F15.1 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
475 | E15 | Daily Reward | F15.1.T2 | Implementation | Task | Implement Daily Reward Config with versioned/configurable behavior where required. | MVP-P0 | Medium | CONFIRMED | Backend Engineer | 3 | 18 | 0 | Not Started |  | F15.1 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
476 | E15 | Daily Reward | F15.1.T3 | Validation & QA | Task | Add automated/manual validation for Daily Reward Config; cover error, retry and regression cases. | MVP-P0 | Medium | CONFIRMED | QA Engineer | 2 | 12 | 0 | Not Started |  | F15.1 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
477 | E15 | Daily Reward | F15.2 | Daily Reward Eligibility | Feature | Server-time claim eligibility and idempotency | MVP-P0 | Medium | CONFIRMED | Backend Engineer | 8 | 48 | 0 | Not Started |  | E15 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
478 | E15 | Daily Reward | F15.2.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Daily Reward Eligibility. | MVP-P0 | Medium | CONFIRMED | Backend Engineer | 3 | 18 | 0 | Not Started |  | F15.2 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
479 | E15 | Daily Reward | F15.2.T2 | Implementation | Task | Implement Daily Reward Eligibility with versioned/configurable behavior where required. | MVP-P0 | Medium | CONFIRMED | Backend Engineer | 4 | 24 | 0 | Not Started |  | F15.2 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
480 | E15 | Daily Reward | F15.2.T3 | Validation & QA | Task | Add automated/manual validation for Daily Reward Eligibility; cover error, retry and regression cases. | MVP-P0 | Medium | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F15.2 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
481 | E15 | Daily Reward | F15.3 | Daily Reward UI | Feature | Calendar/claim experience | MVP-P0 | Medium | CONFIRMED | UI Engineer | 8 | 48 | 0 | Not Started |  | E15 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
482 | E15 | Daily Reward | F15.3.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Daily Reward UI. | MVP-P0 | Medium | CONFIRMED | UI Engineer | 3 | 18 | 0 | Not Started |  | F15.3 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
483 | E15 | Daily Reward | F15.3.T2 | Implementation | Task | Implement Daily Reward UI with versioned/configurable behavior where required. | MVP-P0 | Medium | CONFIRMED | UI Engineer | 4 | 24 | 0 | Not Started |  | F15.3 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
484 | E15 | Daily Reward | F15.3.T3 | Validation & QA | Task | Add automated/manual validation for Daily Reward UI; cover error, retry and regression cases. | MVP-P0 | Medium | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F15.3 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
485 | E15 | Daily Reward | F15.4 | Daily Reward Analytics | Feature | Claim and play conversion | MVP-P0 | Medium | CONFIRMED | Analytics Engineer | 5 | 30 | 0 | Not Started |  | E15 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
486 | E15 | Daily Reward | F15.4.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Daily Reward Analytics. | MVP-P0 | Medium | CONFIRMED | Analytics Engineer | 2 | 12 | 0 | Not Started |  | F15.4 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
487 | E15 | Daily Reward | F15.4.T2 | Implementation | Task | Implement Daily Reward Analytics with versioned/configurable behavior where required. | MVP-P0 | Medium | CONFIRMED | Analytics Engineer | 3 | 18 | 0 | Not Started |  | F15.4 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
488 | E15 | Daily Reward | F15.4.T3 | Validation & QA | Task | Add automated/manual validation for Daily Reward Analytics; cover error, retry and regression cases. | MVP-P0 | Medium | CONFIRMED | QA Engineer | 2 | 12 | 0 | Not Started |  | F15.4 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
489 | E16 | Daily Challenge | F16.1 | Daily Challenge Definition | Feature | Date, fixed content/config, board/seed and reward | MVP-P0 | Medium | CONFIRMED | Backend/Game Designer | 8 | 48 | 0 | Not Started |  | E16 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Game Design
490 | E16 | Daily Challenge | F16.1.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Daily Challenge Definition. | MVP-P0 | Medium | CONFIRMED | Backend/Game Designer | 3 | 18 | 0 | Not Started |  | F16.1 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Game Design
491 | E16 | Daily Challenge | F16.1.T2 | Implementation | Task | Implement Daily Challenge Definition with versioned/configurable behavior where required. | MVP-P0 | Medium | CONFIRMED | Backend/Game Designer | 4 | 24 | 0 | Not Started |  | F16.1 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Game Design
492 | E16 | Daily Challenge | F16.1.T3 | Validation & QA | Task | Add automated/manual validation for Daily Challenge Definition; cover error, retry and regression cases. | MVP-P0 | Medium | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F16.1 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Game Design
493 | E16 | Daily Challenge | F16.2 | Challenge Generation | Feature | Solver-validated deterministic shared board | MVP-P0 | Medium | CONFIRMED | Solver/Backend Engineer | 13 | 78 | 0 | Not Started |  | E16 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Game Design
494 | E16 | Daily Challenge | F16.2.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Challenge Generation. | MVP-P0 | Medium | CONFIRMED | Solver/Backend Engineer | 5 | 30 | 0 | Not Started |  | F16.2 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Game Design
495 | E16 | Daily Challenge | F16.2.T2 | Implementation | Task | Implement Challenge Generation with versioned/configurable behavior where required. | MVP-P0 | Medium | CONFIRMED | Solver/Backend Engineer | 7 | 42 | 0 | Not Started |  | F16.2 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Game Design
496 | E16 | Daily Challenge | F16.2.T3 | Validation & QA | Task | Add automated/manual validation for Challenge Generation; cover error, retry and regression cases. | MVP-P0 | Medium | CONFIRMED | QA Engineer | 5 | 30 | 0 | Not Started |  | F16.2 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Game Design
497 | E16 | Daily Challenge | F16.3 | Daily Challenge UI | Feature | Landing, gameplay and completion | MVP-P0 | Medium | CONFIRMED | UI Engineer | 13 | 78 | 0 | Not Started |  | E16 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Game Design
498 | E16 | Daily Challenge | F16.3.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Daily Challenge UI. | MVP-P0 | Medium | CONFIRMED | UI Engineer | 5 | 30 | 0 | Not Started |  | F16.3 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Game Design
499 | E16 | Daily Challenge | F16.3.T2 | Implementation | Task | Implement Daily Challenge UI with versioned/configurable behavior where required. | MVP-P0 | Medium | CONFIRMED | UI Engineer | 7 | 42 | 0 | Not Started |  | F16.3 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Game Design
500 | E16 | Daily Challenge | F16.3.T3 | Validation & QA | Task | Add automated/manual validation for Daily Challenge UI; cover error, retry and regression cases. | MVP-P0 | Medium | CONFIRMED | QA Engineer | 5 | 30 | 0 | Not Started |  | F16.3 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Game Design
501 | E16 | Daily Challenge | F16.4 | Challenge Progress/Reward | Feature | Attempts, completion and idempotent reward | MVP-P0 | Medium | CONFIRMED | Backend Engineer | 8 | 48 | 0 | Not Started |  | E16 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Game Design
502 | E16 | Daily Challenge | F16.4.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Challenge Progress/Reward. | MVP-P0 | Medium | CONFIRMED | Backend Engineer | 3 | 18 | 0 | Not Started |  | F16.4 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Game Design
503 | E16 | Daily Challenge | F16.4.T2 | Implementation | Task | Implement Challenge Progress/Reward with versioned/configurable behavior where required. | MVP-P0 | Medium | CONFIRMED | Backend Engineer | 4 | 24 | 0 | Not Started |  | F16.4 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Game Design
504 | E16 | Daily Challenge | F16.4.T3 | Validation & QA | Task | Add automated/manual validation for Challenge Progress/Reward; cover error, retry and regression cases. | MVP-P0 | Medium | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F16.4 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Game Design
505 | E16 | Daily Challenge | F16.5 | Daily Challenge Analytics | Feature | Participation, completion and fairness | MVP-P0 | Medium | CONFIRMED | Analytics Engineer | 5 | 30 | 0 | Not Started |  | E16 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Game Design
506 | E16 | Daily Challenge | F16.5.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Daily Challenge Analytics. | MVP-P0 | Medium | CONFIRMED | Analytics Engineer | 2 | 12 | 0 | Not Started |  | F16.5 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Game Design
507 | E16 | Daily Challenge | F16.5.T2 | Implementation | Task | Implement Daily Challenge Analytics with versioned/configurable behavior where required. | MVP-P0 | Medium | CONFIRMED | Analytics Engineer | 3 | 18 | 0 | Not Started |  | F16.5 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Game Design
508 | E16 | Daily Challenge | F16.5.T3 | Validation & QA | Task | Add automated/manual validation for Daily Challenge Analytics; cover error, retry and regression cases. | MVP-P0 | Medium | CONFIRMED | QA Engineer | 2 | 12 | 0 | Not Started |  | F16.5 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Game Design
509 | E17 | Daily Streak & Smart Notifications | F17.1 | Daily Streak State | Feature | Consecutive-day state and milestone hooks | MVP-P0 | Medium | CONFIRMED | Backend Engineer | 8 | 48 | 0 | Not Started |  | E17 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
510 | E17 | Daily Streak & Smart Notifications | F17.1.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Daily Streak State. | MVP-P0 | Medium | CONFIRMED | Backend Engineer | 3 | 18 | 0 | Not Started |  | F17.1 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
511 | E17 | Daily Streak & Smart Notifications | F17.1.T2 | Implementation | Task | Implement Daily Streak State with versioned/configurable behavior where required. | MVP-P0 | Medium | CONFIRMED | Backend Engineer | 4 | 24 | 0 | Not Started |  | F17.1 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
512 | E17 | Daily Streak & Smart Notifications | F17.1.T3 | Validation & QA | Task | Add automated/manual validation for Daily Streak State; cover error, retry and regression cases. | MVP-P0 | Medium | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F17.1 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
513 | E17 | Daily Streak & Smart Notifications | F17.2 | Streak UI | Feature | Current streak and milestone presentation | MVP-P0 | Medium | CONFIRMED | UI Engineer | 5 | 30 | 0 | Not Started |  | E17 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
514 | E17 | Daily Streak & Smart Notifications | F17.2.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Streak UI. | MVP-P0 | Medium | CONFIRMED | UI Engineer | 2 | 12 | 0 | Not Started |  | F17.2 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
515 | E17 | Daily Streak & Smart Notifications | F17.2.T2 | Implementation | Task | Implement Streak UI with versioned/configurable behavior where required. | MVP-P0 | Medium | CONFIRMED | UI Engineer | 3 | 18 | 0 | Not Started |  | F17.2 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
516 | E17 | Daily Streak & Smart Notifications | F17.2.T3 | Validation & QA | Task | Add automated/manual validation for Streak UI; cover error, retry and regression cases. | MVP-P0 | Medium | CONFIRMED | QA Engineer | 2 | 12 | 0 | Not Started |  | F17.2 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
517 | E17 | Daily Streak & Smart Notifications | F17.3 | Push Registration | Feature | Token registration and preferences | MVP-P0 | Medium | CONFIRMED | Mobile/Backend Engineer | 8 | 48 | 0 | Not Started |  | E17 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
518 | E17 | Daily Streak & Smart Notifications | F17.3.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Push Registration. | MVP-P0 | Medium | CONFIRMED | Mobile/Backend Engineer | 3 | 18 | 0 | Not Started |  | F17.3 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
519 | E17 | Daily Streak & Smart Notifications | F17.3.T2 | Implementation | Task | Implement Push Registration with versioned/configurable behavior where required. | MVP-P0 | Medium | CONFIRMED | Mobile/Backend Engineer | 4 | 24 | 0 | Not Started |  | F17.3 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
520 | E17 | Daily Streak & Smart Notifications | F17.3.T3 | Validation & QA | Task | Add automated/manual validation for Push Registration; cover error, retry and regression cases. | MVP-P0 | Medium | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F17.3 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
521 | E17 | Daily Streak & Smart Notifications | F17.4 | Smart Notification Rules | Feature | Daily challenge, streak risk and future event notifications | MVP-P0 | Medium | CONFIRMED | Backend Engineer | 8 | 48 | 0 | Not Started |  | E17 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
522 | E17 | Daily Streak & Smart Notifications | F17.4.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Smart Notification Rules. | MVP-P0 | Medium | CONFIRMED | Backend Engineer | 3 | 18 | 0 | Not Started |  | F17.4 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
523 | E17 | Daily Streak & Smart Notifications | F17.4.T2 | Implementation | Task | Implement Smart Notification Rules with versioned/configurable behavior where required. | MVP-P0 | Medium | CONFIRMED | Backend Engineer | 4 | 24 | 0 | Not Started |  | F17.4 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
524 | E17 | Daily Streak & Smart Notifications | F17.4.T3 | Validation & QA | Task | Add automated/manual validation for Smart Notification Rules; cover error, retry and regression cases. | MVP-P0 | Medium | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F17.4 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
525 | E17 | Daily Streak & Smart Notifications | F17.5 | Notification Deep Links | Feature | Typed routes and expired-target fallback | MVP-P0 | Medium | CONFIRMED | Mobile Engineer | 5 | 30 | 0 | Not Started |  | E17 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
526 | E17 | Daily Streak & Smart Notifications | F17.5.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Notification Deep Links. | MVP-P0 | Medium | CONFIRMED | Mobile Engineer | 2 | 12 | 0 | Not Started |  | F17.5 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
527 | E17 | Daily Streak & Smart Notifications | F17.5.T2 | Implementation | Task | Implement Notification Deep Links with versioned/configurable behavior where required. | MVP-P0 | Medium | CONFIRMED | Mobile Engineer | 3 | 18 | 0 | Not Started |  | F17.5 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
528 | E17 | Daily Streak & Smart Notifications | F17.5.T3 | Validation & QA | Task | Add automated/manual validation for Notification Deep Links; cover error, retry and regression cases. | MVP-P0 | Medium | CONFIRMED | QA Engineer | 2 | 12 | 0 | Not Started |  | F17.5 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: Daily systems are P0 at launch (not P1). | Product/Backend
529 | E18 | QA & Automated Validation | F18.1 | Engine Unit Tests | Feature | Automate all core move and invariant rules | MVP-P0 | High | CONFIRMED | QA/Game Engineer | 13 | 78 | 0 | Not Started |  | E18 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
530 | E18 | QA & Automated Validation | F18.1.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Engine Unit Tests. | MVP-P0 | High | CONFIRMED | QA/Game Engineer | 5 | 30 | 0 | Not Started |  | F18.1 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
531 | E18 | QA & Automated Validation | F18.1.T2 | Implementation | Task | Implement Engine Unit Tests with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | QA/Game Engineer | 7 | 42 | 0 | Not Started |  | F18.1 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
532 | E18 | QA & Automated Validation | F18.1.T3 | Validation & QA | Task | Add automated/manual validation for Engine Unit Tests; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 5 | 30 | 0 | Not Started |  | F18.1 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
533 | E18 | QA & Automated Validation | F18.2 | Property-Based Tests | Feature | Random state/action invariant validation | MVP-P0 | High | PROPOSED | QA Engineer | 13 | 78 | 0 | Not Started |  | E18 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
534 | E18 | QA & Automated Validation | F18.2.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Property-Based Tests. | MVP-P0 | High | PROPOSED | QA Engineer | 5 | 30 | 0 | Not Started |  | F18.2 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
535 | E18 | QA & Automated Validation | F18.2.T2 | Implementation | Task | Implement Property-Based Tests with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED | QA Engineer | 7 | 42 | 0 | Not Started |  | F18.2 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
536 | E18 | QA & Automated Validation | F18.2.T3 | Validation & QA | Task | Add automated/manual validation for Property-Based Tests; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED | QA Engineer | 5 | 30 | 0 | Not Started |  | F18.2 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
537 | E18 | QA & Automated Validation | F18.3 | Solver Golden Boards | Feature | Solvable/unsolvable/boundary regression corpus | MVP-P0 | High | CONFIRMED STRATEGY | QA/Solver Engineer | 13 | 78 | 0 | Not Started |  | E18 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
538 | E18 | QA & Automated Validation | F18.3.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Solver Golden Boards. | MVP-P0 | High | CONFIRMED STRATEGY | QA/Solver Engineer | 5 | 30 | 0 | Not Started |  | F18.3 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
539 | E18 | QA & Automated Validation | F18.3.T2 | Implementation | Task | Implement Solver Golden Boards with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED STRATEGY | QA/Solver Engineer | 7 | 42 | 0 | Not Started |  | F18.3 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
540 | E18 | QA & Automated Validation | F18.3.T3 | Validation & QA | Task | Add automated/manual validation for Solver Golden Boards; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED STRATEGY | QA Engineer | 5 | 30 | 0 | Not Started |  | F18.3 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
541 | E18 | QA & Automated Validation | F18.4 | Engine-Solver Parity | Feature | Cross-check legal moves and replay | MVP-P0 | High | CONFIRMED | QA Engineer | 13 | 78 | 0 | Not Started |  | E18 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
542 | E18 | QA & Automated Validation | F18.4.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Engine-Solver Parity. | MVP-P0 | High | CONFIRMED | QA Engineer | 5 | 30 | 0 | Not Started |  | F18.4 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
543 | E18 | QA & Automated Validation | F18.4.T2 | Implementation | Task | Implement Engine-Solver Parity with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | QA Engineer | 7 | 42 | 0 | Not Started |  | F18.4 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
544 | E18 | QA & Automated Validation | F18.4.T3 | Validation & QA | Task | Add automated/manual validation for Engine-Solver Parity; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 5 | 30 | 0 | Not Started |  | F18.4 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
545 | E18 | QA & Automated Validation | F18.5 | Simulation CI | Feature | Automated generated-board simulation tiers | MVP-P0 | High | CONFIRMED | QA Engineer | 13 | 78 | 0 | Not Started |  | E18 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
546 | E18 | QA & Automated Validation | F18.5.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Simulation CI. | MVP-P0 | High | CONFIRMED | QA Engineer | 5 | 30 | 0 | Not Started |  | F18.5 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
547 | E18 | QA & Automated Validation | F18.5.T2 | Implementation | Task | Implement Simulation CI with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | QA Engineer | 7 | 42 | 0 | Not Started |  | F18.5 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
548 | E18 | QA & Automated Validation | F18.5.T3 | Validation & QA | Task | Add automated/manual validation for Simulation CI; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 5 | 30 | 0 | Not Started |  | F18.5 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
549 | E18 | QA & Automated Validation | F18.6 | Arabic Content QA | Feature | Language/semantic/RTL checklist and signoff | MVP-P0 | High | CONFIRMED | Arabic Reviewer/QA | 8 | 48 | 0 | Not Started |  | E18 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
550 | E18 | QA & Automated Validation | F18.6.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Arabic Content QA. | MVP-P0 | High | CONFIRMED | Arabic Reviewer/QA | 3 | 18 | 0 | Not Started |  | F18.6 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
551 | E18 | QA & Automated Validation | F18.6.T2 | Implementation | Task | Implement Arabic Content QA with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | Arabic Reviewer/QA | 4 | 24 | 0 | Not Started |  | F18.6 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
552 | E18 | QA & Automated Validation | F18.6.T3 | Validation & QA | Task | Add automated/manual validation for Arabic Content QA; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F18.6 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
553 | E18 | QA & Automated Validation | F18.7 | Economy/IAP QA | Feature | Idempotency, ad, purchase and entitlement matrix | MVP-P0 | High | CONFIRMED | QA Engineer | 8 | 48 | 0 | Not Started |  | E18 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
554 | E18 | QA & Automated Validation | F18.7.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Economy/IAP QA. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F18.7 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
555 | E18 | QA & Automated Validation | F18.7.T2 | Implementation | Task | Implement Economy/IAP QA with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | QA Engineer | 4 | 24 | 0 | Not Started |  | F18.7 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
556 | E18 | QA & Automated Validation | F18.7.T3 | Validation & QA | Task | Add automated/manual validation for Economy/IAP QA; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F18.7 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
557 | E18 | QA & Automated Validation | F18.8 | Cloud/Offline QA | Feature | Sync, conflict, resume and network failures | MVP-P0 | High | CONFIRMED | QA Engineer | 8 | 48 | 0 | Not Started |  | E18 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
558 | E18 | QA & Automated Validation | F18.8.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Cloud/Offline QA. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F18.8 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
559 | E18 | QA & Automated Validation | F18.8.T2 | Implementation | Task | Implement Cloud/Offline QA with versioned/configurable behavior where required. | MVP-P0 | High | CONFIRMED | QA Engineer | 4 | 24 | 0 | Not Started |  | F18.8 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
560 | E18 | QA & Automated Validation | F18.8.T3 | Validation & QA | Task | Add automated/manual validation for Cloud/Offline QA; cover error, retry and regression cases. | MVP-P0 | High | CONFIRMED | QA Engineer | 3 | 18 | 0 | Not Started |  | F18.8 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
561 | E18 | QA & Automated Validation | F18.9 | Device/RTL QA | Feature | Representative screen/device matrix | MVP-P0 | High | REQUIRED | QA Engineer | 8 | 48 | 0 | Not Started |  | E18 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
562 | E18 | QA & Automated Validation | F18.9.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Device/RTL QA. | MVP-P0 | High | REQUIRED | QA Engineer | 3 | 18 | 0 | Not Started |  | F18.9 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
563 | E18 | QA & Automated Validation | F18.9.T2 | Implementation | Task | Implement Device/RTL QA with versioned/configurable behavior where required. | MVP-P0 | High | REQUIRED | QA Engineer | 4 | 24 | 0 | Not Started |  | F18.9 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
564 | E18 | QA & Automated Validation | F18.9.T3 | Validation & QA | Task | Add automated/manual validation for Device/RTL QA; cover error, retry and regression cases. | MVP-P0 | High | REQUIRED | QA Engineer | 3 | 18 | 0 | Not Started |  | F18.9 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
565 | E18 | QA & Automated Validation | F18.10 | Release Regression Suite | Feature | Critical E2E smoke and release candidate suite | MVP-P0 | High | REQUIRED | QA Engineer | 13 | 78 | 0 | Not Started |  | E18 | Feature behavior matches the approved specification and has test evidence. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
566 | E18 | QA & Automated Validation | F18.10.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Release Regression Suite. | MVP-P0 | High | REQUIRED | QA Engineer | 5 | 30 | 0 | Not Started |  | F18.10 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
567 | E18 | QA & Automated Validation | F18.10.T2 | Implementation | Task | Implement Release Regression Suite with versioned/configurable behavior where required. | MVP-P0 | High | REQUIRED | QA Engineer | 7 | 42 | 0 | Not Started |  | F18.10 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
568 | E18 | QA & Automated Validation | F18.10.T3 | Validation & QA | Task | Add automated/manual validation for Release Regression Suite; cover error, retry and regression cases. | MVP-P0 | High | REQUIRED | QA Engineer | 5 | 30 | 0 | Not Started |  | F18.10 | Done when implementation/validation is traceable to the parent feature. | Decision Align v1.1: S0–S4; release blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity critical. | QA
569 | E19 | DevOps, Environments & Release | F19.1 | Repository & Branching | Feature | Repositories, conventions and protection rules | MVP-P0 | High | PROPOSED | DevOps/Tech Lead | 5 | 30 | 0 | Not Started |  | E19 | Feature behavior matches the approved specification and has test evidence. |  | DevOps
570 | E19 | DevOps, Environments & Release | F19.1.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Repository & Branching. | MVP-P0 | High | PROPOSED | DevOps/Tech Lead | 2 | 12 | 0 | Not Started |  | F19.1 | Done when implementation/validation is traceable to the parent feature. |  | DevOps
571 | E19 | DevOps, Environments & Release | F19.1.T2 | Implementation | Task | Implement Repository & Branching with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED | DevOps/Tech Lead | 3 | 18 | 0 | Not Started |  | F19.1 | Done when implementation/validation is traceable to the parent feature. |  | DevOps
572 | E19 | DevOps, Environments & Release | F19.1.T3 | Validation & QA | Task | Add automated/manual validation for Repository & Branching; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED | QA Engineer | 2 | 12 | 0 | Not Started |  | F19.1 | Done when implementation/validation is traceable to the parent feature. |  | DevOps
573 | E19 | DevOps, Environments & Release | F19.2 | Client CI | Feature | Lint, tests, builds and internal artifacts | MVP-P0 | High | PROPOSED | DevOps Engineer | 8 | 48 | 0 | Not Started |  | E19 | Feature behavior matches the approved specification and has test evidence. |  | DevOps
574 | E19 | DevOps, Environments & Release | F19.2.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Client CI. | MVP-P0 | High | PROPOSED | DevOps Engineer | 3 | 18 | 0 | Not Started |  | F19.2 | Done when implementation/validation is traceable to the parent feature. |  | DevOps
575 | E19 | DevOps, Environments & Release | F19.2.T2 | Implementation | Task | Implement Client CI with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED | DevOps Engineer | 4 | 24 | 0 | Not Started |  | F19.2 | Done when implementation/validation is traceable to the parent feature. |  | DevOps
576 | E19 | DevOps, Environments & Release | F19.2.T3 | Validation & QA | Task | Add automated/manual validation for Client CI; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED | QA Engineer | 3 | 18 | 0 | Not Started |  | F19.2 | Done when implementation/validation is traceable to the parent feature. |  | DevOps
577 | E19 | DevOps, Environments & Release | F19.3 | Backend CI/CD | Feature | Tests, migrations, package/container and staged deployment | MVP-P0 | High | PROPOSED | DevOps Engineer | 8 | 48 | 0 | Not Started |  | E19 | Feature behavior matches the approved specification and has test evidence. |  | DevOps
578 | E19 | DevOps, Environments & Release | F19.3.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Backend CI/CD. | MVP-P0 | High | PROPOSED | DevOps Engineer | 3 | 18 | 0 | Not Started |  | F19.3 | Done when implementation/validation is traceable to the parent feature. |  | DevOps
579 | E19 | DevOps, Environments & Release | F19.3.T2 | Implementation | Task | Implement Backend CI/CD with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED | DevOps Engineer | 4 | 24 | 0 | Not Started |  | F19.3 | Done when implementation/validation is traceable to the parent feature. |  | DevOps
580 | E19 | DevOps, Environments & Release | F19.3.T3 | Validation & QA | Task | Add automated/manual validation for Backend CI/CD; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED | QA Engineer | 3 | 18 | 0 | Not Started |  | F19.3 | Done when implementation/validation is traceable to the parent feature. |  | DevOps
581 | E19 | DevOps, Environments & Release | F19.4 | Environment Configuration | Feature | DEV/TEST/STAGING/PROD separation | MVP-P0 | High | PROPOSED | DevOps Engineer | 8 | 48 | 0 | Not Started |  | E19 | Feature behavior matches the approved specification and has test evidence. |  | DevOps
582 | E19 | DevOps, Environments & Release | F19.4.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Environment Configuration. | MVP-P0 | High | PROPOSED | DevOps Engineer | 3 | 18 | 0 | Not Started |  | F19.4 | Done when implementation/validation is traceable to the parent feature. |  | DevOps
583 | E19 | DevOps, Environments & Release | F19.4.T2 | Implementation | Task | Implement Environment Configuration with versioned/configurable behavior where required. | MVP-P0 | High | PROPOSED | DevOps Engineer | 4 | 24 | 0 | Not Started |  | F19.4 | Done when implementation/validation is traceable to the parent feature. |  | DevOps
584 | E19 | DevOps, Environments & Release | F19.4.T3 | Validation & QA | Task | Add automated/manual validation for Environment Configuration; cover error, retry and regression cases. | MVP-P0 | High | PROPOSED | QA Engineer | 3 | 18 | 0 | Not Started |  | F19.4 | Done when implementation/validation is traceable to the parent feature. |  | DevOps
585 | E19 | DevOps, Environments & Release | F19.5 | Secrets Management | Feature | Secure runtime/store/backend credentials | MVP-P0 | High | REQUIRED | DevOps Engineer | 5 | 30 | 0 | Not Started |  | E19 | Feature behavior matches the approved specification and has test evidence. |  | DevOps
586 | E19 | DevOps, Environments & Release | F19.5.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Secrets Management. | MVP-P0 | High | REQUIRED | DevOps Engineer | 2 | 12 | 0 | Not Started |  | F19.5 | Done when implementation/validation is traceable to the parent feature. |  | DevOps
587 | E19 | DevOps, Environments & Release | F19.5.T2 | Implementation | Task | Implement Secrets Management with versioned/configurable behavior where required. | MVP-P0 | High | REQUIRED | DevOps Engineer | 3 | 18 | 0 | Not Started |  | F19.5 | Done when implementation/validation is traceable to the parent feature. |  | DevOps
588 | E19 | DevOps, Environments & Release | F19.5.T3 | Validation & QA | Task | Add automated/manual validation for Secrets Management; cover error, retry and regression cases. | MVP-P0 | High | REQUIRED | QA Engineer | 2 | 12 | 0 | Not Started |  | F19.5 | Done when implementation/validation is traceable to the parent feature. |  | DevOps
589 | E19 | DevOps, Environments & Release | F19.6 | Monitoring & Alerts | Feature | Backend, purchase, content and solver alerts | MVP-P0 | High | REQUIRED | DevOps Engineer | 8 | 48 | 0 | Not Started |  | E19 | Feature behavior matches the approved specification and has test evidence. |  | DevOps
590 | E19 | DevOps, Environments & Release | F19.6.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Monitoring & Alerts. | MVP-P0 | High | REQUIRED | DevOps Engineer | 3 | 18 | 0 | Not Started |  | F19.6 | Done when implementation/validation is traceable to the parent feature. |  | DevOps
591 | E19 | DevOps, Environments & Release | F19.6.T2 | Implementation | Task | Implement Monitoring & Alerts with versioned/configurable behavior where required. | MVP-P0 | High | REQUIRED | DevOps Engineer | 4 | 24 | 0 | Not Started |  | F19.6 | Done when implementation/validation is traceable to the parent feature. |  | DevOps
592 | E19 | DevOps, Environments & Release | F19.6.T3 | Validation & QA | Task | Add automated/manual validation for Monitoring & Alerts; cover error, retry and regression cases. | MVP-P0 | High | REQUIRED | QA Engineer | 3 | 18 | 0 | Not Started |  | F19.6 | Done when implementation/validation is traceable to the parent feature. |  | DevOps
593 | E19 | DevOps, Environments & Release | F19.7 | Backup & Restore | Feature | DB/content backup plus restore drill | MVP-P0 | High | REQUIRED | DevOps Engineer | 8 | 48 | 0 | Not Started |  | E19 | Feature behavior matches the approved specification and has test evidence. |  | DevOps
594 | E19 | DevOps, Environments & Release | F19.7.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Backup & Restore. | MVP-P0 | High | REQUIRED | DevOps Engineer | 3 | 18 | 0 | Not Started |  | F19.7 | Done when implementation/validation is traceable to the parent feature. |  | DevOps
595 | E19 | DevOps, Environments & Release | F19.7.T2 | Implementation | Task | Implement Backup & Restore with versioned/configurable behavior where required. | MVP-P0 | High | REQUIRED | DevOps Engineer | 4 | 24 | 0 | Not Started |  | F19.7 | Done when implementation/validation is traceable to the parent feature. |  | DevOps
596 | E19 | DevOps, Environments & Release | F19.7.T3 | Validation & QA | Task | Add automated/manual validation for Backup & Restore; cover error, retry and regression cases. | MVP-P0 | High | REQUIRED | QA Engineer | 3 | 18 | 0 | Not Started |  | F19.7 | Done when implementation/validation is traceable to the parent feature. |  | DevOps
597 | E19 | DevOps, Environments & Release | F19.8 | Store Release Pipeline | Feature | Signing, internal testing, submission and rollout | MVP-P0 | High | REQUIRED | Mobile/DevOps Engineer | 8 | 48 | 0 | Not Started |  | E19 | Feature behavior matches the approved specification and has test evidence. |  | DevOps
598 | E19 | DevOps, Environments & Release | F19.8.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Store Release Pipeline. | MVP-P0 | High | REQUIRED | Mobile/DevOps Engineer | 3 | 18 | 0 | Not Started |  | F19.8 | Done when implementation/validation is traceable to the parent feature. |  | DevOps
599 | E19 | DevOps, Environments & Release | F19.8.T2 | Implementation | Task | Implement Store Release Pipeline with versioned/configurable behavior where required. | MVP-P0 | High | REQUIRED | Mobile/DevOps Engineer | 4 | 24 | 0 | Not Started |  | F19.8 | Done when implementation/validation is traceable to the parent feature. |  | DevOps
600 | E19 | DevOps, Environments & Release | F19.8.T3 | Validation & QA | Task | Add automated/manual validation for Store Release Pipeline; cover error, retry and regression cases. | MVP-P0 | High | REQUIRED | QA Engineer | 3 | 18 | 0 | Not Started |  | F19.8 | Done when implementation/validation is traceable to the parent feature. |  | DevOps
601 | E20 | Security, Privacy & Accessibility | F20.1 | API Security Baseline | Feature | TLS, auth, authorization, validation and rate-limit hooks | MVP-P0 | High | REQUIRED | Backend Engineer | 8 | 48 | 0 | Not Started |  | E20 | Feature behavior matches the approved specification and has test evidence. |  | Engineering/Product
602 | E20 | Security, Privacy & Accessibility | F20.1.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for API Security Baseline. | MVP-P0 | High | REQUIRED | Backend Engineer | 3 | 18 | 0 | Not Started |  | F20.1 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
603 | E20 | Security, Privacy & Accessibility | F20.1.T2 | Implementation | Task | Implement API Security Baseline with versioned/configurable behavior where required. | MVP-P0 | High | REQUIRED | Backend Engineer | 4 | 24 | 0 | Not Started |  | F20.1 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
604 | E20 | Security, Privacy & Accessibility | F20.1.T3 | Validation & QA | Task | Add automated/manual validation for API Security Baseline; cover error, retry and regression cases. | MVP-P0 | High | REQUIRED | QA Engineer | 3 | 18 | 0 | Not Started |  | F20.1 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
605 | E20 | Security, Privacy & Accessibility | F20.2 | Purchase/Wallet Abuse Protection | Feature | Server validation, idempotency and replay protection | MVP-P0 | High | REQUIRED | Backend Engineer | 8 | 48 | 0 | Not Started |  | E20 | Feature behavior matches the approved specification and has test evidence. |  | Engineering/Product
606 | E20 | Security, Privacy & Accessibility | F20.2.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Purchase/Wallet Abuse Protection. | MVP-P0 | High | REQUIRED | Backend Engineer | 3 | 18 | 0 | Not Started |  | F20.2 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
607 | E20 | Security, Privacy & Accessibility | F20.2.T2 | Implementation | Task | Implement Purchase/Wallet Abuse Protection with versioned/configurable behavior where required. | MVP-P0 | High | REQUIRED | Backend Engineer | 4 | 24 | 0 | Not Started |  | F20.2 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
608 | E20 | Security, Privacy & Accessibility | F20.2.T3 | Validation & QA | Task | Add automated/manual validation for Purchase/Wallet Abuse Protection; cover error, retry and regression cases. | MVP-P0 | High | REQUIRED | QA Engineer | 3 | 18 | 0 | Not Started |  | F20.2 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
609 | E20 | Security, Privacy & Accessibility | F20.3 | Privacy/Data Minimization | Feature | Anonymous-first data collection and deletion-ready model | MVP-P0 | High | REQUIRED | Product/Backend | 5 | 30 | 0 | Not Started |  | E20 | Feature behavior matches the approved specification and has test evidence. |  | Engineering/Product
610 | E20 | Security, Privacy & Accessibility | F20.3.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Privacy/Data Minimization. | MVP-P0 | High | REQUIRED | Product/Backend | 2 | 12 | 0 | Not Started |  | F20.3 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
611 | E20 | Security, Privacy & Accessibility | F20.3.T2 | Implementation | Task | Implement Privacy/Data Minimization with versioned/configurable behavior where required. | MVP-P0 | High | REQUIRED | Product/Backend | 3 | 18 | 0 | Not Started |  | F20.3 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
612 | E20 | Security, Privacy & Accessibility | F20.3.T3 | Validation & QA | Task | Add automated/manual validation for Privacy/Data Minimization; cover error, retry and regression cases. | MVP-P0 | High | REQUIRED | QA Engineer | 2 | 12 | 0 | Not Started |  | F20.3 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
613 | E20 | Security, Privacy & Accessibility | F20.4 | Consent & Store Compliance | Feature | Ads/analytics/store privacy flows | MVP-P0 | High | TBD PROVIDERS | Product/Mobile Engineer | 8 | 48 | 0 | Not Started |  | E20 | Feature behavior matches the approved specification and has test evidence. |  | Engineering/Product
614 | E20 | Security, Privacy & Accessibility | F20.4.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Consent & Store Compliance. | MVP-P0 | High | TBD PROVIDERS | Product/Mobile Engineer | 3 | 18 | 0 | Not Started |  | F20.4 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
615 | E20 | Security, Privacy & Accessibility | F20.4.T2 | Implementation | Task | Implement Consent & Store Compliance with versioned/configurable behavior where required. | MVP-P0 | High | TBD PROVIDERS | Product/Mobile Engineer | 4 | 24 | 0 | Not Started |  | F20.4 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
616 | E20 | Security, Privacy & Accessibility | F20.4.T3 | Validation & QA | Task | Add automated/manual validation for Consent & Store Compliance; cover error, retry and regression cases. | MVP-P0 | High | TBD PROVIDERS | QA Engineer | 3 | 18 | 0 | Not Started |  | F20.4 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
617 | E20 | Security, Privacy & Accessibility | F20.5 | Accessibility Implementation | Feature | RTL, semantics, text scaling, contrast and touch targets | MVP-P0 | High | REQUIRED | Mobile/UI Engineer | 8 | 48 | 0 | Not Started |  | E20 | Feature behavior matches the approved specification and has test evidence. |  | Engineering/Product
618 | E20 | Security, Privacy & Accessibility | F20.5.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Accessibility Implementation. | MVP-P0 | High | REQUIRED | Mobile/UI Engineer | 3 | 18 | 0 | Not Started |  | F20.5 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
619 | E20 | Security, Privacy & Accessibility | F20.5.T2 | Implementation | Task | Implement Accessibility Implementation with versioned/configurable behavior where required. | MVP-P0 | High | REQUIRED | Mobile/UI Engineer | 4 | 24 | 0 | Not Started |  | F20.5 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
620 | E20 | Security, Privacy & Accessibility | F20.5.T3 | Validation & QA | Task | Add automated/manual validation for Accessibility Implementation; cover error, retry and regression cases. | MVP-P0 | High | REQUIRED | QA Engineer | 3 | 18 | 0 | Not Started |  | F20.5 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
621 | E20 | Security, Privacy & Accessibility | F20.6 | Security QA | Feature | Authz, IDOR, forged grants and unsafe-upload checks | MVP-P0 | High | REQUIRED | QA/Security | 8 | 48 | 0 | Not Started |  | E20 | Feature behavior matches the approved specification and has test evidence. |  | Engineering/Product
622 | E20 | Security, Privacy & Accessibility | F20.6.T1 | Analysis & Design | Task | Finalize contracts, edge cases and acceptance criteria for Security QA. | MVP-P0 | High | REQUIRED | QA/Security | 3 | 18 | 0 | Not Started |  | F20.6 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
623 | E20 | Security, Privacy & Accessibility | F20.6.T2 | Implementation | Task | Implement Security QA with versioned/configurable behavior where required. | MVP-P0 | High | REQUIRED | QA/Security | 4 | 24 | 0 | Not Started |  | F20.6 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product
624 | E20 | Security, Privacy & Accessibility | F20.6.T3 | Validation & QA | Task | Add automated/manual validation for Security QA; cover error, retry and regression cases. | MVP-P0 | High | REQUIRED | QA Engineer | 3 | 18 | 0 | Not Started |  | F20.6 | Done when implementation/validation is traceable to the parent feature. |  | Engineering/Product

## Epics
MVP Epic Register
20 delivery epics. Phase is a proposed planning classification; no dates/assignees are locked.
Epic ID | Epic | Phase | Decision State | Description | Workstream | Feature Count | Backlog Items | Story Points | Hours | Cost | Status | Progress %
E01 | Product & UX Foundation | MVP-P0 | CONFIRMED/PROPOSED | Product foundation, UX flows, interaction spec and design-system baseline. | Product/UX | 5 | 20 | 78 | 468 | 0 | Not Started | 0
E02 | Arabic Content System | MVP-P0 | CONFIRMED | Arabic-first content library, editorial rules, associations, members and variants. | Content | 8 | 32 | 144 | 864 | 0 | Not Started | 0
E03 | Game Engine | MVP-P0 | CONFIRMED | Runtime rules for Tableau, Stock, stacks, slots, moves, streak and win. | Engineering | 12 | 48 | 264 | 1584 | 0 | Not Started | 0
E04 | Solver | MVP-P0 | CONFIRMED | Solvability, move-bounded validation, hints, dead-end detection and metrics. | Engineering | 10 | 40 | 252 | 1512 | 0 | Not Started | 0
E05 | Level Generator & Difficulty | MVP-P0 | CONFIRMED | Randomized attempts, level configs, difficulty acceptance and simulation. | Game Design/Engineering | 10 | 40 | 222 | 1332 | 0 | Not Started | 0
E06 | Tutorial & Onboarding | MVP-P0 | CONFIRMED | Concise onboarding plus interactive tutorial. | Product/UX | 7 | 28 | 114 | 684 | 0 | Not Started | 0
E07 | Main Journey & Chapters | MVP-P0 | CONFIRMED | Endless levels, 50-level chapters and difficulty-wave-ready progression. | Product/Game Design | 7 | 28 | 132 | 792 | 0 | Not Started | 0
E08 | Economy & Rewards | MVP-P0 | CONFIRMED | Coins, hints, level rewards, streak rewards and safe transactions. | Product/Backend | 6 | 24 | 90 | 540 | 0 | Not Started | 0
E09 | Gameplay Assistance & Recovery | MVP-P0 | CONFIRMED | Undo, hints, out-of-moves, extra moves and dead-end rescue. | Engineering/Product | 7 | 28 | 102 | 612 | 0 | Not Started | 0
E10 | Monetization | MVP-P0 | CONFIRMED | Rewarded ads, adaptive interstitials, Remove Ads and Coin Pack IAP. | Product/Backend | 11 | 44 | 174 | 1044 | 0 | Not Started | 0
E11 | Identity, Account & Cloud Save | MVP-P0 | CONFIRMED | Anonymous-first identity, optional Apple/Google linking and cloud progression. | Backend | 8 | 32 | 144 | 864 | 0 | Not Started | 0
E12 | Backend Platform (Firebase) | MVP-P0 | CONFIRMED | Firebase Auth, Firestore, Storage, Cloud Functions/Cloud Run, FCM, Remote Config. Azure/ASP.NET/PG always-on out of MVP. | Backend/Cloud | 9 | 36 | 186 | 1116 | 0 | Not Started | 0
E13 | Admin / CMS | MVP-P0 | CONFIRMED | Angular CMS + Entra ID; content/level/solver/publish/audit (2y); Firebase/GCP via security boundaries. | Admin/Content | 10 | 40 | 240 | 1440 | 0 | Not Started | 0
E14 | Analytics & Observability | MVP-P0 | CONFIRMED | Firebase Analytics + BigQuery, Crashlytics, GCP-native serverless observability. | Analytics/Engineering | 8 | 32 | 126 | 756 | 0 | Not Started | 0
E15 | Daily Reward | MVP-P0 | CONFIRMED | Daily reward calendar and claim state. | Product/Backend | 4 | 16 | 60 | 360 | 0 | Not Started | 0
E16 | Daily Challenge | MVP-P0 | CONFIRMED | One daily shared puzzle with special reward. | Product/Game Design | 5 | 20 | 108 | 648 | 0 | Not Started | 0
E17 | Daily Streak & Smart Notifications | MVP-P0 | CONFIRMED | Consecutive-day streak plus smart notifications. | Product/Backend | 5 | 20 | 78 | 468 | 0 | Not Started | 0
E18 | QA & Automated Validation | MVP-P0 | CONFIRMED | Automated rules tests, solver parity, simulation, Arabic QA and release validation. | QA | 10 | 40 | 252 | 1512 | 0 | Not Started | 0
E19 | DevOps, Environments & Release | MVP-P0 | PROPOSED ARCH | CI/CD, environments, secrets, monitoring, backups and store release. | DevOps | 8 | 32 | 132 | 792 | 0 | Not Started | 0
E20 | Security, Privacy & Accessibility | MVP-P0 | CONFIRMED/REQUIRED | Security, privacy, accessibility baseline and store compliance. | Engineering/Product | 6 | 24 | 102 | 612 | 0 | Not Started | 0

## Dashboard
MVP Delivery Dashboard
Formula-driven summary after Decision Align v1.1 (Firebase-first; Daily moved to P0). Cost remains zero until Hourly Rate is entered.
KPI | MVP-P0 | MVP-P1 | Total
Backlog Items | 624 | 0 | 624
Features | 156 | 0 | 156
Story Points | 3000 | 0 | 3000
Estimated Hours | 18000 | 0 | 18000
Estimated Cost | 0 | 0 | 0
Done Items | 0 | 0 | 0
Progress | 0 | 0 | 0
Epic ID | Phase | Story Points | Hours
E01 | MVP-P0 | 78 | 468
E02 | MVP-P0 | 144 | 864
E03 | MVP-P0 | 264 | 1584
E04 | MVP-P0 | 252 | 1512
E05 | MVP-P0 | 222 | 1332
E06 | MVP-P0 | 114 | 684
E07 | MVP-P0 | 132 | 792
E08 | MVP-P0 | 90 | 540
E09 | MVP-P0 | 102 | 612
E10 | MVP-P0 | 174 | 1044
E11 | MVP-P0 | 144 | 864
E12 | MVP-P0 | 186 | 1116
E13 | MVP-P0 | 240 | 1440
E14 | MVP-P0 | 126 | 756
E15 | MVP-P0 | 60 | 360
E16 | MVP-P0 | 108 | 648
E17 | MVP-P0 | 78 | 468
E18 | MVP-P0 | 252 | 1512
E19 | MVP-P0 | 132 | 792
E20 | MVP-P0 | 102 | 612

## Release Plan
Proposed MVP Release Plan
Milestones are sequencing guidance only; no dates are approved. Decision Align v1.1: Firebase-first; Daily systems are launch P0 (not deferred P1).
Milestone | Scope | Entry Criteria | Exit Criteria | Decision State | Target Date | Status
M0 — Foundations | Architecture (Firebase-first), backlog, UX baseline, repositories | Core specs available | Implementation baseline + CI skeleton | CONFIRMED |  | Not Started
M1 — Playable Core | Game Engine + manual test boards | M0 complete | Core moves playable and tested | PROPOSED |  | Not Started
M2 — Solver-Validated Game | Solver + random generator + difficulty metrics | Playable engine | Generated boards valid within Move Limit | PROPOSED |  | Not Started
M3 — MVP Product Loop | Journey + tutorial + rewards + local persistence | M2 complete | Start→play→win/restart→reward→next level | PROPOSED |  | Not Started
M4 — Online Services | Identity + Firebase/GCP serverless + content delivery | M3 stable | Anonymous Firebase Auth cloud sync/server economy functional | CONFIRMED |  | Not Started
M5 — Monetization & CMS | Ads/IAP + CMS + analytics | Online services stable | Store/publish/telemetry/rollback pass | PROPOSED |  | Not Started
M6 — QA / Beta | Simulation, devices, Arabic signoff | M5 complete | Release candidate passes quality gates | PROPOSED |  | Not Started
M7 — Launch Daily Engagement (P0) | Daily Reward + Challenge + Streak + Notifications (launch P0) | Stable core P0 gameplay + Firebase Daily authority | Daily systems validated for launch | CONFIRMED |  | Not Started

## Dependencies
Cross-Epic Dependency Register
Planning dependency map; refine once technical stack is approved.
From | Depends On | Dependency | Type | Criticality | Status | Notes
E04 Solver | E03 Game Engine | Shared authoritative state/rules | Technical | Critical | Confirmed | Solver parity is release-critical.
E05 Level Generator | E04 Solver | Attempt validation/reference moves | Technical | Critical | Confirmed | No generated board bypasses Solver.
E07 Main Journey | E05 Level Generator | Validated Attempts | Functional | Critical | Confirmed | Restart keeps content/config and re-shuffles.
E08 Economy | E03 Game Engine | Reward/streak events | Functional | High | Confirmed | Wallet remains outside Engine.
E09 Assistance | E04 Solver | Hints/dead-end | Technical | Critical | Confirmed | Rescue behavior remains TBD.
E10 Monetization | E08 Economy | Coin grants/spends | Transactional | Critical | Confirmed | IAP validation via Cloud Functions/Cloud Run (Decision Align v1.1).
E11 Cloud | E08 Economy | Economy reconciliation | Data | Critical | Confirmed | Wallet server-authoritative via Functions; progression merge-highest; Firebase Auth.
E13 CMS | E02 Content System | Content schema/reviews | Functional | Critical | Confirmed | Human approval mandatory.
E13 CMS | E04 Solver | Level/sample validation | Technical | High | Confirmed | CMS should share solver/rules.
E14 Analytics | E03/E04/E08/E10 | Domain/solver/economy events | Data | High | Confirmed | Firebase Analytics + BigQuery + Crashlytics confirmed.
E16 Daily Challenge | E04/E05 | Shared deterministic validated board | Technical | High | Confirmed | Daily Challenge is launch P0 (Decision Align v1.1).
E18 QA | E03/E04/E05 | Rules/Solver/generator | Quality | Critical | Confirmed | Parity/replay block release.
E19 DevOps | E12 Backend | Deployment/runtime | Platform | High | Confirmed | GitHub Actions + Firebase/GCP managed services; no Azure/K8s/Redis/broker in MVP.
E20 Security | E10/E11/E12/E13 | Purchases/identity/API/admin security | Security | Critical | Required | Launch requirement.

## Risk Register
MVP Risk Register
Risk ratings are planning proposals; review after stack/scope approval.
Risk ID | Risk | Category | Likelihood | Impact | Rating | Mitigation | Owner Role | Status | Trigger / Signal
R01 | Solver state explosion on advanced boards | Technical | Medium | Critical | High | Prototype early; canonicalization/pruning; simulation; fallback option | Solver Engineer | Open | p95 solve time/timeouts
R02 | Randomized restarts vary too much in difficulty | Game Design | Medium | High | Difficulty windows + variance telemetry | Game Designer | Open | Large B-score spread
R03 | Arabic content production becomes bottleneck | Content | High | High | CMS, AI drafts, reviewer workflow, reusable variants | Content Lead | Open | Content-ready levels lag
R04 | Ambiguous/incorrect associations damage trust | Content | Medium | Critical | Human review; advanced-only ambiguity; emergency disable | Arabic Reviewer | Open | Hint/wrong-target spikes
R05 | Local Solver too CPU/battery intensive | Performance | Medium | High | Benchmark; workers/isolates; optimize; remote/cached fallback | Game Engineer | Open | Latency/battery regression
R06 | Cloud sync corrupts wallet/progression | Data | Low | Critical | Server ledger, revisions, idempotency, conflict tests | Backend Engineer | Open | Balance mismatch
R07 | Purchase/ad duplicate grants | Monetization | Low | Critical | Idempotency, validation, reconciliation | Backend Engineer | Open | Duplicate transaction alerts
R08 | Interstitial cadence harms retention | Product | Medium | High | Adaptive guardrails, natural breaks, analytics | Product Owner | Open | Post-ad exits
R09 | Scope exceeds solo/small-team capacity | Delivery | High | High | P0/P1 boundary and milestone gating | Product Owner | Open | Backlog growth
R10 | Unapproved decisions become hard-coded | Governance | Medium | High | Decision register, ADRs, configurable tunables | Tech Lead | Open | TBD values in code
R11 | CMS over-engineering delays game | Delivery | Medium | High | Prioritize CRUD/review/solver/publish | Product Owner | Open | Admin effort dominates
R12 | Store/privacy policy changes near launch | Compliance | Medium | High | Recheck policies before submission | Product/Mobile Engineer | Open | Store/SDK changes

## Decision Register
Decision Register — aligned to Final Decision Register v1.1
CONFIRMED items are closed for planning. Real-money prices and Firebase quotas/billing remain TBD. Calendar/staffing TBD.
Decision ID | Area | Decision Needed | Current Proposal | Required Before | Status | Notes
D01 | Client | Mobile framework | Flutter | Production coding | CONFIRMED | Register v1.1
D02 | Client | State management | Riverpod | Production coding | CONFIRMED | Register v1.1
D03 | Client | Local database | Drift / SQLite | Persistence implementation | CONFIRMED | Register v1.1
D04 | Solver | Solver algorithm | Benchmark DFS/IDA*/A* hybrid variants | Solver freeze | TBD | Prototype first.
D05 | Solver | Execution location | Hybrid on-device + reusable core; backend fallback if needed | Architecture freeze | CONFIRMED | Exact fallback rules TBD
D06 | Backend | Backend stack | Firebase-first serverless (Functions/Run); ASP.NET+PG DEFERRED | Backend implementation | CONFIRMED | Azure/ASP.NET/PG superseded for MVP
D07 | Cloud | Cloud provider | Firebase / Google Cloud managed services | Infrastructure implementation | CONFIRMED | No Azure in MVP baseline
D08 | Data | Primary database | Cloud Firestore (no always-on relational DB in MVP) | Backend implementation | CONFIRMED | PostgreSQL deferred
D09 | Cloud Save | Active Attempt cloud policy | Local-first active Attempt; cloud durable progression/economy | Sync implementation | CONFIRMED | Domain-specific conflict policy approved
D10 | Economy | Starting Coins | 300 | Economy freeze | CONFIRMED | Register v1.1
D11 | Economy | Starting Hints | 3 | Economy freeze | CONFIRMED | Register v1.1
D12 | Economy | Hint Coin price | 75 Coins | Economy freeze | CONFIRMED | Register v1.1
D13 | Economy | Extra Moves grant/pricing | +5; 150/250 Coins; max 2 | Economy freeze | CONFIRMED | Register v1.1
D14 | Economy | Dead-End Rescue behavior/cost | Solver-Guided Recovery; 200 Coins; max 1; no Mid-Level Reshuffle MVP | Gameplay/economy freeze | CONFIRMED | Register v1.1
D15 | Monetization | Rewarded Coin grant/cap | 100 Coins; 3/day | Monetization freeze | CONFIRMED | Register v1.1
D16 | Ads | Interstitial cadence | Adaptive; ~3–5 levels; max 3/session; Remove Ads=interstitials only | Monetization freeze | CONFIRMED | Register v1.1
D17 | IAP | Coin Pack ladder | 1k / 3k / 7k / 15k; real-money prices TBD | Store setup | CONFIRMED / TBD prices | Amounts confirmed; prices TBD
D18 | Content | MVP launch content quantity | 5 Chapters / 250 Level Definitions | Content plan | TBD | Prior proposal only.
D19 | MVP | P1 Daily features in launch | Daily Reward + Challenge + Streak + notifications | Release scope freeze | TBD | P1 boundary.
D20 | Platform | Minimum iOS/Android versions | Not selected | QA/device matrix | TBD | Select after client stack.
D21 | Analytics | Analytics/crash providers | Managed provider TBD | Instrumentation | TBD | No vendor selected.
D22 | CMS | Admin frontend | Angular or React | CMS implementation | TBD | Proposal only.
D23 | Daily | Timezone/eligibility policy | Server-authoritative; timezone TBD | P1 implementation | TBD | Required for daily systems.
D24 | Offline | Offline economy/ad behavior | Core gameplay offline; transactional behavior TBD | Architecture freeze | TBD | Needs cloud/economy decision.
D18 | CMS | Admin stack | Angular + Microsoft Entra ID + MFA; audit 2y; Firebase/GCP boundaries | CMS implementation | CONFIRMED | Register v1.1
D19 | Analytics | Analytics/observability | Firebase Analytics + BigQuery; Crashlytics; GCP-native logs (not Azure App Insights) | Instrumentation | CONFIRMED | Quotas/billing TBD
D20 | Scope | Daily at launch | Daily Reward/Challenge/Streak + Smart Notifications P0; Events post-launch | Launch scope | CONFIRMED | Quiet hours 22:00–09:00
D21 | QA | Release QA bar | S0–S4; blockers; 10k+ critical sims; iOS15/API26 portrait; Engine/Solver parity | Release | CONFIRMED | Register v1.1
D22 | Ops | Firebase quotas/billing | Enable budgets/alerts; exact limits TBD | PROD rollout | TBD | Still open operational tuning

## DoR-DoD
Definition of Ready / Definition of Done
Decision Align v1.1: severity S0–S4 and release blockers are CONFIRMED.
Type | Check | Required? | Notes
Story DoR | Acceptance criteria are testable | Yes | No ambiguous outcome.
Story DoR | Dependencies identified | Yes | Include feature/technical dependencies.
Story DoR | Blocking product decisions resolved | Yes | TBD allowed only for explicit discovery/spike.
Story DoR | UX/content inputs available | Yes | Use approved source documents.
Story DoD | Implementation complete | Yes | Matches accepted contract.
Story DoD | Unit/integration tests pass | Yes | Critical domain logic automated.
Story DoD | Analytics/error states implemented where required | Yes | No silent failure.
Story DoD | Arabic/RTL verified where player-facing | Yes | When applicable.
Story DoD | No blocker/critical defect | Yes | S0–S4 confirmed; any S0 or unresolved core-path S1 blocks release.
Level DoR | Config/content/difficulty target defined | Yes | Move Limit fixed.
Level DoD | Solver simulation passes | Yes | Accepted boards solvable within Move Limit.
Level DoD | Human Arabic/semantic review passes | Yes | AI never auto-publishes.
Level DoD | Device/playtest validation passes | Yes | Fairness and pacing checked.
Release DoD | Store/purchase/cloud/content smoke passes | Yes | Migration/rollback ready.

## MVP Scope Matrix
MVP Scope Matrix
Decision Align v1.1: P0 includes Daily Reward/Challenge/Streak/Notifications. Temporary Events remain post-launch.
Epic ID | Epic | Phase | P0 | P1 | Notes
E01 | Product & UX Foundation | MVP-P0 | Yes | No | Core MVP baseline
E02 | Arabic Content System | MVP-P0 | Yes | No | Core MVP baseline
E03 | Game Engine | MVP-P0 | Yes | No | Core MVP baseline
E04 | Solver | MVP-P0 | Yes | No | Core MVP baseline
E05 | Level Generator & Difficulty | MVP-P0 | Yes | No | Core MVP baseline
E06 | Tutorial & Onboarding | MVP-P0 | Yes | No | Core MVP baseline
E07 | Main Journey & Chapters | MVP-P0 | Yes | No | Core MVP baseline
E08 | Economy & Rewards | MVP-P0 | Yes | No | Core MVP baseline
E09 | Gameplay Assistance & Recovery | MVP-P0 | Yes | No | Core MVP baseline
E10 | Monetization | MVP-P0 | Yes | No | Core MVP baseline
E11 | Identity, Account & Cloud Save | MVP-P0 | Yes | No | Core MVP baseline
E12 | Backend Platform | MVP-P0 | Yes | No | Firebase-first; Azure/ASP.NET/PG out of MVP
E13 | Admin / CMS | MVP-P0 | Yes | No | Core MVP baseline
E14 | Analytics & Observability | MVP-P0 | Yes | No | Core MVP baseline
E15 | Daily Reward | MVP-P0 | Yes | No | Launch P0 per Register v1.1
E16 | Daily Challenge | MVP-P0 | Yes | No | Launch P0 per Register v1.1
E17 | Daily Streak & Smart Notifications | MVP-P0 | Yes | No | Launch P0 per Register v1.1
E18 | QA & Automated Validation | MVP-P0 | Yes | No | Core MVP baseline
E19 | DevOps, Environments & Release | MVP-P0 | Yes | No | Core MVP baseline
E20 | Security, Privacy & Accessibility | MVP-P0 | Yes | No | Core MVP baseline

## Read Me
Workbook Guide
Use this as a planning baseline, not as approval of newly introduced assumptions.
Topic | Guidance
Purpose | Translate the Solitaire specifications into an executable MVP Product Backlog / WBS.
Decision discipline | CONFIRMED = previously approved. PROPOSED/TBD = recommendation only.
Story Points | Planning placeholders. Recalibrate after a technical prototype/first sprint.
Hours | Story Points × Hours per Story Point from Estimation Inputs.
Cost | Hours × Hourly Rate. Hourly Rate defaults to 0 until you enter it.
P0 / P1 | P0 = launch-critical including Daily systems (Register v1.1). Temporary Events are post-launch.
Dependencies | Review dependency register before scheduling epics.
Open Decisions | Resolve blocking Decision Register items before implementation freeze.
Recommended next step | Approve decisions, then add dates/owners and convert milestones into sprint plan.
Decision Align v1.1 | Firebase-first rebase: backend tasks retargeted to Auth/Firestore/Storage/Functions/Run/FCM/Remote Config; Daily moved to P0; Azure/ASP.NET/PG/K8s/Redis/broker marked out of MVP. Dates/staffing still TBD.

## Decision Align v1.1
Decision Align v1.1 — Firebase-First Rebase
Source | Final Decision Register Arabic Solitaire Association v1.1
Date applied | 2026-08-21
Change | Detail
Backend epic E12 | Retargeted from ASP.NET/Azure-style APIs to Firebase Auth, Firestore, Storage, Cloud Functions/Cloud Run, FCM, Remote Config
Scope reduction | Always-on Azure/ASP.NET/PostgreSQL/Container Apps/Bicep/Redis/K8s/Message Broker out of MVP; effort stays allocated to serverless Firebase/GCP tasks (reallocation, not invented calendar)
Daily E15–E17 | Moved MVP-P1 → MVP-P0 (launch)
Analytics E14 | Firebase Analytics + BigQuery + Crashlytics + GCP-native observability
CMS E13 | Angular + Entra ID; audit 2 years; Firebase/GCP security boundaries
Monetization | Remove Ads=interstitials only; IAP validation via Functions/Run; economy amounts confirmed; real-money prices TBD
QA | S0–S4, release blockers, 10k+ critical sims, iOS15/API26 portrait, Engine/Solver parity
Still TBD | Real-money prices; Firebase quotas/billing; staffing; calendar dates
Dashboard recalculated | P0 items=624, P1 items=0, P0 SP=3000, P1 SP=0, P0 hours=18000, P1 hours=0